## Slide 1
Prepared by Dr. Amira Elfekky
Project Time Management
Lecture 1
PMG 212
مقرر: إداره وقت المشروع

## Slide 2
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 3
8 steps to effective project time management
Chapter
1
  1. Plan your project
  2. Define your deliverables
  3. Organize project tasks
  4. Create a timeline
  5. Assign jobs
  6. Use project planning tools
  7. Communicate regularly
  8. Minimize distractions

## Slide 4
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 5
The Concept of Project Management Understanding Project Management
In order to understand project management, one must begin with the definition of a project.
A project can be any series of activities and tasks.
Chapter
1

## Slide 6
Meaning of “ Project “
Chapter
1
A project: is a temporary endeavor undertaken to create a unique product, service, or result.
Project characteristic:
  Projects are temporary.
  Has definite beginning and end, the end is reached when the project’s objective have been achieved.
  Projects are unique.
  Every project creates a unique product, service, or results.
  Progressively elaborated.
  Progressively: proceeding in steps.
  Elaborated: worked with care and detail.

## Slide 7
Meaning of “ Project “
Chapter
1
The temporary nature of projects indicates that a project has a definite beginning and end.
Temporary does not necessarily mean a project has a short duration.
The end of the project is reached when one or more of the following is true:
  The project’s objectives have been achieved;
  The objectives will not or cannot be met;

## Slide 8
Project Ending
Chapter
1
  Funding is exhausted or no longer available for allocation to the project;
  The need for the project no longer exists (e.g., the customer no longer wants the project completed, a change in strategy or priority ends the project, the organizational management provides direction to end the project);
  The human or physical resources are no longer available; or The project is terminated for legal cause or convenience.

## Slide 9
Meaning of “ Project time management“
Chapter
1
  Project time management is the process of planning, scheduling and overseeing activities required to complete a project. Organizations use it to define milestones, meet deadlines, stay within budget and work toward project goals. It’s typically handled by a designated project manager, but also involves team managers responsible for helping employees with their own time management skills.

## Slide 10
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 11
History of Project Management
Chapter
1
  Practiced since ancient times (Great Pyramids).
  Emerged as a formal discipline with complex projects.
  Early pioneers: Henry L. Gantt and Henri Fayol.
  Developed principles still used today.

## Slide 12
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 13
Benefits of project management
Chapter
1
● Identification of functional responsibilities to ensure that all activities are accounted for, regardless of personnel turnover
● Minimizing the need for continuous reporting
● Identification of time limits for scheduling

## Slide 14
Benefits of project management
Chapter
1
● Identification of a methodology for trade-off analysis
● Measurement of accomplishment against plans
● Early identification of problems so that corrective action may follow
● Improved estimating capability for future planning
● Knowing when objectives cannot be met or will be exceeded

## Slide 15
Benefits of project time management
Chapter
1
Effective task management doesn’t just lead to more productive employees. With the right strategies in place, you’ll also experience:
Shorter deadlines: Proper time management makes it easier to complete tasks on time, ensuring customer satisfaction and helping you maintain a competitive edge in your market.
Better use of resources: Managing project timelines also helps improve employee efficiency as you redistribute unbalanced workloads. By keeping your finger on the pulse of all activities, you’ll see if someone’s carrying more than their fair share of the burden

## Slide 16
Benefits of project time management
Chapter
1
Effective task management doesn’t just lead to more productive employees. With the right strategies in place, you’ll also experience:
Controlled budgets: Time management helps control project costs by ensuring timely completion of activities and preventing delays that would otherwise lead to additional expenses.
Improved communication: By adhering to project schedules, project managers have the details they need to update stakeholders and set clear expectations.

## Slide 17
Benefits of Proper Planning
Chapter
1
• Provides waterfall structure.
• Reduces risks and unforeseen issues.
• Improves team buy-in.
• Establishes performance baseline.

## Slide 18
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 19
Approaches to Project Management “Project Management Life Cycle”
Initiation
Planning
Controlling
Execution
Closeout
Chapter
1

## Slide 20
1st Project initiation
Chapter
1
● Selection of the best project given resource limits
● Recognizing the benefits of the project
● Preparation of the documents to sanction the project
● Assigning of the project manager

## Slide 21
2nd Project planning
Chapter
1
● Definition of the work requirements
● Definition of the quality and quantity of work
● Definition of the resources needed
● Scheduling the activities
● Evaluation of the various risks

## Slide 22
3rd Project execution
Chapter
1
● Negotiating for the project team members
● Directing and managing the work
● Working with the team members to help them improve

## Slide 23
4th Project monitoring and control
Chapter
1
● Tracking progress
● Comparing actual outcome to predicted outcome
● Analyzing variances and impacts
● Making adjustments

## Slide 24
5th Project closure
Chapter
1
● Verifying that all of the work has been accomplished
● Contractual closure of the contract
● Financial closure of the charge numbers
● Administrative closure of the paper work

## Slide 25
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 26
Successful project management
Chapter
1
Successful project management can then be defined as having achieved the project objectives:
● Within time
● Within cost
● At the desired performance/technology level
● While utilizing the assigned resources effectively and efficiently
● Accepted by the customer

## Slide 27
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 28
Obstacles of project management
Chapter
1
● Project complexity
● Customer’s special requirements and scope changes
● Organizational restructuring
● Project risks
● Changes in technology
● Forward planning and pricing

## Slide 29
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 30
Project Management
Chapter
1
Project management can mean different things to different people.
Quite often, people misunderstand the concept because they have ongoing projects within their company and feel that they are using project management to control these activities.

## Slide 31
Project Management
Chapter
1
In such a case, the following might be considered an appropriate definition:
Project management is the art of creating the illusion that any outcome is the result of a series of predetermined, deliberate acts when, in fact, it was dumb luck.

## Slide 32
Project Management
Chapter
1
Project management is designed to make better use of existing resources by getting work to flow horizontally as well as vertically within the company.

## Slide 33
Project Management
Chapter
1
Project management is the planning, organizing, directing, and controlling of company resources for a relatively short-term objective that has been established to complete specific goals and objectives.

## Slide 34
Project Management
Chapter
1
Classical management is usually considered to have five functions or principles:
● Planning
● Organizing
● Staffing
● Controlling
● Directing

## Slide 35
Project Management
Chapter
1
Today, the definition of project success has been modified to include completion:
● Within the allocated time period
● Within the budgeted cost
● At the proper performance or specification level
● With acceptance by the customer/user

## Slide 36
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 37
PROJECT MANAGER’S ROLE
Chapter
1
The project manager is responsible for coordinating and integrating activities across multiple, functional lines.
The integration activities performed by the project manager include:
● Integrating the activities necessary to develop a project plan

## Slide 38
PROJECT MANAGER’S ROLE
Chapter
1
The integration activities performed by the project manager include:
● Integrating the activities necessary to execute the plan
● Integrating the activities necessary to make changes to the plan

## Slide 39
Integration management.
Chapter
1

## Slide 40
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 41
FUNCTIONAL MANAGER’S ROLE
Chapter
1
● The functional manager has the responsibility to define how the task will be done and where the task will be done (i.e., the technical criteria).

## Slide 42
FUNCTIONAL MANAGER’S ROLE
Chapter
1
● The functional manager has the responsibility to provide sufficient resources to accomplish the objective within the project’s constraints (i.e., who will get the job done).

## Slide 43
FUNCTIONAL MANAGER’S ROLE
Chapter
1
● The functional manager has the responsibility for the deliverable.

## Slide 44
The Concept of Project Management Understanding Project Management
Meaning of “ Project “
Meaning of “ Project time management“
History of Project Management
Benefits of project management
Benefits of project time management
Benefits of Proper Planning
Approaches to Project Management “Project Management Life Cycle” The Initiating Process
The Planning Process
The Executing Process
The Monitoring and Controlling Process
The Closing Process
Successful project management
Obstacles of project management
Project Management
Role of the Project Manager
Role of the Functional Manager
Goals of the Project
Agenda

## Slide 45
Project Goals
Chapter
1
Contractual performance obligations.
Financial objectives: profit and cost control.
Prevent delays and claims.
Maintain team focus on objectives.

## Slide 46
Thank You