## ورقة1
student name |  | عاليه بنت متعب غازي العتيبي | student Id | 2021206137
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | A serious traffic accident involving the transportation of fuel/explosivesEstimated deaths and emptying of an area of the station about 3 km of the materials used. Possibility to release up to 50 tons of liquid fuel in local envernment | high | low | Medium | police emergency plans Highway egency plans liaison with the family of staff Company emergency respose Local authority emergency plan | safety and risk management | مشروع مترو الرياض
2 | OPPORTUNITIES | Project resources inadequate with insufficient staff to support project. | moderate | high | Medium | Project management team established with support from other staff departments, including HR and finance. | safety and risk management | مشروع مترو الرياض
3 | THREATS | Stormy winds and rain affect transportation routes for up to 6 hours. Expect that most roads in the vicinity will be closed or restricted. Travel time will be extended and bus delays may occur for passengers | moderate | moderate | Medium | police emergency plans Highway egency plans Investigate weather forcast liaison with the family of staff Notification to customers | safety and risk management | مشروع الهايبر لوب
4 | OPPORTUNITIES | Project resources has insufficient funds for the necessary external professional technical advice. | low | high | Medium | Sufficient budget identified to find external advice. | safety and risk management | مشروع الهايبر لوب
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low