## Slide 1
Prepared by Dr. Amira Elfekky
Project Time Management
Lecture 10
PMG 212
مقرر: إداره وقت المشروع

## Slide 2
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 3
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 4
Introduction to Risk Management
All projects contain some amount of risk. Risk is an uncertain event that can positively or negatively affect project goals.
Example – Apple: Apple faces supply chain risks when major suppliers experience delays. This uncertainty affects product launch timelines.
10
Chapter

## Slide 5
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Project Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 6
Why Risk Management Is Important
Risk cannot be fully eliminated.
Most risks have negative consequences.
Some risks can be predicted and planned for; others cannot.
Example – Toyota: After the 2011 earthquake, Toyota realized some risks (natural disasters) cannot be fully controlled. They improved supplier diversification to reduce future impact.
10
Chapter

## Slide 7
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 8
Sources of Risk (with Examples)
10
Chapter
Internal Risks
Poor planning (Example: Boeing’s 737 MAX development delays)
Design errors (Example: Samsung battery design issue – Note 7 recall)
External Risks
Supply shortages (Toyota 2021 semiconductor shortage)
Economic changes (Amazon warehouse expansion delays during inflation)
Regulatory changes (Meta privacy regulation impacts in Europe)
Weather disasters (Apple suppliers hit by 2022 floods in China)

## Slide 9
Sources of Construction & Project Risks
10
Chapter
Risks may come from:
Owners
Designers
Contractors
Subcontractors
Weather
Economic changes
Material shortages

## Slide 10
Sources of Construction & Project Risks
10
Chapter
Example – Samsung: Samsung faced material and quality risk with the Note 7 battery issue. Supplier quality problems directly affected project outcomes.

## Slide 11
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 12
Objectives of Risk Management
10
Chapter
The goal is to:
Identify risks early
Reduce likelihood
Minimize impact
Improve project control
Increase chances of meeting time & budget goals
Example – Amazon: Amazon predicts delivery risks during Black Friday using analytics to minimize delays and protect promised delivery dates.

## Slide 13
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 14
Risk Assessment
10
Chapter
Evaluate each risk by:
  Probability (1–5 scale)
  Impact (1–5 scale)
High probability + high impact = High priority
Output: Risk Severity Matrix

## Slide 15
Risk Assessment
10
Chapter
Example of Probability vs Impact
10% chance of losing $100,000 = serious
90% chance of losing $1,000 = less serious → Impact often more critical than probability

## Slide 16
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 17
Components of Risk Management
10
Chapter
Risk Identification
Risk Assessment
Risk Response Planning
Risk Monitoring & Control
Example – Microsoft: Microsoft identifies and monitors cybersecurity risks 24/7 to prevent system failures.

## Slide 18
Risk Identification
10
Chapter
Team lists all possible risks during planning.
Includes internal vs. external risks.
WBS is used to ensure no activity is missed.
Use risk profiles and historical data.
Example – Tesla: Tesla identifies technical risks early when designing new batteries by testing prototypes before mass production.

## Slide 19
Risk Assessment
Assess probability and impact of each risk.
Some risks are minor; others need deep evaluation.
Scenario analysis is used to classify severity.
Both probability and impact are rated 1–5.
Example – Google: Google assessed the market and privacy risks for Google Glass. High impact led them to discontinue the consumer version.
10
Chapter

## Slide 20
10
Chapter
Risk Severity Matrix
Combines probability + impact
High probability + high impact = highest priority
Helps project managers focus on critical risks
Example – Samsung (Quality Risk): The battery defect in Note 7 scored high impact & high probability → required immediate global recall.
Risk Assessment

## Slide 21
Risk Response Planning
10
Chapter
Choose the best plan:
Mitigate – reduce probability
Avoid – remove the risk altogether
Transfer – move risk to another party
Share – multiple parties handle the risk
Retain – accept and plan for it

## Slide 22
Risk Response Planning
10
Chapter
Mitigation
Reduce likelihood and/or impact
Understand the cause
Provide alternatives to reduce effect on cost or time

## Slide 23
Risk Response Planning
10
Chapter
Avoidance
Change plan to remove risk source
Choose proven methods
Sometimes: do not bid the project

## Slide 24
Risk Response Planning
10
Chapter
Transfer
Give responsibility to a more capable party
Examples:
  Subcontracting
  Contract clauses (e.g., No-Damage-for-Delay)

## Slide 25
Risk Response Planning
10
Chapter
Sharing
Joint ventures
Partnering with owner
Shared cost and responsibility

## Slide 26
Risk Response Planning
10
Chapter
Retention
Risk stays with original party
Used when probability is low or risk is manageable
Requires a ready action plan

## Slide 27
Risk Response Planning
10
Chapter
Sharing
Joint ventures
Partnering with owner
Shared cost and responsibility

## Slide 28
Risk Response Control
10
Chapter
Monitor risks continuously
Check for trigger events
Adjust plans as needed
Regular updates in meetings and reports
Assign clear responsibility (“Who handles what?”)

## Slide 29
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 30
What Is Project Closeout?
10
Chapter
What Is Project Closeout?
Final step in the construction project life cycle
Ensures orderly transfer from contractor → owner
Includes documentation, inspections, payments, training, warranties
Begins from the pre-construction phase, not at the end

## Slide 31
What Is Project Closeout?
10
Chapter
What is Project Closeout?
Final phase of the project life cycle
Ensures an orderly, documented transition from contractor → owner
Includes: physical work, administrative tasks, documentation, lessons learned
Starts early during pre-construction
🌍 Example: Microsoft Data Center Projects begin collecting closeout documents from the first construction month to avoid delays at handover.

## Slide 32
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 33
Initiation of Project Closeout
10
Chapter
Begins during pre-construction
Closeout meeting with subcontractors & vendors
Review of Section 01 70 00 requirements (closeout procedures, cleaning, testing, warranties, etc.)
🌍 Example: Tesla Gigafactory introduces closeout checklists at the start of the project so suppliers know documentation expectations months in advance.

## Slide 34
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 35
Closeout Checklist
10
Chapter
Includes:
Final cleaning
Starting systems
Testing & commissioning
Punchlist & substantial completion
Warranty items
As-built drawings
Maintenance manuals
Spare parts
Bond releases & insurance
Extra stock materials

## Slide 36
Closeout Checklist
10
Chapter
🌍 Example: Siemens Energy requires full testing & commissioning reports before equipment handover on all power plant projects.

## Slide 37
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 38
Building a Closeout Matrix
Matrix includes:
Document name
Submission date
Date requested
Date received
Sent to owner? (Y/N)
Person responsible
10
Chapter

## Slide 39
Building a Closeout Matrix
Amazon Web Services (AWS) Construction Team uses a digital matrix via Procore to track all subcontractor documents.
10
Chapter

## Slide 40
Objectives of Closeout
Smooth transition to owner
Reduce owner anxiety
Ensure all contractual and technical requirements are complete
Build long-term relationship
🌍 Example: Dubai Expo 2020 Projects emphasized orderly handover to avoid delays and ensure positive relations with global partners.
10
Chapter

## Slide 41
Risks of Poor Closeout
Owner may withhold payments
Retainage delays
Claims or disputes
Damage to contractor reputation
🌍 Example: UK NHS Hospital Projects delayed final payments for months because incomplete O&M manuals were not submitted on time.
10
Chapter

## Slide 42
Two Types of Closeout
1. Contract Closeout
Verify contract obligations
Match POs with invoices
Review change orders
Close vendor agreements
2. Administrative Closeout
Financial reconciliation
Payment records
Archive documents
Lessons learned
10
Chapter

## Slide 43
Two Types of Closeout
🌍 Example: Bechtel Corporation uses a dual closeout: contract reviews + administrative audits to avoid disputes in mega-projects.
10
Chapter

## Slide 44
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 45
Contract Closeout Example
Global Example:
Apple Park Construction
Contractor had to submit 100% verified change orders and warranty records before Apple released final payment.
PO-to-invoice matching was mandatory for every vendor.
10
Chapter

## Slide 46
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 47
Administrative Closeout Example
Global Example: Google Office Campus Projects
Use automated financial reconciliation in Oracle systems
Archive everything digitally
Final job cost reports shared with HQ
10
Chapter

## Slide 48
Part 1
Introduction to Risk Management
Why Risk Management Is Important
Sources of Risks
Objectives of Risk Management
Risk Assessment
Components of Risk Management
Part 2
What Is Project Closeout?
Initiation of Project Closeout
Closeout Checklist
Building a Closeout Matrix
Contract Closeout Example
Administrative Closeout Example
Archiving Project Files
Agenda

## Slide 49
Archiving Project Files
Files include:
Contracts
Change orders
Correspondence
RFIs
Payments
Schedules
Meeting minutes
Lessons learned
🌍 Example: Saudi Aramco keeps digital archives for 10–15 years due to long-term operational needs of oil & gas facilities.
10
Chapter

## Slide 50
Lessons Learned Meetings
Review successes and issues
Identify root causes
Document cost/schedule differences
Recognize team achievements
Share best practices for future projects
🌍 Example: NASA conducts formal “Post-Project Reviews” for all missions to capture lessons for future launches.
10
Chapter

## Slide 51
Lessons Learned Example
Global Example: Hyundai Engineering & Construction
Learned that early supplier integration reduced delays by 18%
Standardized the process for all future global projects
10
Chapter

## Slide 52
Lessons Learned Documentation
Must include:
Issue description
Impacts (cost/schedule)
Root cause
Corrective actions
References
Opportunities (if positive event)
🌍 Example: IBM Data Center Builds maintain a global lessons-learned library shared across all continents.
10
Chapter

## Slide 53
Project Closeout Report
Summarizes project baselines & achievements
Records schedule & cost variances
Includes lessons learned
Written 60–90 days after project completion
🌍 Example: Qatar FIFA World Cup Projects produced closeout reports to ensure stadium and infrastructure data remain accessible for future events.
10
Chapter

## Slide 54
Summary
Closeout is as important as planning
Begins early in the project
Ensures smooth handover to owner
Includes contract + administrative closeout
Lessons learned improve future performance
Global companies rely on strong closeout systems
10
Chapter

## Slide 55
Thank You