## Slide 1
Project Time Management
Lecture 6
PMG 212
Prepared by Dr. Amira Elfekky

## Slide 2
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 3
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 4
Purpose of a Performance Measurement Baseline
www.midocean.ae
06
Roadmap for project execution
Integration of project components
Basis for change management
Project communication
Basis for project status and metrics
Chapter

## Slide 5
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 6
Components of the Performance
Baseline
www.midocean.ae
06
All five components interact and must be combined in baselining.
Project team members must be made aware of the components within their area of responsibility.
Chapter

## Slide 7
Agenda
www.midocean.ae
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning

## Slide 8
Components and Assembly of the Performance Baseline
www.midocean.ae
06
Chapter

## Slide 9
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 10
Scope
www.midocean.ae
06
Defines the work the contractor or supplier is required to complete
  Statement of Work
  Scope determines the cost and schedule
  Creation of Work breakdown structure
Chapter

## Slide 11
Scope – Case study -1
www.midocean.ae
06
Chapter

## Slide 12
Scope – Case study - 2
www.midocean.ae
06
Chapter

## Slide 13
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 14
Contract Terms and Conditions (CTC)
www.midocean.ae
06
Contract terms and conditions address:
  Rights and obligations
  Contract form and function
  Risk allocation
  Contract management process, including dispute resolution
Chapter

## Slide 15
Contract Terms and Conditions (CTC)
www.midocean.ae
06
Contract terms and conditions address:
  Payment terms
  Quality requirements
  Acceptance and testing requirements
  Reporting requirements
Chapter

## Slide 16
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 17
Project Execution Plan (PEP)
www.midocean.ae
06
Defines the execution approach
  Identifies how engineering will be carried out
  Identifies how equipment and materials will be acquired
  Identifies how construction will be completed
Chapter

## Slide 18
Project Execution Plan (PEP)
www.midocean.ae
06
Chapter
Defines the execution approach
  Identifies what all functions (E, P, C, PC, Contracts, Startup, and others) will do in delivering the project and how they will do it
  Describes how handoffs, interfaces, and integration between functions will work

## Slide 19
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 20
Schedule
www.midocean.ae
06
Management Schedule (Level I) includes:
  Major milestones
  Long lead items
Control Schedule (Level III)
  Part of the contract
  The CS is a package containing:
    Major milestones
    Engineering Work Packages (EWP)
    Procurement and Long lead items
Chapter

## Slide 21
Schedule
www.midocean.ae
06
Control Schedule (Level III)
  The CS is a package containing:
    Construction Work Packages
    Critical path activities
    Resources loaded schedule
    Progress curves
    Bulk commodity curves (concrete, structural steel, piping, wire & cable, etc.)
Chapter

## Slide 22
Schedule
www.midocean.ae
06
Always provide the Basis of Schedule (assumptions, exclusions, allowances, etc.).
Level II Summary Schedules and Level IV Medium Term Schedules are used when needed.
Chapter

## Slide 23
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 24
Work Breakdown Structure
www.midocean.ae
06
The Work Breakdown Structure (WBS) is a hierarchical code structure representing the entire work scope of a project. The WBS:
  Integrates project data from Engineering, Procurement, Construction, and Startup.
Chapter

## Slide 25
Work Breakdown Structure
www.midocean.ae
06
  Is used to separate project scope into manageable subsections, facilitate communication, and identify integration points for project plans.
  Provides a systematic approach to ensure key scope and activities are not omitted.
Chapter

## Slide 26
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 27
Work Breakdown Structure Benefits
www.midocean.ae
06
Facilitates systematic planning
Removes project complexity by allocating scope
Provides a framework for:
    Defining specific tasks
    Linking activities and resources
    Facilitating communication
    Allowing integration of project plans
Chapter

## Slide 28
Work Breakdown Structure Example
www.midocean.ae
06
Chapter

## Slide 29
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 30
Organizational Breakdown Structure
www.midocean.ae
06
Takes the WBS and merges with the organization and individuals assigned to the project
Benefits:
      Enables clear assignment of scope to
      team members
      Facilitates ownership and accountability
      Assures all project elements are accounted for
Chapter

## Slide 31
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 32
WBS/OBS Diagram
www.midocean.ae
06
Chapter

## Slide 33
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 34
Ownership
www.midocean.ae
06
PEP
Hold teams accountable (performance)
Manage change
Risk and contingency management
Project Execution Plan adjustments
Team A
Team B
Team C
Team D
The Baseline
Project organized by teams
100% of scope, budget, schedule allocated
Contractor perform
Partners/ subs/ suppliers
PEP
Scope
Schedule
Budget
Chapter

## Slide 35
Alignment and Ownership of the Baseline Benefits
www.midocean.ae
06
Ensure teams know and accept their scope, schedule, and budgets.
Drive ownership.
Ensure that stretch goals and targets are defined and accepted by the teams.
Establish an environment of accountability.
Chapter

## Slide 36
Agenda
Purpose of a Performance Measurement Baseline
Components of the Performance Baseline
Components and Assembly of the Performance Baseline
Scope
Contract Terms and Conditions (CTC)
Project Execution Plan (PEP)
Schedule
Work Breakdown Structure
Work Breakdown Structure Benefits
Organizational Breakdown Structure
WBS/OBS Diagram
Ownership
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 37
The Concept of Rolling Wave Planning
www.midocean.ae

## Slide 38
The Concept of Rolling Wave Planning
www.midocean.ae
06
Rolling wave planning is a project management technique that involves progressive elaboration to add detail to the Work Breakdown Structure (WBS) on an ongoing basis.
At the beginning of the project, near term deliverables are decomposed into individual components (work packages) and defined at the greatest level of detail.
Chapter

## Slide 39
The Concept of Rolling Wave Planning
www.midocean.ae
06
Deliverables and schedule activities that will take place several reporting periods in the future are more broadly defined. For example, Phases 1-2 might be broken down fully in the WBS.
Phases 3-6 might be outlined only to the level of subprojects.
Chapter

## Slide 40
www.midocean.ae

## Slide 41
Thank You