## Slide 1
Prepared by Dr. Amira Elfekky
Project Time Management
Lecture 07
PMG 212
مقرر: إداره وقت المشروع

## Slide 2
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 3
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 4
Introduction to Productivity in Construction
Chapter
07
Labor is the primary driver of construction project performance.
Productivity directly influences CPI (Cost Performance Index) and SPI (Schedule Performance Index).
Productivity measures efficiency — output per unit of input.
In construction, productivity typically varies over time.
Effective labor management determines project success or failure.

## Slide 5
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 6
Understanding Productivity vs. Production
Chapter
07
Production = Total units of work completed.
Productivity = Rate of production (units per labor-hour).
A project can meet production targets but fail productivity targets.
Example: 100 ft installed using double the planned labor = lower productivity.
Productivity impacts earned value and contractor profitability.

## Slide 7
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 8
Measuring Productivity (Production Model Example)
Chapter
07
Daily Output Example: 100 LF per 8-hour workday.
Crew Example: 2 workers × 8 hours = 16 labor-hours.
Productivity = 100 LF ÷ 16 labor-hours.
Result = 6.25 LF per labor-hour.
Productivity models help quantify efficiency mathematically.

## Slide 9
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 10
Productivity Index (PI)
Chapter
07
PI compares planned vs. actual performance.
Formula: PI = Budgeted Work Hours (BWH) ÷ Actual Work Hours (AWH).
PI > 1 → Better than planned performance.
PI < 1 → Underperformance.
Most accurate when applied at labor cost element level.

## Slide 11
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 12
Controllable Factors Affecting Productivity
Chapter
07
Proper planning and task analysis.
Availability of materials, tools, and equipment.
Clear communication and effective supervision.
Adequate training and appropriate crew size.
Safe and well-organized work environment.

## Slide 13
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 14
Uncontrollable Factors Affecting Productivity
Chapter
07
Weather conditions and environmental factors.
Worker health and personal issues.
Economic conditions and regional factors.
Strikes or work stoppages.
Owner/client scope changes.

## Slide 15
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 16
The Results of Uncontrolled Obstacles
Chapter
07
New products introduced into the marketplace too late
Temptation اغراء to make hasty متعجلdecisions that prove to be costly.
Management insisting on earlier and greater return on investment
Greater difficulty in establishing on-target objectives in real time
Problems in relating cost to technical performance and scheduling during the execution of the project

## Slide 17
The Results of Uncontrolled Obstacles
Chapter
07
Decreased profits
Increased manpower needs
Cost overruns, schedule delays, and penalty payments occurring earlier and earlier
An inability to cope with new technology
R&D results too late to benefit existing product lines

## Slide 18
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 19
Project Management: 1985–2009
Chapter
07
About markets, production methods, costs and scientific potentials are related to investment decisions.
All of these factors have combined to produce a king-size managerial headache.
There are just too many crucial decisions to have them all processed and resolved through regular line hierarchy at the top of the organization.

## Slide 20
Project Management: 1985–2009
Chapter
07
Providing the project manager with integrative responsibility resulted in:
● Total accountability assumed by a single person
● Project rather than functional dedication
● A requirement for coordination across functional interfaces
● Proper utilization of integrated planning and control

## Slide 21
Project Management: 1985–2009
Chapter
07
By the 1990s, companies had begun to realize that implementing project management was a necessity, not a choice.
The question was not how to implement project management, but how fast could it be done?

## Slide 22
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 23
Lifecycle Phase for Project Management Maturity
Chapter
07

## Slide 24
1- Embryonic Phase
Recognize need → Awareness that projects require structured management.
Recognize benefits → Understanding how project management improves efficiency, reduces risk, and saves cost.
Recognize applications → Identifying where project management can be applied (construction, IT, R&D).
Recognize what must be done → Initial steps: appoint a project leader, define scope, and plan resources.
Lifecycle Phase for Project Management Maturity
Chapter
07

## Slide 25
2- Executive Management Acceptance Phase
Visible executive support → Leadership must actively endorse project management.
Understanding project management → Executives realize it is not just paperwork, but a strategic tool.
Project sponsorship → Senior managers allocate funding and resources.
Willingness to change business practices → Acceptance that traditional approaches may need updating.
Lifecycle Phase for Project Management Maturity
Chapter
07

## Slide 26
3- Line Management Acceptance Phase
Line management support → Department heads align with project goals.
Commitment from line managers → They assign staff and encourage collaboration.
Line management education → Training managers in project principles and methodologies.
Willingness to release employees for training → Investing in building PM capabilities within the team.
Lifecycle Phase for Project Management Maturity
Chapter
07

## Slide 27
4- Growth Phase
Use of life-cycle phases → Projects progress through defined stages (initiation → planning → execution → closure).
Development of methodology → Adoption of formal frameworks (PMBOK, PRINCE2).
Commitment to planning → Emphasis on detailed schedules, budgets, and risk management.
Minimization of “scope creep” → Keeping projects focused on agreed objectives.
Project tracking system → Using software/tools for monitoring progress.
Lifecycle Phase for Project Management Maturity
Chapter
07

## Slide 28
5- Maturity Phase
Cost/schedule control system → Implementing earned value management (EVM) and dashboards.
Integrating cost and schedule → Coordinating budgets with timelines for realistic forecasts.
Educational programs → Continuous training and certification (PMP, PgMP, Agile).
Outcome → Sustainable project success and an organizational culture of excellence.
Lifecycle Phase for Project Management Maturity
Chapter
07

## Slide 29
The Six Driving Forces that lead recognize the need for Project Management
Chapter
07
Capital projects
Customer expectations
Competitiveness
Executive understanding
New project development
Efficiency and effectiveness

## Slide 30
The components of survival
Chapter
07

## Slide 31
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 32
Project Vs Product
Chapter
07
Introduction to Scope:
Scope defines the boundaries of what will (and won’t) be done.
Divided into Project Scope and Product Scope.
Helps avoid misunderstandings and scope creep.

## Slide 33
Project Vs Product
Chapter
07
Project Scope – Definition
Describes the work required to deliver the final outcome.
Includes all activities, tasks, and deliverables.
Example: “Developing a mobile banking app” → coding, testing, training, deployment.

## Slide 34
Project Vs Product
Chapter
07
Product Scope – Definition
Describes the features and characteristics of the deliverable itself.
Focuses on “what the end product will do.”
Example: “Mobile banking app” → fund transfers, bill payments, biometric login, notifications.

## Slide 35
Project Vs Product
Chapter
07
Project Scope vs Product Scope (Comparison)

## Slide 36
Project Vs Product
Chapter
07
Project Scope – Key Elements
Scope statement → formal description of work.
WBS (Work Breakdown Structure) → breaking down work into manageable parts.
Deliverables list → clear outputs at each stage.
Exclusions → what is NOT part of the project.

## Slide 37
Project Vs Product
Chapter
07
Product Scope – Key Elements
Functional requirements → what the product must do.
Non-functional requirements → performance, quality, security.
Acceptance criteria → conditions for customer sign-off.
User experience (UX) considerations.

## Slide 38
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 39
Maturity and Excellence
Chapter
07
Introduction to Maturity in Project Management
Maturity = structured processes, methods, and standards.
Goal → Predictable outcomes & repeatable success.
Not just experience, but systematic improvement.

## Slide 40
Maturity and Excellence
Chapter
07
Characteristics of Mature Organizations
Standardized methodology across projects.
Consistent use of tools (MS Project, Jira, Primavera).
Trained workforce with certifications.
Effective governance and risk management.

## Slide 41
Maturity and Excellence
Chapter
07
Excellence in Project Management
Continuous stream of successful projects.
Success measured not only in time & cost, but also in customer value.
Creating an environment for success (culture, leadership, tools).

## Slide 42
Maturity and Excellence
Chapter
07
Key Factors Driving Excellence
Leadership commitment.
Integration of projects with strategy.
Investment in people (training, certifications).
Knowledge sharing across projects.

## Slide 43
Maturity and Excellence
Chapter
07
Path to Excellence
Assess current maturity level.
Develop a roadmap for improvement.
Establish a PMO (Project Management Office).
Promote a continuous learning culture.
Align success with company + customer objectives.

## Slide 44
Maturity and Excellence
Chapter
07
● Maturity in project management is the implementation of a standard methodology and accompanying processes such that there exists a high likelihood of repeated successes.
● Organizations excellent in project management are those that create the environment in which there exists a continuous stream of successfully managed projects and where success is measured by what is in the best interest of both the company and the project (i.e.,customer).

## Slide 45
The Growth of Excellence.
Chapter
07

## Slide 46
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 47
Primary Success Factors
Chapter
07
• Within time
• Within cost
• Within quality limits
• Accepted by the customer

## Slide 48
Secondary Success Factors
Chapter
07
• Follow-on work from this customer
• Using the customer’s name as a reference on your literature
• Commercialization تسويقof a product
• With minimum or mutually agreed upon scope changes
• Without disturbing the main flow of work

## Slide 49
Secondary Success Factors
Chapter
07
• Maintaining ethical conduct
• Providing a strategic alignment
• Maintaining a corporate reputation
• Maintaining regulatory agency relations

## Slide 50
Productivity
Introduction to Productivity in Construction
Understanding Productivity vs. Production
Measuring Productivity (Production Model Example)
Productivity Index (PI)
Controllable Factors Affecting Productivity
Uncontrollable Factors Affecting Productivity
The Results of Uncontrolled Obstacles
Project Management: 1985–2009
Lifecycle Phase for Project Management Maturity
Project Vs Product
Maturity and Excellence
Success Factors
The Many Faces of Failure
Agenda

## Slide 51
The Many Faces of Failure
Chapter
07
● Ineffective planning
● Ineffective scheduling
● Ineffective estimating
● Ineffective cost control
● Project objectives being “moving targets”

## Slide 52
Components of Failure (pessimistic planning).
Chapter
07
Project management has planned a level of accomplishment (C) lower than what is achievable given project circumstances and resources (D).
This is a classic under planning situation.
Actual accomplishment (B), however, was less than planned.

## Slide 53
Components of Failure (pessimistic planning).
Chapter
07
0
070
80
100
120

## Slide 54
Components of failure (optimistic planning).
Chapter
07
Here, we have planned to accomplish more than is achievable. Planning failure is again assured even if no actual failure occurs. In both of these situations (overplanning and under planning), the actual failure is the same, but the perceived failure can vary considerably.

## Slide 55
Components of failure (optimistic planning).
Chapter
07
0
070
80
100
120

## Slide 56
The Many Faces of Failure
Chapter
07
Today, most project management practitioners focus on the planning failure term.
If this term can be compressed or even eliminated, then the magnitude of the actual failure, should it occur, would be diminished. A good project management methodology helps to reduce this term.
We now believe that the existence of this term is largely due to the project manager’s inability to perform effective risk management.

## Slide 57
Thank You