## Slide 1
PROJECT MONITORING
Lecture 00
PMG333
Dr. Bassel alhassan
Prepared by
INTRODUCTION TO PROJECT MONITORING

## Slide 2
1 - 2
Lecture
00

## Slide 3
1 - 3
Lecture
00
Failing to Plan is Planning to Fail
Notes: “

## Slide 4
1 - 4
Lecture
00
From Pyramids to Rockets: The Evolution of Project Management Through History
Is Project Management a Modern Science? The designation of Project Management as a formal profession is relatively new, dating back only to the middle of the last century. However, project management as an activity and practice is an ancient process that dates back thousands of years. | 

## Slide 5
1 - 5
Lecture
00
Project Management: Integrating Knowledge, Skills, and Tools to Achieve Result
Project management is the application
of knowledge, skills, tools, and techniques
to project activities to meet the project
requirements. Project management is
accomplished through the appropriate
application and integration of the project
management processes identified
for the project

## Slide 6
1 - 6
Lecture
00
What is a Project?
Definition (PMI): A project is a temporary endeavor undertaken to create a unique product, service, or result
Key characteristics:
Temporary: Has a defined beginning and end
Unique: Creates something new or different
Specific objectives: Clear goals and deliverables
Organized effort: Requires coordination and resources
Practical Examples:
Building construction (12-24 months)
Software development (release date)
Marketing campaign (3-6 months)

## Slide 7
1 - 7
Lecture
00
The Five Phases of Project Management Lifecycle
Phase 1 - Initiation: Define project, obtain authorization
Phase 2 - Planning: Develop detailed plans, define scope, schedule, budget
Phase 3 - Execution: Perform project work, produce deliverables
Phase 4 - Monitoring & Control: Track progress, measure performance
Phase 5 -Closure: Archive knowledge, release resources
Key Principle: Monitoring and control occur throughout all phases

## Slide 8
1 - 8
Lecture
00
Project Monitoring Definition
Definition: Project monitoring is the continuous process of collecting, measuring, and analyzing project performance data
Purpose:
Ensure project stays on track with schedule and budget
Identify issues and risks early
Enable timely corrective actions
Maintain stakeholder confidence
Monitoring vs. Control:
Monitoring: Observation and measurement
Control: Taking corrective actions

## Slide 9
1 - 9
Lecture
00
Project Monitoring Definition
MONITORING
Timing: Continuous and regular throughout the project lifecycle.
Focus: Inputs, activities, outputs, and deliverables.
Core Question: "Is the work being done correctly?" (Compliance).
Example: Did we distribute the food baskets on time as scheduled
EVALUATION
Timing: At specific phases (beginning, middle, end).
Focus: Results and outcomes.
Core Question: "Did the work achieve its intended goal?" (Effectiveness).
Example: Did malnutrition rates decrease in the region?

## Slide 10
Robust Monitoring Improves Performance by 30-40%
1 - 10
Lecture
00
Why Project Monitoring Matters?
Robust Monitoring Improves Performance by 30-40% Key benefit: 30-40% Better Performance (PMI Research) | 

## Slide 11
فا
1 - 11
Lecture
00
The requirement is to deliver ten tables in ten days at a cost of one thousand per table
As a result, one table is delivered daily at a unit cost of one thousand
Case study

## Slide 12
1 - 12
Lecture
00
By day four, the planned completion is four tables at a cost of 4,000
Case study

## Slide 13
1 - 13
Lecture
00
Case study
However, upon reviewing the actual progress on day four, three tables had been completed at a cost of 5,000

## Slide 14
1 - 14
Lecture
00
Actual Cost of Work Performed (ACWP)= 5000
Budget Cost of Work Schedule (BCWS)= 4000
Budget Cost of Work Performed (BCWP)=3000
Case study

## Slide 15
1 - 15
Lecture
00
Schedule Variance (SV)
= BCWP-BCWS
= 3000-4000=-1000<0
behind schedule
Lecture
Case study

## Slide 16
1 - 16
Lecture
00
Cost Variance (CV)
= BCWP-ACWP
= 3000- 5000= -2000<0
over budget
Case study

## Slide 17
1 - 17
Lecture
00
Schedule performance Index (SPI)
= BCWP / BCWS
= 3000/4000=0.75<1
behind schedule
Case study

## Slide 18
1 - 18
Lecture
00
Cost performance Index (CPI)
= BCWP / ACWP
= 3000/5000=0.6<1
over budget
Case study

## Slide 19
1 - 19
Lecture
00
Schedule Variance
S.V = BCWP – BCWS = +ve
Ahead
S.V = BCWP – BCWS = 0.0
As Planned
S.V = BCWP – BCWS = -ve
Behind & Delay
Case study

## Slide 20
1 - 20
Lecture
00
SPI = BCWP / BCWS = > 1
Ahead
SPI = BCWP / BCWS = 1
As Planned
SPI = BCWP / BCWS < 1
Behind & Delay
Schedule Performance Index
Case study

## Slide 21
1 - 21
Lecture
00
Estimated Final Time (EFT)
EFT = TAC / SPI
EFT= 10/0.75= 13.33= 14
Case study

## Slide 22
1 - 22
Lecture
00
Cost Variance
C.V = BCWP – ACWP = +ve
Under Budget
C.V = BCWP – ACWP = 0.0
As Budget
C.V = BCWP – ACWP = -ve
Over Budget
Case study

## Slide 23
1 - 23
Lecture
00
CPI = BCWP / ACWP = > 1
Under Budget
CPI = BCWP / ACWP = 1
As Budget
CPI = BCWP / ACWP < 1
Over Budget
Cost Performance Index
Case study

## Slide 24
1 - 24
Lecture
00
EAC = BAC / CPI
        EAC = 10000 / 0.6=16667(Estimated at complete )
Estimated Cost At Completion (EAC)
  EAC = ACWP+ Original Remaining Budget
            EAC = ACWP + New Budget for the remaining work
Case study

## Slide 25
1 - 25
Lecture
00
ETC = EAC – ACWP(estimated to complete )
ETC= 16667-5000=11667
Estimated To Complete (ETC)
Case study

## Slide 26
1 - 26
Lecture
00
VAC = BAC – EAC
VAC= 10000-16667=-6667
Variance At Completion (VAC)
Variance At Completion= Budget Cost At Completion - Estimated Cost At Completion
Case study

## Slide 27
1 - 27
Lecture
00
Best Practices:
1. Establish clear baseline before execution
2. Collect data regularly (daily to weekly)
3. Measure against plan consistently
4. Analyze trends, not just individual data points
5. Communicate transparently
6. Take corrective action quickly
7. Involve stakeholders throughout
8. Use tools effectively
9. Adapt to changes
10. Document everything
Best Practices for Effective Project Monitoring

## Slide 28
Thank You