## ورقة1
student name |  | Salahalden Yousief Tobbal | student Id | 2021206114
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
10001 | THREATS | Land acquisition | high | moderate | Schedule delay, receiving a lot of complaint from the private owners land | 1 Planning and Design phase, locating the rail paths and corridors in goverment owned lands 2 Execution Phase, conduct sessions of negeogation with the private owners till we reach an fair agreed settlement | Higher management, Stakeholders Team | مشروع مترو الرياض
10002 | THREATS | Required huge and heavy Infrastructure associated with high cost impact to be factional | high | high | Feasibility study, Business case | 1 Minimizing the CAPEX regarding cost of the infrastructure 2 Exploring more alternatives through the R&D department | Board of directors, Higher management and R&D dep. | مشروع الهايبر لوب
10003 | OPPORTUNITIES | Environmentally friendly | high | moderate | Global changing in term of carbon emission | 1 Cooperation with private sector 2 Increasing and raising awareness about cliamte change | Project Manager | مشروع مرآة للطاقة الشمسية
10004 | OPPORTUNITIES | Decrease Cars Traffic in Riyadh City | moderate | high | High society awareness and start using public transportation | 1 Increase the awareness of using Public transportations (Metro and Buses) 2 Encouraging students of using PT by providing affordable membership | PR Manager | مشروع مترو الرياض
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low