## Slide 1
PMG510
Risk Management
Prepared by Dr. Ayman Elmaasarawy
Risk management Standards Lecture 4

## Slide 2
Lecture 3 Summery
Origins of Risk Management
Representation of Risk Management
Enterprise Risk Management
Levels of risk management sophistication
Principles of risk management
Implementing risk management

## Slide 3
Lecture 4 Organization
Risk management process:
Risk management context
Components of the RM context
Scope of the context
Designing a risk register
Risk Management Planning

## Slide 4
Lecture 4 Risk management Standards
Risk management process:
A simple representation of the risk management process is provided by the Figure and a similar process is contained in all of the established risk management standards.

## Slide 5
Lecture 4 Risk management Standards
Risk management process:
In ISO 31000 The pervious diagram is reproduced. It could be argued that the new figure contains elements of the risk management framework, as well as the key stages of the risk management process.

## Slide 6
Lecture 4 Risk management Standards
Risk management context:
There needs to be a clear understanding of the risk management process, followed by a clear definition of the framework that supports the process.
Because the risk management framework is a supportive structure.
it is shown in the next Figure as a series of components built around and supporting the risk management process.

## Slide 7
Lecture 4 Risk management Standards
Risk management context:

## Slide 8
Lecture 4 Risk management Standards
Components of the RM context:
Risk architecture: defines roles, responsibilities, communication and risk-reporting structure.
Risk strategy: Risk strategy, appetite, attitudes and philosophy are defined in the risk management policy
Risk protocols: are defined in the risk guidelines for the organization and include the rules and procedures, as well as the risk management methodologies, tools and techniques that should be used

## Slide 9
Lecture 4 Establishing the Context
Scope of the context :
The components the context are the risk management context, internal context and external context. The relationship between the three contexts is illustrated in the Figure.

## Slide 10
Lecture 4 Establishing the Context
The three components of context may be considered as follows:
1- Risk management context:
Has already been described as the risk architecture, strategy and protocols or the risk management framework within the organization.
This framework must fulfil two functions:
Provide support for the risk management process within the organization;
Ensure that the outputs from the risk management process are communicated to internal and external stakeholders.

## Slide 11
Lecture 4 Establishing the Context
The three components of context may be considered as follows:
2- Internal context:
Internal context refers to the organization itself, the activities it undertakes, the range of skills and capabilities available within the organization, and how it is structured.
Internal stakeholders and their expectations are part of the internal context.
Internal context may be considered to be the strengths and weaknesses within the organization.

## Slide 12
Lecture 4 Establishing the Context
The three components of context may be considered as follows:
2- Internal context:
The FIRM risk scorecard offers one mechanism for evaluating the internal context of an organization, but other approaches may be employed, including a SWOT analysis.
Many organizations use the political, economic, social, technological, legal and environmental/ethical (PESTLE) risk classification system. The PESTLE risk

## Slide 13
Lecture 4 Establishing the Context
The three components of context may be considered as follows:
3- External context :
External context is the environment within which the organization exists.
This environment will include consideration of the business sector within which the organization operates, external stakeholders and their expectations and the external financial environment.
This may be considered to be the opportunities and threats facing the organization.

## Slide 14
Lecture 4 Establishing the Context
Designing a risk register:
A risk register is defined as the ‘document used for recording risk Management process for identified risks’.
The guide adds that the purpose of the risk register is to facilitate ownership and management of each risk.
The risk register will cover the significant risks facing the organization or the project.

## Slide 15
Lecture 4 Establishing the Context
Designing a risk register:
The purpose of the risk register:
is to form an agreed record of the significant risks that have been identified.
Also, the risk register will serve as a record of the control activities that are currently undertaken.
It will also be a record of the additional actions that are proposed to improve the control of the particular risk.

## Slide 16
Lecture 4 Establishing the Context
Designing a risk register:

## Slide 17
Lecture 4 Establishing the Context
Designing a risk register:

## Slide 18
Lecture 4 Project Risk Management Guide

## Slide 19
Project risk management delivers a number of values to the project, including:
Lecture 4 Project Risk Management Guide
Recognizes uncertainty and provides forecasts of possible outcomes.
Produces better business outcomes through more informed decision making.
Has a positive influence on creative thinking and innovation.
Creates opportunities for improved project monitoring and control.
Can aide in addressing concerns with respect to overhead and time.

## Slide 20
Project Risk Management Process & steps:
Planning Project Risk Management Guide
Risk Management Planning:
Risk management planning is the systematic process of deciding how to approach, plan, and execute risk management activities throughout the life of a project.
It is intended to maximize the beneficial outcome of the opportunities and minimize or eliminate the consequences of adverse risk events.

## Slide 21
Project Risk Management Process & steps:
Planning Project Risk Management Guide
2. Identify Risk Events:
Risk identification involves determining and documenting which risks can affect the project.
It may be a simple risk assessment organized by the project team, or an outcome of a formal risk assessment process.

## Slide 22
Planning Project Risk Management Guide
3. Qualitative Risk Analysis:
Qualitative risk analysis involves Project teams assessing identified risks for probability of occurrence and impact on project objectives.
Teams may elicit assistance from subject matter experts or functional units to assess the risks in their respective fields.
Risks are measured by their “quality” in words rather than quantified in numbers.
Project Risk Management Process & steps:

## Slide 23
Planning Project Risk Management Guide
4. Quantitative Risk Analysis:
Quantitative risk analysis is a way of numerically estimating the probability that a project will meet its cost and time objectives.
Quantitative analysis is based on a simultaneous evaluation of the impacts of all identified and quantified risks.
Project Risk Management Process & steps:

## Slide 24
Planning Project Risk Management Guide
5. Risk Response Risk response:
involves developing options and determining actions to reduce threats or enhance opportunities to project objectives.
Actions are identified and assigned to parties that take responsibility for the risk response. This process ensures each risk requiring a response has an “owner.”
The Project Manager and the project team identify a strategy that is best for each risk, and then select specific actions to implement that strategy.
Project Risk Management Process & steps:

## Slide 25
Planning Project Risk Management Guide
6. Risk Monitoring & Control:
Risk monitoring and control tracks identified risks, monitors residual risks, and identifies new risks—ensuring the execution of risk plans and evaluating their effectiveness in reducing risk.
Risk monitoring and control is an ongoing process for the life of the project.
Much of project risk management relies on sound engineering judgment and knowing where to focus energy and resources.
Project Risk Management Process & steps:

## Slide 26
1- Project Risk Management Planning
Lecture 4 Project Risk Management Guide

## Slide 27
1- Project Risk Management Planning
Planning Project Risk Management Guide
Great project risk management requires good planning.
Risk management must commence early in project development and proceed as the project evolves and project information increases in quantity and quality.

## Slide 28
1- Project Risk Management Planning
Planning Project Risk Management Guide
Aim of the project risk Plan :
Identify, assess/analyze, and respond to major risks
Continually monitor project risks and response actions.
Conduct an appropriate number and level of risk assessments to update the Risk Management Plan and evolving risk profile for the project.

## Slide 29
1- Project Risk Management Planning
Planning Project Risk Management Guide
The following figure illustrates how project information develops and evolves over time.
With rising project knowledge comes an understanding that contending with some elements of the project will require significant additional resources.
These elements could involve: scope; environmental mitigation and permitting; rising cost of right of way as corridors develop in advance of the project; utilities; seismic issues; and other elements.

## Slide 30
1- Project Risk Management Planning
Planning Project Risk Management Guide
Evolution of Project Knowledge Through Project Development

## Slide 31
1- Project Risk Management Planning
Planning Project Risk Management Guide
How to Plan for Project Risk Management
Determine the level of risk assessment for your project .
2. Incorporate risk management activities into the project schedule.
3. Make risk management an agenda item for scheduled project meetings.
4. Communicate the importance of risk management to the entire project team.
5. Establish the expectation that risk will be managed, documented, and reported.

## Slide 32
1- Project Risk Management Planning
Planning Project Risk Management Guide
Tips for Risk Management Planning
Risk assessment planning should begin early. There is a minimum level of project knowledge needed to understand what is being assessed.
This varies depending on the point in project development at which the risk assessment is conducted (planning, scoping, design); hence, schedule risk assessments at appropriate times.

## Slide 33
1- Project Risk Management Planning
Planning Project Risk Management Guide
Tips for Risk Management Planning
At a minimum there must be an understood project scope of work, associated project cost estimate – with a basis of estimate complete, and an estimated project schedule.
Allow a budget and time in the schedule for risk assessment, risk management, and risk response activities.
Report on the status of project risk at regularly scheduled project meetings.

## Slide 34
1- Project Risk Management Planning
Planning Project Risk Management Guide
Tips for Risk Management Planning
Know the organization’s tolerance for risk. Are Project Managers (and upper management) risk averse or risk seeking? How much risk is the organization willing to accept? Knowing the answers to these questions will help with risk management and contribute to the decision-making process when determining risk response actions.
Contact the Strategic Analysis and Estimating Office (SAEO) and discuss the possibility of coordinating or integrating project risk assessment with value engineering

## Slide 35
1- Project Risk Management Planning
Planning Project Risk Management Guide
Determine the Level of Risk Assessment

## Slide 36
Conclusion

## Slide 37
Thanks