## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | Corona’s return globally (Amicron) | high | high | Scarcity of manpower | Avoid hiring workers from African countries because Amicron was born from there | HR Manager | مشروع مرآة للطاقة الشمسية
2 | THREATS | Rain and flood | high | high | Construction and structural design | Ensure that materials and designs are resistant to rain and floods and take them into account | Manufacturing & design managers | مشروع مرآة للطاقة الشمسية
3
4 | OPPORTUNITIES | A national project supported by the government | high | high | government support | Benefit from government support, whether it's financially or advisory | Project Manager & Shareholders | مشروع مرآة للطاقة الشمسية
5 | OPPORTUNITIES | The growing demand for energy resources and its scarcity in Oman | high | high | Lack of energy sources | Expanding the project to include a larger proportion of the community | Project Manager & Shareholders | مشروع مرآة للطاقة الشمسية
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low