## Slide 1
Prepared by Dr. Amira Elfekky
Project Time Management
Lecture 9
PMG 212
مقرر: إداره وقت المشروع

## Slide 2
Acceleration and Schedule Compression
Top Project Management Cases
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
Agenda

## Slide 3
Acceleration and Schedule Compression
Top Project Management Cases
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
Agenda

## Slide 4
AstraZeneca During Covid 19
AstraZeneca was under pressure during the pandemic to develop and distribute the COVID-19 vaccine as quickly as possible. The company needed to work in collaboration with Oxford University for the research and the clinical trials.
AstraZeneca created an effective project management infrastructure to face challenges like establishing an internal government contracting organization, finding personnel for vaccine development, and amping up the manufacturing facility.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 5
Vodafone
Vodafone had to replace its current network with a GLAN (Global Local Area Network) in 42 cities. Vodafone used a project management approach that included workshops, the creation of resource and risk management plans, and tailored project documentation for this project. The project was completed by the given deadline.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 6
British Columbia’s Ministry of Transportation and Infrastructure
Massive floods destroyed the roads connecting British Columbia to the rest of Canada. The Ministry of Transportation and Infrastructure used a project management approach based on ‘A Guide to the Project Management Body of Knowledge’ to repair and reopen the roads quickly. They identified the most crucial paths, assessed risks, and managed several aspects of the project in just 35 days.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 7
Hospital El Pilar
This hospital in Guatemala was facing challenges within its technology department that worked to develop tech solutions for the hospital. They had trouble prioritizing projects, had a lack of visibility, and had little to no interaction with the technology users. The hospital overcame these challenges by using project management concepts.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 8
Saudi Aramco
This oil company in Saudi was managing two ambitious oil and gas programs called Marjan and Zuluf. The biggest challenge was to manage multiple contractors working simultaneously on the congested oil fields. Their project team tackled this challenge by simplifying construction, using contracting strategies and marine management techniques.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 9
Gordie Howe International Bridge
A non-profit-making company was in charge of building a six-lane bridge between the USA and Canada. It was one of the largest projects in North America. The organization took the help of a project management company to complete this project using their knowledge and expertise in the domain.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 10
Fujitsu
Famous MNC Fujitsu needed excellent project managers within the company. Their 2-year training program did not work due to a lack of the latest project management content and failure to address the concerns of trainees. The company developed an innovative ‘Early-Career Development Framework,’ using rotational assignments in project management, along with training.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 11
Panama Canal
The Panama Canal had to be expanded in 2014. This project was worth nearly 7% of the country’s GDP. The management had to balance construction, contractors, the site’s biological environment, and finances. The team had to use several project management elements to do this.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 12
London Olympics 2012
The UK government had the challenge of preparing the country for the 2012 Olympic Games within time. They had to prepare world-class sports facilities along with amenities needed for viewers and visitors. It is one of the biggest examples of project management, where over 2,60,000 project managers worked on this project.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 13
Apple iPhone
The project of developing and launching Apple’s iPhone is one of the most important ones in history. The company spent $150 million on this project, which turned out to be its best investment. The main challenges in managing this project were hiring the best talent, maintaining high quality, and keeping the project a secret despite so many people working on it.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 14
Healthcare.gov
It is an example of the consequences of poor project management. Due to a lack of proper planning and coordination, the website could only register six users out of 4 million on its launch day.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 15
Nike Supply Chain Project
I2 Technologies was assigned a project to create supply chain management software for Nike. The project was not properly planned or executed. It took more time than expected, burned Nike’s financial resources, and affected Nike’s profits and stock.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 16
Airbus A380
The development of Airbus A380 turned out to be too expensive, and the launch of this aircraft was delayed multiple times, further increasing its costs. After using project management strategies, the project was successfully launched.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 17
Netflix
Netflix completed its project of developing original streaming content in 2017. Netflix spent its $10 million budget successfully and developed content that appealed to the tastes and preferences of its viewers through excellent project management. It also used unique marketing strategies to launch this project successfully.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 18
Sydney Opera House
Constructing the seemingly unreal Sydney Opera House was a challenge back in the 1950s. This was a 4-year project initially, which got stretched to almost 10 years. However, it was completed despite problems in the design, budget concerns, and leadership changes.
www.midocean.ae
Top Project Management Cases
09
Chapter

## Slide 19
Acceleration and Schedule Compression
Top Project Management Cases
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
Agenda

## Slide 20
Case study
Road Network
A
B
C
D
1
1
3
2
1
3
2
4
3
2
3
2
1
www.midocean.ae
09
Chapter

## Slide 21
Acceleration and Schedule Compression
Top Project Management Cases
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
Agenda

## Slide 22
Case study – Create WBS
www.midocean.ae
09
Chapter

## Slide 23
Case study – Create WBS
Click
www.midocean.ae
09
Chapter

## Slide 24
Case study – Create WBS
www.midocean.ae
09
Chapter

## Slide 25
Acceleration and Schedule Compression
Top Project Management Cases
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
Agenda

## Slide 26
Case study – Create activity code
Activity | Code
Excavation | EX
Replacement | RE
Ferma Layer | FR
Base Layer | BA
Prime Coat | PR
Layer Bond | LB
Tack Coat | TA
Asphalt Layer | AS
Curbs | CU
Sign Traffic | ST
Draw Axis | DR
Pavement Layer | PV
www.midocean.ae
09
Chapter

## Slide 27
Case study – Create activity
www.midocean.ae
09
Chapter

## Slide 28
Case study – Create activity
www.midocean.ae
09
Chapter

## Slide 29
Case study – Create activity
www.midocean.ae
09
Chapter

## Slide 30
Acceleration and Schedule Compression
Top Project Management Cases
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
Agenda

## Slide 31
Case study – Scheduling
www.midocean.ae
09
Chapter

## Slide 32
Acceleration and Schedule Compression
Top Project Management Cases
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
Agenda

## Slide 33
Project duration versus cost
www.midocean.ae
09
Chapter

## Slide 34
Acceleration and Schedule Compression
Top Project Management Cases
Case study
Case study – Create WBS
Case study – Create activity
Case study – Scheduling
Project duration versus cost
Acceleration and Schedule Compression
www.midocean.ae
Agenda

## Slide 35
Acceleration and Schedule Compression
Construction projects always have delivery dates. Some are dictated by the owner, and some are dictated by the contractor.
Most delivery dates are contractual.
There are a multitude of reasons, but the most prominent one is that a project needs a delivery date for control.
Without a delivery date, there is no goal and human nature’s proclivity toward procrastination takes over.
www.midocean.ae
09
Chapter

## Slide 36
Acceleration
Delivering on time or ahead of schedule is important for all parties, from subcontractors all the way up to the owner.
Finishing within or under budget is another important goal.
The real achievement, however, is doing both simultaneously. Unfortunately, this may not always be possible.
www.midocean.ae
09
Chapter

## Slide 37
Acceleration
At the point where an accelerated pace of the work is diagnosed as the cure
for delay, the project manager may have to make the decision to spend money.
Acceleration is defined as the addition of resources or work hours to a task
or project.
Acceleration results in schedule compression or reducing the duration of the task or shortening the entire project without diminishing the scope of the
project.
www.midocean.ae
09
Chapter

## Slide 38
Acceleration
The acceleration must be applied to the critical path or a critical task.
To accelerate a noncritical task rarely benefits the schedule.
There are three different types of acceleration that the average project may potentially encounter.
Acceleration is issued in the form of written direction from the owner to the contractor and can be classified in three categories: actual, constructive, and forced.
www.midocean.ae
09
Chapter

## Slide 39
Actual Acceleration
Actual acceleration is the directive to complete the project ahead of the accepted or contractual schedule.
This directive comes from the owner to the contractor through the architect, and is then passed on to the subcontractors.
www.midocean.ae
09
Chapter

## Slide 40
Constructive Acceleration
Constructive acceleration occurs when the contractor requests an extension of time and is denied.
If the delay that resulted in the request for an extension of time is an excusable delay, the extension should be granted.
www.midocean.ae
09
Chapter

## Slide 41
Constructive Acceleration
Constructive acceleration exists when the following conditions occur:
  ● There is an excusable delay to the project.
  ● The contractor requests a justifiable extension of time for the excusable delay.
  ● The request for an extension is denied.
www.midocean.ae
09
Chapter

## Slide 42
Constructive Acceleration
Constructive acceleration exists when the following conditions occur:
  ● The contractor is directed to achieve the original completion date.
  ● The contractor actually accelerates the work to meet the original date.
  ● The contractor incurs additional costs for acceleration.
www.midocean.ae
09
Chapter

## Slide 43
Forced Acceleration
There is also a need for acceleration when delay occurs as a result of nonperformance.
This type of acceleration is sometimes referred to as forced acceleration.
This occurs frequently when a subcontractor on the critical path is falling behind.
While this is not acceleration in the truest sense of the definition, it does require an increase in production.
www.midocean.ae
09
Chapter

## Slide 44
Schedule Compression
The decision to accelerate work and incur costs must have a tangible benefit to the project.
Schedule compression is not always about the shortest duration of the task.
It is more about the balance of getting the shortest duration for the least
cost.
www.midocean.ae
09
Chapter

## Slide 45
Schedule Compression
Schedule compression is generally defined as modifying the plan and/or schedule to complete critical tasks or the project early.
Schedule compression is the resequencing or rescheduling of tasks with minimal or no cost impact.
www.midocean.ae
09
Chapter

## Slide 46
www.midocean.ae

## Slide 47
Thank You