## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | Miscommunication and misunderstanding | High | high | Issues, delay, | Using standard official channels. Acquiring translators. Hold awareness sessions. | Project Manger
2 | THREATS | Increase costs, as consequence of Economic inflation | High | moderate | Global oil price | Long-term contracting. Diversification of supply sources. | Procurements Manager
3 | OPPORTUNITIES | Tax Exemption | High | high | High Society Cooperation | Adopting social community initiatives. Cooperation with humanitarian sector organizations | Public relations manager
4
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low