## ورقة1
student name |  | khalid almohimeed | student Id | 2021206173
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | miscommuncation and misunderstanding | high | high | issues | using standard official chanels | public relations manager | مشروع الهايبر لوب
2 | THREATS | manpwoer shortage | moderate | moderate | delay | Long term contracting | project manager
3 | OPPORTUNITIES | Tax Exemption | high | high | آigh siciety cooperation | dopting social communicating initiatives | ublic relation Manager
4 | OPPORTUNITIES
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low