## Slide 1
Prepared by Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Agile Project Management
Lecture 05
PMG 622
Master of Project Management

## Slide 2
Different Agile Frameworks and Methodologies
Lecture 5
PMG 622
Agile Project Management
Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Prepared by

## Slide 3
Learning Objectives
Learn a brief overview and core principles of the following Agile Frameworks and Methodologies:
  Lean Product Development
  Kanban
  Scrum
  Xtreme Programming (XP)
  Crystal
  DSDM
  FDD
Chapter
05

## Slide 4
There are many different Agile Frameworks
Chapter
05
Scrum
XP
ScrumBan
DSDM
Kanban
Crystal
FDD
Lean
Agile

## Slide 5
The Agile Subway Roadmap
Chapter
05
Retrieved from https://www.agilealliance.org/agile101/subway-map-to-agile-practices/

## Slide 6
Lean Product Development
Chapter
05

## Slide 7
Using visual management tools
Identifying costumer defined value
Building in learning and continuous improvement
Lean Product Development
Chapter
05
Lean product development (LPD) is a systematic approach to product development that focuses on eliminating waste in processes and delivering value to customers as quickly as possible.
It is based on the principles of lean manufacturing, started in Toyota Company
Used mainly for operations but principles can be applied to projects
Using visual management tools
Identifying costumer value
Building in learning and continuous improvement

## Slide 8
Using visual management tools
Identifying costumer defined value
Building in learning and continuous improvement
Lean Product Development – Seven Core Concepts
Chapter
05
Eliminate waste
Empower the team
Deliver fast
Optimize the whole
Build quality in
Defer decisions
Amplify learning

## Slide 9
Lean Product Development – Seven Wastes
Chapter
02
Partially done work
Extra processes
Extra features
Task switching
Waiting
Motion
Defects

## Slide 10
Lean Product Development – Main Tools
Chapter
02
Lean Tools
Value Stream Mapping
Kaizen
Kanban
Root-Cause Analysis
Bottleneck Analysis
PDCA

## Slide 11
Kanban
Chapter
05

## Slide 12
Kanban Overview and Principles
Chapter
05
Kanban is an approach for designing, managing, and improving the flow of processes in systems
Organizations can use it to visualize the flow of work and limit work in progress
Used for projects as well as continuous operations
Establishes a method for “pull” systems, or Just in Time (JIT) Work by using Kanban Boards.
Japanese word meaning “Card” “signal”

## Slide 13
Kanban Five Principles
Chapter
05
5 principles
Visualize the workflow
Limit WIP (work in progress)
Manage flow
Make process policies explicit
Improve collaboratively

## Slide 14
Kanban Board – Pull System
Chapter
02
To Do
In Progress
Done
User Story 2
User Story 4
User Story 1
User Story 3
User Story 5

## Slide 15
Kanban Boards are typically used for Iteration/ Sprint Management and Tracking (ScrumBan)
Chapter
02
Product Backlog
Design (3)
Testing
(2)
User Story 150
User Story 151
User Story 100
User Story 101
User Story 152
Iteration 1 Backlog (12)
Development
(2)
Done
User Story 102
User Story 96
User Story 97
User Story 94
User Story 95
User Story 90
User Story 80
User Story 81
User Story 82
User Story 83

## Slide 16
Cumulative Flow Diagrams
Chapter
05
We use lead time, WIP as metrics to track performance instead of velocity

## Slide 17
Scrum
Chapter
05

## Slide 18
Scrum Overview and Pillars
Chapter
05
Most Widely uses Agile Methodology
Goal is to deliver working products to customers on a regular basis
Time-boxed iterations (sprints) with a focus on planning, execution, and review
Focus on customer collaboration, value delivery, and continuous improvement
Transparency
Gives visibility to those responsible
Inspection
Timely checks of how the project is progressing
Adaptation
Adjusting team’s process and course correcting

## Slide 19
Scrum Process
Chapter
05

## Slide 20
Scrum Ceremonies
Chapter
05
Sprint Review
At the end of each sprint
Sprint Retrospective
After the sprint review, before next sprint planning meeting
Includes Team, product owner, and ScrumMaster
Product owner inspects work/explains what is missing
Team holds final “inspect and adapt” activity
Find improvements for next sprint
Backlog Refinement
“grooming the backlog”
Everyone in the project discusses and updates items
Sprint Planning Meeting
Everyone decides what will be included in the next sprint/iteration
Product owner presents updated backlog
Group gets shared understanding
Team forecast what can be delivered
Daily Scrum
15-minute timeboxed meeting
Same time everyday
ScrumMaster is responsible
3 questions
What have I done since last daily scrum
What do I plan to do today
Are there any impediments to my progress

## Slide 21
Scrum Team Roles
Chapter
05
Team
The people building the product
They are self organizing
They are cross-functional
Product Owner
Maximizes value of the product by managing the product backlog
Ensures work items in backlog are up to date
Responsible or the business and the team having a shared understanding of the project vision
ScrumMaster
Ensures scrum methodology is understood and used effective
They are a servant leader
Removes impediments to team
May also serve as an Agile Coach - Facilitating the organization's adoption of scrum on an enterprise level

## Slide 22
Scrum Key Artifacts
Chapter
05
Product Increment
Build by the team
It’s an increment of the solution
“Definition of Done” is agreed upon before the team begins working
Product Backlog
Prioritized list of all the work
May include:
Features
Functions
Requirements
Quality attributes
Sprint Backlog
Subset of items in product backlog selected as the goal for a specific sprint
It’s the team’s commitment for functionality that they will deliver
Is highly visible
Updated by the team
User Stories
fixes

## Slide 23
Scrum Key Terms
Chapter
05

## Slide 24
Scrum Key Terms – Scrum of Scrums
Chapter
05
Takes place on a regular basis
A representative from each team meets
The representative reports back to their teams any issues

## Slide 25
Extreme Programming (XP)
Chapter
05

## Slide 26
XP Overview and Core Values
Chapter
05
Goal is to produce High-Quality Software while also improving the team’s quality of life
Low risk, flexible, and cost-effective method
Testing software starts from the beginning and feedback used to improve the development
Simplicity
Communication
Feedback
Courage
Respect

## Slide 27
Using visual management tools
Identifying costumer defined value
Building in learning and continuous improvement
XP – Team Roles
Chapter
05
Coach
Customer
Programmers
Testers

## Slide 28
Using visual management tools
Identifying costumer defined value
Building in learning and continuous improvement
XP – Core Practices (1/2)
Chapter
05
Whole Team
Planning games
Small releases
Customer tests
Collective code ownership
Code standards
Sustainable pace
Co-Location, Generalized Specialists, Role Switching
used in Release Planning and Iteration Planning
frequent small releases for testing, and continuous integration
Customer describes test criteria, then the team builds automated tests to prove that the solution met criteria
everyone works on code to increase visibility and knowledge, identify defects early and reduce risk when a team member leaves
The team chooses a single standard for coding
Improves productivity and Optimizes delivery of long-term value

## Slide 29
Using visual management tools
Identifying costumer defined value
Building in learning and continuous improvement
XP – Core Practices (2/2)
Chapter
05
Metaphor
Continuous integration
Test-driven development
Refactoring
Simple design
Pair programming
uses metaphors to establish comparisons so that all stakeholders understand how a system should work
Automated integration testing, Ensures all code works together, and Surfaces problems early, decreasing rework
Team writes acceptance tests prior to developing the new code
Shortens the test-feedback cycle as much as possible
Improves design of existing code, increases Efficiency in coding enhances ability to apply changes and new functionality easily
developers working as a pair, one writes, the other reviews – changing roles frequently
Helps to capture issues early, save time, spread knowledge

## Slide 30
Crystal
Chapter
05

## Slide 31
Crystal Overview
Chapter
05
A software development approach that focuses on people and their interactions rather than tools and processes
Crystal goal is streamlining and optimizing processes
Lightweight and Adaptable
Consists of a family of methodologies coded by color names
Customized by criticality and team size

## Slide 32
Example of Crystal Methods Chart
Chapter
05
Criticality | Crystal Clear | Crystal Yellow | Crystal Orange | Crystal Red | Crystal Magenta
Life | L6 | L20 | L40 | L100 | L200
Essential Funds | E6 | E20 | E40 | E100 | E200
Discretionary Funds | D6 | D20 | D40 | D100 | D200
Comfort | C6 | C20 | C40 | C100 | C200
TEAM SIZE | 1-6 | 7-20 | 21-40 | 41-100 | 101-200

## Slide 33
Dynamic Systems Development Method (DSDM)
Chapter
05

## Slide 34
DSDM Overview
Chapter
05
Was an earlier agile method used to rapidly develop and deliver high quality software
Goal is to guarantee strong governance of projects during the whole project life cycle
User-Driven and thinks Change is expected at all times
Time-boxed iterations (phases) with a focus on business involvement, iterative development, and continuous testing

## Slide 35
DSDM – Eight Principles
Chapter
05
Focus on the business need
Deliver on time
Collaborate
Never compromise quality
Build incrementally from firm foundations
Develop iteratively
Communicate continuously and clearly
Demonstrate control

## Slide 36
DSDM Process
Chapter
05
Functional Model Iteration
Design & Build Iteration
Implementation
Feasibility

## Slide 37
Feature Driven Development
(FDD)
Chapter
05

## Slide 38
FDD Overview
Chapter
05
Develop an Overall Model
Build a Feature List
Plan By Feature
Build by Feature
Design by Feature
Goal to develop stable and functional products on time
Iterative and Incremental

## Slide 39
FDD – Good Practices
Chapter
05
Developing by feature
Business modeling
Feature teams
Inspections
Configuration management
Regular builds
Visibility of progress and results
Individual class (code) ownership

## Slide 40: Comparing Agile Frameworks and Methodologies
Element | Lean | Kanban | Scrum | Xp | Crystal | DSDM | FDD
Focus | Eliminating waste and delivering value to customers quickly | Visualizing and optimizing the flow of work | Delivering working software to customers on a regular basis | Producing high-quality software and improving the quality of life for the team | Lightweight and flexible, with no prescribed process | Rapidly developing and delivering high-quality software | Building features in a short, iterative, and incremental manner
Process | Iterative and incremental | Pull-based system with no fixed iterations | Time-boxed iterations (sprints) with a focus on planning, execution, and review | Time-boxed iterations (releases) with a focus on communication, feedback, and continuous improvement | Lightweight and flexible, with no prescribed process | Time-boxed iterations, focus on business involvement, iterative development, and continuous testing | Process-driven approach with a focus on domain modeling, feature development, and inspections
Principles | Focus on customer value, continuous improvement, and collaboration | Focus on continuous flow, work-in-progress limits, and visualization | Focus on customer collaboration, value delivery, and continuous improvement | Focus on communication, feedback, continuous improvement, and technical excellence | Focus on simplicity, communication, collaboration, and adaptability | Focus on customer collaboration, risk management, and continuous improvement | Focus on visibility, communication, collaboration, and quality
Others | Can be used with any agile methodology | Can be used for software development, but also other types of work | Most widely used agile methodology | The most specific agile framework regarding appropriate practices for software development | Can be used for software development, but also other types of work |  | Well-suited for software development projects with complex requirements

## Slide 41
Key Points
Chapter
05
Scrum is the most widely used Agile Methodology
Some Agile methodologies as Lean, Crystal has no prescribed processes
Most methodologies started in the Software Industry, except for Lean and Kanban who came from manufacturing
You can mix tools from different methodologies together in your Agile project

## Slide 42
Preparation for discussion panel:
Which of the Agile Frameworks and methodologies are you using or planning to use?
Why?
For Discussion Panel
Chapter
05
www.midocean.ae

## Slide 43
Before next lecture:
Watch the Video
“Intro to Scrum in Under 10 Minutes”
For Next Lecture
Chapter
05
www.midocean.ae

## Slide 44
Thank You