## Slide 1
Project Risk& Supply
Chain Risk Management

## Slide 2
Lecture 4
Dr. Dalia Hosni
Prepared by
www.midocean.ae
Project Risk& Supply
Chain Risk Management
PMG 663
Project Risk &Supply Chain Risk

## Slide 3
Chapter
04
www.midocean.ae
Monitor and Control Risks

## Slide 4
Project Risk Topics
Chapter
4
Plan Risk Management
Identify Risks
Perform Qualitative Risk Analysis
Perform Quantitative Risk Analysis
Plan Risk Responses
Monitor and Control Risks
www.midocean.ae

## Slide 5
Monitor and Control Risks
Chapter
4
Goal: Change requests, updates
www.midocean.ae

## Slide 6
Chapter
04
As in other monitor and controlling activities, it is assumed you have performed all the necessary elements to identify and quantify project risk, and have a created the necessary strategies to respond to risk on the project.
Monitor and Control Risks
www.midocean.ae

## Slide 7
Chapter
04
Part of the process of monitoring and controlling risks is to perform risk reassessments of the project on a regular basis:
Monitor and Control Risks
Have the risk elements changed?
Have lower level, low priority risks become high priority risks?
Have certain risks been addressed, and be considered closed on the risk log?
Do contingency or management reserves need to be adjusted?
www.midocean.ae

## Slide 8
Risk Audits and Reviews
Chapter
04
In most large organizations, there are individuals who specialize in risk auditing and conducting risk reviews.
You would do well to learn as much as you can from these individuals about project risk - it will help you do a better job of identifying risks and planning risk responses.
Usually, risk audits are periodically scheduled throughout the project.
They are typically conducted by people outside of your immediate organization.
Why do you think that is so?
www.midocean.ae

## Slide 9
Risk Audits and Reviews
Chapter
04
There are several reasons why auditors are not part of the project team:
Provides for an objective review of risks
Provides a fresh pair of eyes to review risk elements from a different perspective
Can help identify risks not considered by the team
www.midocean.ae

## Slide 10
Risk reassessment or risk reviews
Chapter
04
Periodic and scheduled
Should occur to determine if any risk priorities or ratings have Changed
Risk audits
Carried out throughout project life
Typically performed by experts outside project team
www.midocean.ae

## Slide 11
Risk reassessment or risk reviews
Chapter
04
Additional Risk Tools
Variance and Trend analysis compares planned results to the actual results. Variance tools such as earned value analysis can be used for monitoring overall project performance. As a result, potential forecasts of deviation at the project’s completion from cost and schedule targets are possible.
Technical Performance Measurement compares technical accomplishments during project execution to the project management plan schedule of technical achievement. Quantifiable measurements are taken and compared against actual results.
Reserve Analysis compares the amount of contingency reserves remaining to the amount of risk remaining at any time in the project.
www.midocean.ae

## Slide 12
Risk reassessment or risk reviews
Chapter
04
reserve analysis and the funds set aside for contingencies apply only to the specific risks on the project for which they were set aside
Notes
www.midocean.ae

## Slide 13
Risk reassessment or risk reviews
Chapter
04
Workarounds are usually employed when no contingency plan exists, and are generally executed ‘on the-fly' to address some unplanned event.
The result of implementing a workaround can be the identification of an undiscovered risk for which the contingency and fallback planning can now be addressed.
Workarounds
www.midocean.ae

## Slide 14
Project Risk Management: Key Process Interactions
Chapter
04
www.midocean.ae

## Slide 15
In Summary
Chapter
04
The benefit of using a risk breakdown structure
Information gathering techniques: brainstorming, Delphi technique, interviewing, root cause identification, and SWOT analysis
Importance and components of the risk register
Deciding on the best risk response strategy: avoid, transfer, mitigate, exploit, share, enhance, or accept risk events
www.midocean.ae

## Slide 16
Supply Chain Management
Chapter
04
A supply chain is a set of organizations directly linked by one or more of the upstream and downstream flows of products, services, finances, and information from a source to a customer.
Managing a supply chain is 'supply chain management 'Supply chain management (SCM) is the management of a network of interconnected businesses involved in the ultimate provision of product and service packages required by end customers.
www.midocean.ae

## Slide 17
Supply Chain Management
Chapter
04
Supply chain management spans all movement and storage of raw materials, work- in-process inventory, and finished goods from point of origin to point of consumption (supply chain).
www.midocean.ae

## Slide 18
Supply Chain Management
Chapter
04
www.midocean.ae

## Slide 19
Supply Chain Management
Chapter
04
www.midocean.ae

## Slide 20
Supply Chain for Service Providers
Chapter
04
More difficult than manufacturing
Does not focus on the flow of physical goods
Focuses on human resources and support services
More compact and less extended
www.midocean.ae

## Slide 21
Supply chain management
Chapter
04
- A supply chain consists of
- aims to Match Supply and Demand, profitably for products and services
SUPPLY SIDE
DEMAND SIDE
The right
Product
Higher
Profits
The right
Time
The right
Customer
The right
Quantity
The right
Store
The right
Price
=
+
+
+
+
+
- achieves
Supplier
Manufacturer
Distributor
Retailer
Customer
Upstream
Downstream
www.midocean.ae

## Slide 22
Supply chain management
Chapter
04
www.midocean.ae

## Slide 23
Supply chain flow diagram
Chapter
04
www.midocean.ae

## Slide 24
Supply chain flow diagram
Chapter
04
Supply chain management is control of supply chain as process from supplier to manufacture to wholesaler to retailer to consumer.
Supply chain management flow can be divided into three main flow
                The product flow
                The information flow
                The finance flow
www.midocean.ae

## Slide 25
supplier
customer
producer
Information flow
Primary product flow
Primary product flow
Reverse product flow
Primary cash flow
Supply chain management flow
www.midocean.ae

## Slide 26
Knowledge management in SC
Chapter
04
Knowledge management is the process of capturing, developing, sharing and effectively using organizational knowledge
Knowledge management system refer to any kind of IT system that stores and retrieves knowledge, improves collaboration locates knowledge source
www.midocean.ae

## Slide 27
Supply chain knowledge management
Chapter
04
The KM adoption in supply chain makes the environment collaborative that enables the chain to be more adaptive and response.
This helps to organization to achieves an improvement strategic competitive position in the market.
More cost effective, efficient and competitively response and adaptive supply chain.
www.midocean.ae

## Slide 28
Benefits of supply chain knowledge management
Chapter
04
Improve project management
Supply chain
Reduced process cycle time
Customer participation
www.midocean.ae

## Slide 29
Key Issue in supply chain management
Chapter
04
Bullwhips effect- In supply chain increasing demand and supply variation from retailer, customer to manufacturing. Away from customer the always fluctuated demand like increase and suddenly decrease in supply chain such case is affected on production management and supply chain management, price of product. The effect is known as Bullwhip effect
  Cost/pricing issues
  Managing inventory and supplier
  Primary manufacturing process PUSH
  Maintaining safety and quality
www.midocean.ae

## Slide 30
Key challenges in supply chain management
Chapter
04
Customer service - Supply chain management is all about providing the right product in the right quantity to the right place and the right time. Seems simple, but can get complicated...quickly.
Cost control - Operating costs are under extreme pressure by rising energy/fuel and freight costs, greater number of global customers, technology, increasing labor rates and new regulations and rising commodity prices.
www.midocean.ae

## Slide 31
Key challenges in supply chain management
Chapter
04
Planning & risk management - In order to stay as efficient and effective as possible, periodic assessments and redesigns are needed. These adjustments are in response to changes in the market - changes such as new product launches, global sourcing, credit availability and the need to protect intellectual property. These risks must be identified and quantified in order to control and mitigate.
Supplier/partner relationship management - It is important to create, understand and follow mutually agreed upon standards to better understand current performance and opportunities for improvement. Having two different methods for measuring and communicating performance and results wastes time and effort. Trust the system that was put in place for consistent results and better supplier/partner relationships.
www.midocean.ae

## Slide 32
Supply Chain Management (SCM)
Chapter
03
Managing flow of information through supply chain in order to attain the level of synchronization that will make it more responsive to customer needs while lowering costs
Keys to effective SCM
Information
Communication
Cooperation
trust
www.midocean.ae

## Slide 33
What Is Supply Chain Management (SCM)?
Chapter
04
A set of approaches used to efficiently integrate
Suppliers
Manufacturers
Warehouses
Distribution centers
www.midocean.ae

## Slide 34
What Is Supply Chain Management (SCM)?
Chapter
04
So that the product is produced and distributed
In the right quantities
To the right locations
And at the right time
System-wide costs are minimized and
Service level requirements are satisfied
www.midocean.ae

## Slide 35
WHAT IS SUPPLY CHAIN MANAGEMENT
Chapter
04
Customer Management
Supplier Management
Material Flow
Information Flow
Delivery
Schedule /Resources
Conversion
Stock Deployment
Leads to Business Process Integration
Is the strategic management of activities involved in the acquisition and conversion of materials to finished products delivered to the customer"
www.midocean.ae

## Slide 36
SUPPLY CHAIN MANAGEMENT
Chapter
04
Supply chain is the system by which organizations source, make and deliver their products or services according to market demand.
Supply chain management operations and decisions are ultimately triggered by demand signals at the ultimate consumer level.
Supply chain as defined by experienced practitioners extends from suppliers’ suppliers to customers’ customers.
www.midocean.ae

## Slide 37
Why is SCM Difficult
Chapter
03
Uncertainty is inherent to every supply chain
Travel times
Breakdowns of machines and vehicles
Weather, natural catastrophe, war
Local politics, labor conditions, border issues
The complexity of the problem to globally optimize a supply chain is significant
Minimize internal costs
Minimize uncertainty
Deal with remaining uncertainty
www.midocean.ae

## Slide 38
Thank You