## Slide 1
Project Resources and Time Management
Lecture 9
PMG 605
Dr. Eng. Abdullah Jameel Halawany
Prepared by
Progress and Performance Measurement and Evaluation

## Slide 2
Session Outline
Lecture
09
9–2
Progress and Performance Measurement and Evaluation
Structure of a Project Monitoring Information System
The Project Control Process
Monitoring Time Performance
Development of an Earned Value Cost/Schedule System
Developing a Status Report
Indexes to Monitor Progress
Forecasting Final Project Cost

## Slide 3
9–3

## Slide 4
9–4
Progress and Performance Measurement and Evaluation
Lecture
09
Evaluation and control are part of every project manager’s job.
Large projects need some form of formal control.
Control holds people accountable, prevents small problems from escalating into large problems, and keeps focus.
Except for accounting controls, project control is not performed well in most organizations.
Control is one of the most neglected areas of project management.
Unfortunately, it is not uncommon to find resistance to control processes.
For effective control, the project manager needs a single information system to collect data and report progress on cost, schedule, and specifications

## Slide 5: Progress and Performance Measurement and Evaluation
9–5

## Slide 6
Structure of a Project Monitoring Information System
PMG 605
Project Resources and Time Management
Progress and Performance Measurement and Evaluation
Lecture
08
9–6

## Slide 7
9–7
Structure of a Project Monitoring Information System
Lecture
09
Creating a project monitoring system involves determining
  What data to collect
  How, when, and who will collect the data
  How to analyze the data
  How to report current progress to management

## Slide 8
9–8
What Data Are Collected?
Lecture
09
Data collected are determined by which metrics will be used for project control.
Typical key data collected are
  actual activity duration times,
  actual resource usage and rates,
  actual costs,
which are compared against planned times, resources, and budgets.

## Slide 9
9–9
What Data Are Collected?
Lecture
09
Major portion of the monitoring system focuses on cost/schedule concerns
It is crucial to provide the project manager and stakeholders with data to answer questions such as:
  What is the current status of the project in terms of schedule and cost?
  How much will it cost to complete the project?
  When will the project be completed?
  Are there potential problems that need to be addressed now?
  What, who, and where are the causes for cost or schedule overruns?
  If there is a cost overrun midway in the project, can we forecast the overrun at completion?

## Slide 10
9–10
Collecting Data and Analysis
Lecture
09
Will the data be collected by the project team, contractor, independent cost engineers?
Or will the data be derived electronically from some form of surrogate data such as cash flow, machine hours, labor hours, or materials in place?
Should the reporting period be one hour, one day, one week, or what?
Electronic means of collecting data have vastly improved data assembly, analysis, and dissemination.
Currently software have tools to analyze your customized collected data and present it in a form that facilitates monitoring the project, identifying sources of problems, and updating your plan.

## Slide 11
9–11
Reports and Reporting
Lecture
09
Who gets the progress reports?
Different stakeholders and levels of management need different kinds of project information.
Senior management’s major interests are usually,
  “Are we on time and within budget?
  If not, what corrective action is taking place?”
The reports should be designed for the right audience.

## Slide 12
9–12
Reports and Reporting
Lecture
09
A common topic format for progress reports follows:
Progress since last report
Current status of project
Schedule
Cost
Scope
Cumulative trends
Problems and issues since last report
Actions and resolution of earlier problems
New variances and problems identified
Corrective action planned

## Slide 13
The Project
Control Process
PMG 605
Project Resources and Time Management
Progress and Performance Measurement and Evaluation
Lecture
08
9–13

## Slide 14
9–14
The Project Control Process
Lecture
09
The project control steps for measuring and evaluating project performance are
Setting a baseline plan.
Measuring progress and performance.
Comparing plan against actual.
Taking action.
Control is the process of comparing actual performance against plan to identify deviations, evaluate possible alternative courses of actions, and take appropriate corrective action.

## Slide 15
9–15
Step 1: Setting a Baseline Plan
Lecture
09
The baseline plan provides us with the elements for measuring performance.
The baseline is derived from the cost and duration information found in the work breakdown structure (WBS) database and time-sequence data from the network and resource scheduling decisions.

## Slide 16
9–16
Step 2: Measuring Progress and Performance
Lecture
09
Qualitative measures such as meeting customer technical specifications and product function are most frequently determined by on-site inspection or actual use.
Time and budgets are quantitative measures of performance that readily fit into the integrated information system.

## Slide 17
9–17
Step 3: Comparing Plan against Actual
Lecture
09
Because plans seldom materialize as expected, it becomes imperative to measure deviations from plan to determine if action is necessary.
Periodic monitoring and measuring the status of the project allow for comparisons of actual versus expected plans.
It is crucial that the timing of status reports be frequent enough to allow for early detection of variations from plan and early correction of causes.

## Slide 18
9–18
Step 4: Taking Action
Lecture
09
If deviations from plans are significant, corrective action will be needed to bring the project back in line with the original or revised plan.
In some cases, conditions or scope can change, which, in turn, will require a change in the baseline plan to recognize new information.

## Slide 19
Monitoring Time Performance
PMG 605
Project Resources and Time Management
Progress and Performance Measurement and Evaluation
Lecture
08
9–19

## Slide 20
9–20
Monitoring Time Performance
Lecture
09
A major goal of progress reporting is to catch any negative variances from plan as early as possible to determine if corrective action is necessary.
The project network schedule, derived from the WBS/OBS, serves as the baseline to compare against actual performance.
Tools used
  Tracking Gantt Chart
  Control Chart
  Milestone Schedules

## Slide 21: Tracking Gantt Chart
The most favored, used, and understandable.
9–21

## Slide 22
9–22
Control Chart
Lecture
09
The chart is used to plot the difference between the scheduled time on the critical path at the report date with the actual point on the critical path.
The figure shows the project was behind early in the project, the plot suggests corrective action brought the project back on track.
Control chart trends are very useful for giving warning of potential problems so appropriate action can be taken if necessary.

## Slide 23
9–23
Milestone Schedules
Lecture
09
Stakeholders, whether it is senior management, the owner, or regulatory agencies often neither need or desire a detailed accounting of project progress.
Instead, their interests can be satisfied by reporting progress towards major project milestones.
Remember, milestones are significant project events that mark major accomplishments.
Project managers recognize the need to use
  A more macro schedule of significant deliverables to keep external stakeholders informed and
  A more detailed milestone driven schedule to manage and motivate the project team to achieve those deliverables.

## Slide 24
Development of an
Earned Value (EV)
Cost/Schedule System
PMG 605
Project Resources and Time Management
Progress and Performance Measurement and Evaluation
Lecture
08
9–24

## Slide 25
9–25
Earned Value Cost/Schedule System
Lecture
09
The earned value system starts with the time-phased costs that provide the project budget baseline, which is called the planned budgeted value (PV) of the work scheduled.
Given this time-phased baseline, comparisons are made with actual and planned schedule and costs using earned value.
The earned value approach provides the missing links not found in conventional cost-budget systems.
At any point in time, a status report can be developed for the project.
The earned value cost/schedule system uses several acronyms and equations for analysis.

## Slide 26
9–26
Glossary of Terms
Lecture
09
EV | Earned value for a task is simply the percent complete times its original budget. Stated differently, EV is the percent of the original budget that has been earned by actual work completed
PV | The planned time-phased baseline of the value of the work scheduled. An approved cost estimate of the resources scheduled in a time-phased cumulative baseline
AC | Actual cost of the work completed. The sum of the costs incurred in accomplishing work.
CV | Cost variance is the difference between the earned value and the actual costs for the work completed to date where CV = EV – AC.
SV | Schedule variance is the difference between the earned value and the baseline line to date where SV = EV – PV.
BAC | Budgeted cost at completion. Total budgeted cost of the baseline or project cost accounts.
EAC | Estimated cost at completion.
ETC | Estimated cost to complete remaining work.
VAC | Cost variance at completion. VAC indicates expected actual over- or under-run cost at completion.

## Slide 27
9–27
Development of an EV Cost/Schedule System
Lecture
09
Define the work using a WBS.
  Scope
  Work packages
  Deliverables
  Organization units
  Resources
  Budgets
Develop work and resource schedules.
  Schedule resources to activities
  Time-phase work packages into a network
Develop a time-phased budget using work packages included in an activity. Accumulate budgets (PV).
At the work package level, collect the actual costs for the work performed (AC). Multiply percent complete times original budget (EV).
Compute the schedule variance (EV-PV) and the cost variance (EV-AC).

## Slide 28: Project Management Information System Overview
9–28

## Slide 29
9–29
Project Management Information System Overview
Lecture
09
The major reasons for creating a baseline are to monitor and report progress and to estimate cash flow.
Therefore, it is crucial to integrate the baseline with the performance measurement system.

## Slide 30
9–30
Percent Complete Rule
Lecture
09
Percent Complete is the workhorse most commonly used.
Someone familiar with each task estimates what percent of the task has been completed or how much of the task remains.
When measuring percent complete in the monitoring phase of the project, it is common to limit the amount earned to 80 or 90 percent until the work package is 100 percent complete.

## Slide 31
9–31
Methods of Variance Analysis
Lecture
09
The method for measuring accomplishments centers on Comparing Earned Value
  With the expected schedule value.
  With the actual costs.
These comparisons can be made at the project level or down to the cost account level.
Project status can be determined for the
  latest period,
  all periods to date,
  and estimated to the end of the project.

## Slide 32
9–32
Methods of Variance Analysis
Lecture
09
Assessing Status of a Project Required data elements
  Data Budgeted cost of the work scheduled (PV)
  Budgeted cost of the work completed (EV)
  Actual cost of the work completed (AC)
Calculate schedule and cost variances
  A positive variance indicates a desirable condition,
  A negative variance suggests problems or changes that have taken place.

## Slide 33
9–33
Cost Variance (CV)
Lecture
09
Indicates if the work accomplished using labor and materials costs more or less than was planned at any point in the project.
Should be reviewed carefully to isolate the cause to either labor or materials—or to both.

## Slide 34
9–34
Schedule Variance (SV)
Lecture
09
Critical and non-critical activities are combined in the calculation.
Schedule variance measures progress in dollars rather than time units. Therefore, it is unlikely that any translation of dollars to time will yield accurate information telling if any milestone or critical path is early, on time, or late.
The only accurate method for determining the true time progress of the project is to compare the project network schedule against the actual network schedule to measure if the project is on time.
However, SV is very useful in assessing the direction all the work in the project is taking—after 20 or more percent of the project has been completed.

## Slide 35
9–35
Methods of Variance Analysis
Lecture
09
EV = % completed * Original Budget
Cost Variance (CV) = EV – AC
Schedule Variance (SV) = EV – PV

## Slide 36: Cost/Schedule Graph
9–36

## Slide 37
9–37
Suggests the project may be ahead of schedule
Suggests the project may be ahead of schedule and under budget
Suggests the project behind of schedule
Suggests the project behind of schedule and over budget

## Slide 38
Developing a Status Report
PMG 605
Project Resources and Time Management
Progress and Performance Measurement and Evaluation
Lecture
08
9–38

## Slide 39
9–39

## Slide 40
9–40

## Slide 41
9–41

## Slide 42
9–42

## Slide 43
Indexes to Monitor Progress
PMG 605
Project Resources and Time Management
Progress and Performance Measurement and Evaluation
Lecture
08
9–43

## Slide 44
9–44
Indexes to Monitor Progress
Lecture
09
Practitioners sometimes prefer to use schedule and cost indexes over the values of SV and CV, because indexes can be considered efficiency ratios.
Indexes are typically used at the cost account level and above.

## Slide 45
Performance Indexes
Cost Performance Index
CPI = EV/AC
Scheduling Performance Index
SPI = EV/PV
Project Percent Complete Indexes
Percent Complete Index Budgeted Costs
PCIB = EV/BAC
Percent Complete Index Actual Costs
PCIC = AC/EAC
Indexes To Monitor Progress
9–45

## Slide 46
9–46
Performance Indexes- Cost Performance Index (CPI)
Lecture
09
Cost Performance Index (CPI) measures cost efficiency of the work accomplished to date
Most accurate, reliable, and stable
The CPI can provide an “early warning signal” as to cost overruns so that adjustments can be made to the budget or scope of a project
CPI = EV/AC = 160/230 = .7

## Slide 47
9–47
Performance Indexes- Scheduling Performance Index (SPI)
Lecture
09
Scheduling Performance Index (SPI) measures scheduling efficiency to date
SPI = EV/PV = 160/200 = .8

## Slide 48
9–48
Project Percent Complete Indexes – Percent Complete Index Budgeted Costs (PCIB)
Lecture
09
This index is favored by many project managers when there is a high level of confidence in the original budget estimates (BAC).
PCIB = EV/BAC = 160/320 = .50 (50%)
Indicates the work accomplished represents 50 percent of the total budgeted (BAC) dollars to date.

## Slide 49
9–49
Project Percent Complete Indexes – Percent Complete Index Actual Costs (PCIC)
Lecture
09
This index assumes the actual costs-to-date and expected cost at completion are the most reliable for measuring project percent complete (EACre).
Example, at the end of period 7 the staff re-estimates that the EACre will be 575 instead of 320.
PCIC = AC/EACre = 230/575 = .40 (40%)
Some managers favor this index because it contains actual and revised estimates that include newer, more complete information.

## Slide 50
9–50
Performance Indexes
Lecture
09

## Slide 51
Forecasting Final Project Cost
PMG 605
Project Resources and Time Management
Progress and Performance Measurement and Evaluation
Lecture
08
9–51

## Slide 52
9–52
Forecasting Final Project Cost
Lecture
09
Basically, two methods used to revise estimates of future project costs.
Revised Estimated Cost At Completion (EACre)
  Allows experts in the field to change original baseline durations and costs because new information tells them the original estimates are not accurate.
  Almost always used on smaller projects.
Forecasted Total Cost At Completion (EACf)
  Used in large projects where the original budget is reliable.

## Slide 53
9–53
Revised Estimated Cost At Completion (EACre)
Lecture
09
EACre = AC + ETCre
Where
EACre = revised estimated cost at completion.
AC = cumulative actual cost of work completed to date.
ETCre = revised estimated cost to complete remaining work.

## Slide 54
9–54
Forecasted Total Cost At Completion (EACf)
Lecture
09
EACf = AC + ETC =
Where
EACf = forecasted total cost at completion.
ETC = estimated cost to complete remaining work.
AC = cumulative actual cost of work completed to date.
CPI = cumulative cost index to date.
BAC = total budget of the baseline.
EV = cumulative budgeted cost of work completed to date.

## Slide 55: Monthly Status Report - Example
9–55

## Slide 56
9–56

## Slide 57
Summary of Today Session
PMG 605
Project Resources and Time Management
Progress and Performance Measurement and Evaluation
Lecture
08
9–57

## Slide 58
9–58

## Slide 59
9–59

## Slide 60
Resources
Project Management: The Managerial Process Fifth Edition. By: Erik W. Larson, Oregon State University, Clifford F. Gray, Oregon State University
9-60

## Slide 61
Thank You