## Slide 1
Project Monitoring Course
Prepared & presented by:
Dr. Dhouha Melliti
2022-2023
Lecture 10:
Evaluation (Part3)

## Slide 2
«
“
Session5:Evaluation
(Part3)
Lecture10
« The passion to create founds the realization project, the passion to love founds the communication project, the passion to play founds the participation project. Separated, these three projects reinforce the repressive unity of power.”Boris Vian

## Slide 3
Lecture9
Session 5:Evaluation
(Part2)
An overview of chapter 5
R
C
E
S
R
E
S
O
U
  Professional standards and ethical guidelines
During the different stages of monitoring or evaluation, including for the collection and use of data, M&E practitioners are required to adopt ethical behaviours that prevent them from being influenced by internal and external pressures that may try to change the findings before they are released or to use them in an inappropriate way.2
    Ethical behaviour
Ethics are a set of values and beliefs that are based on a person’s view of what is right, wrong, good and bad and that influence the decisions people make. They can be dictated by the organization and also by laws in the country in which the M&E practitioners work and what people consider to be ethical in that context.
Evaluation overview
Planning for evaluation
Undertaking evaluation
Follow-up and using evaluation
Accountability and learning from evaluation

## Slide 4
Lecture10
Session 5: Evaluation (Part3)
Accountability and learning from evaluation
The benefits of using information derived from evaluations are numerous. Practitioners must effectively apply this information to enhance accountability, improve performance, as well as strengthen decision- making through learning.
Accountability can be defined as “the obligation to demonstrate that work has been conducted in compliance with agreed rules and standards or to report fairly and accurately on performance results vis-à-vis mandated roles and/or plans. This may require a careful, even a legally sound, demonstration that the work is consistent with the contract terms”.
Learning, on the other hand, is the process by which individuals or organizations acquire and use skills and knowledge. This section will address the various ways of learning through evaluation and other evaluative approaches and, while the requirements related to accountability in sharing an evaluation report are covered in the previous section, this section will also include accountability considerations for the other evaluative approaches that are discussed.

## Slide 5
Lecture10
Session 5: Evaluation (Part3)
    Generating knowledge and learning through evaluation
Regular reflection
Accessibility and regular exchange of information
Reporting
Exchange of knowledge products and learning sessions
Organizational learning and planning process
Information
Knowledge and learning derived from evaluation can feed back into the organizational learning and planning processes through regular reflection, accessibility to the evaluation reports and regular exchange of information through learning sessions.
This can be visualized as follows:

## Slide 6
Lecture10
Session 5: Evaluation (Part3)
Lessons learned and lessons learning
Lessons learned can be understood as generalizations based on evaluation experiences with projects, programs, strategies or policies that abstract from the specific circumstances to broader situations.
Frequently, lessons highlight strengths or weaknesses in preparation, design and implementation that affect performance, outcome and impact. In other words, they are intended to describe the knowledge gained from experiences in well-defined situations.
Documenting lessons learned and incorporating them into other interventions can lead to improving the quality of service delivery. In particular, they can help to avoid practices that may regularly fail to produce results or other common mistakes.

## Slide 7
Lecture10
Session 5: Evaluation (Part3)
The following graphic provides an overview of the process of how lessons learned are identified (through implementation and evaluating implementation), how they are developed and, finally, incorporated and used to improve implementation.
Lessons learned – Improving implementation
Modify/adjust intervention as needed
Implementation1
Evaluating implementation 2
Drafting and sharing lessons learned
3
Incorporating lessons learned and improving implementation
4

## Slide 8
Lecture10
Session 5: Evaluation (Part3)
While lessons learned are generally surfaced through conducting evaluation, lessons learned can also be captured through specific lessons-learning workshops, which bring together various stakeholders to brainstorm on performance and identify the lessons learned from an intervention. This approach can be used as well for interventions at the policy or strategic levels, where stakeholders may be asked to reflect on their approaches to a particular topic or thematic area over time.
Another similar concept, in terms of generating knowledge from an evaluation, is the notion of good practices, which can be seen as the identification of a procedure that has proven to produce results in a satisfactory way and that is proposed as a “standard” practice suitable for widespread adoption. A lesson learned with an identified practice that produces such satisfactory results is identified to be worthy of replicating and possibly upscaling, may, over time, become an “emerging good practice”.

## Slide 9
Lecture10
Session 5: Evaluation (Part3)
A final evaluation report. In particular, they can be incorporated into any evaluation summary documents made available to relevant users.
The Evaluation brief template and guidance contains a specific section for the presentation of lessons learned, when required.
In some cases, lessons learned may be of particular interest to relevant thematic specialists for their further dissemination and applicability to other similar interventions.
The “use” of lessons learned is particularly critical in the development of new interventions, at the project or program level, as well as in the development of strong strategic and policy guidance to a particular area of work.
Therefore, evaluation managers should carefully consider with whom to share lessons learned and identified good practices, in order to best incorporate them into future

## Slide 10
Lecture10
Session 5: Evaluation (Part3)
Project Performance Review
The objective of a PPR is to support field offices in assessing the performance of their interventions, using a constructive, participatory and coordinated approach. The exercise usually takes place during implementation, so that corrective measures can be taken if necessary.
The criteria of relevance, impact and sustainability are briefly analysed through the PPR, and it may also look at the extent to which the outcomes of an intervention are being achieved or may be achieved due to the activities, as well as outputs completed.
A PPR also looks at cross-cutting issues, analyzing the level of accountability to beneficiaries and affected populations, particularly in emergency context, as well as assessing the intervention’s link to global, regional or country strategies.

## Slide 11
Lecture10
Session 5: Evaluation (Part3)
It is important to note that a PPR is not an evaluation, as it is less comprehensive than an evaluation. An evaluation takes more time and preparation, covers issues in greater detail and is able to produce more evidence-based analysis and findings. Further differences between a review and an evaluation can be summarized as follows:
Evaluation | Review
Is a systematic and objective assessment of an ongoing or completed intervention, and its design, implementation and results; Aims to determine the relevance and fulfilment of objectives, and development of efficiency, effectiveness, impact and sustainability; More solid evidence base for accountability and learning. | Is an assessment of the performance of an intervention on a periodic or ad hoc basis; Reviews are usually less comprehensive and/or in- depth than evaluations; Tends to emphasize operational aspects.

## Slide 12
Lecture10
Session 5: Evaluation (Part3)
After-action review
An AAR is a structural discussion about an intervention that enables a team to consider and reflect on what happened, why it has happened and how to sustain strengths and improve weaknesses.
It is a facilitated process involving key actors, in which the general principle is to be neutral and objective to ensure that the discussions stay focused on challenges, remain positive and do not evolve into self- justification.
Essentially, the review should focus on questions, such as the following:
“What was expected versus what actually happen(ed)?”
, “What went well and why?”
and What could have gone better and why?”.

## Slide 13
Lecture10
Session 5: Evaluation (Part3)
After-action review steps
Reconstruct timeline
Timelines of key events, Identify What could have gone better and why?
Brainstorm understanding
  Objective
  Intent
Asked to vote
  The three most important lessons
Summarize conclusions into lessons learned
What could be done better next time?

## Slide 14
Lecture10
Session 5: Evaluation (Part3)
As a first step, participants brainstorm on their understanding of the objective(s) or intent of the action and then develop a timeline of what actually happened and has changed over time. The next step is more focused on an analytical approach, as they identify what went well and why, and what could have gone better and why.
At the end of the process, conclusions of what could be done better next time are summarized into lessons learned. Participants may be asked to vote for what they regard as the three most important lessons in case of multiple considerations. An AAR discussion is a facilitated process and may not last more than half a day or a day. Depending on the resources and time available, it can either be formal, with additional preparatory work, or informal as detailed in the box below.

## Slide 15
Lecture10
Session 5: Evaluation (Part3)
Key features of after-action review | 
Formal reviews Are facilitated by an objective outsider Take more time Use more complex review techniques and tools Are scheduled beforehand Are conducted in meetings or other “formal” settings Require a more standard and thorough report | Informal reviews Are conducted by those closest to the activity Take less time Use simple review techniques and tools Are conducted when needed Are held at the event’s site Can be covered by a less-comprehensive report

## Slide 16
Lecture10
Session 5: Evaluation (Part3)
ther examples of evaluative approaches and tools are summarized as follows:
The most significant change (MSC) is a type of participatory tool that requires gathering personal accounts of perceived change(s) and determining which of these accounts is the most significant and why.
The Kirkpatrick model is a four-level training evaluation model developed to evaluate trainings. The four levels are as follows: (a) reaction; (b) learning; (c) behaviour; and (d) results.
  This is a commonly used method for assessing the results acquired from a training. A generic post- training completion evaluation form has been developed that can be easily modified as required by interested parties.

## Slide 17
Lecture10
Session 5: Evaluation (Part3)
Peer review is a process that can help advise on quality issues and compliance to standards, usually conducted by other specialists from the same field, who are chosen for their knowledge of the subject matter. This process has been used, for instance, for the review of implementation of the United Nations System-wide Action Plan (UN-SWAP) for gender equality and the empowerment of women, with the participation of two to three other agencies being mutually reviewed. A peer review mechanism has also been developed by UNEG in partnership with OECD/DAC to review the evaluation policy of UNEG members.
Outcome harvesting is an evaluative approach that can be used to collect data on interventions. As its name suggests, outcome harvesting collects (“harvests”) evidence of occurred changes (outcomes). Once changes are identified, it works backwards to determine whether and how these changes are linked to your intervention.

## Slide 18
Lecture10
Session 5: Evaluation (Part3)
Incorporating cross-cutting themes in evaluation
Cross-cutting themes can be defined as additional considerations or areas that intersect with an intervention, or that can be easily integrated into it, without losing focus on the main goals of the intervention. Mainstreaming a cross-cutting theme is generally understood as a strategy to make the specific theme, given its importance, an integral dimension of the organization’s design, implementation and M&E of policies and interventions. The inclusion of themes can evolve over time and new themes can be added; they are not necessarily the same for all organizations and not all may be relevant to be considered in an intervention.

## Slide 19
Lecture10
Session 5: Evaluation (Part3)
Incorporating cross-cutting themes in evaluation (1/
Rights-based approach
RBA is a conceptual framework and methodological tool for developing policies and practices. RBA is the conscious and systematic integration of rights, norms and standards derived from international law into programming,
An RBA to migration programming aims to empower rights holders and strengthen the capacity of duty bearers to fulfil their obligations to protect rights holders.

## Slide 20
Lecture10
Session 5: Evaluation (Part3)
.
Although there is no universal understanding of how to apply an RBA to interventions in practice, it generally includes the following attributes that can be applied :
Identification of the rights holders, their entitlements, and duty bearers’ obligations to respect, protect and fulfil those entitlements;
Assessment of whether rights are being respected, protected and fulfilled and, if they are not, an analysis of the underlying causes and a strategy for correcting;
Capacity-building for rights holders to be aware of and enjoy their rights and of duty bearers to meet their obligations;
Ensuring that rights principles (such as non-discrimination, participation and accountability) are integrated into the project, strategy and policy developed and during the implementation process.

## Slide 21
Lecture10
Session 5: Evaluation (Part3)
How to monitor and evaluate rights-based approach?
When considered as a cross-cutting theme, an RBA would require measuring the process of programming and its adherence to rights principles.
These principles can be incorporated into a results matrix and monitored accordingly, or they can be measured without being set out in the matrix by using a monitoring tool.
Lastly, RBA can and should be included in an evaluation; an evaluation should assess rights issues even if the projects themselves do not have a specific rights-based objective or outcome.

## Slide 22
Lecture10
Session 5: Evaluation (Part3)
The following are some questions that can be asked during both monitoring and evaluation processes to ensure that an RBA perspective is covered:
Participation
  Have the various stakeholders (including both rights holders and duty bearers) been involved in planning and designing the M&E of the project and determining the type of data to collect?
  Are other individuals or groups, such as local civil society groups or NGOs, involved?
  Are key groups, particularly the most marginalized groups of rights holders, included and/or involved in the M&E process?

## Slide 23
Lecture10
Session 5: Evaluation (Part3)
Equality and non-discrimination
  Is the M&E process explicitly designed to detect or measure discrimination against particular groups throughout its objectives and outcomes?
  Is the data collected appropriately disaggregated, such as by age, disability, ethnicity, sex, nationality and migration status, to track any gaps in considering equality and discrimination throughout intervention outputs and outcomes?
Accountability, transparency and rule of law
  Are the M&E processes directly linked to any rights such as measuring the realization of specific rights?
  Do the M&E processes account for any form of complaint mechanisms and how are received complaints dealt with?
  Are the findings from the M&E shared publicly in a transparent manner?
  Are the findings from the M&E used to promote changes in law or policy of the State?

## Slide 24
Lecture10
Session 5: Evaluation (Part3)
During the evaluation, the evaluator should also consider the following tips for ensuring that RBA is integrated in the evaluation process:
Include mechanisms to ensure that the most marginalized groups of rights holders are/were involved in the evaluation.
As an evaluator, ask yourself: Were all stakeholders included and how will the evaluation explicitly detect or measure discrimination against particular groups? For example, the evaluation may be designed to detect any form of discriminatory practices that may have occurred during the implementation of the project or as a result of the project.
Identify channels to field any form of complaints that may be received during the evaluation.

## Slide 25
Lecture10
Session 5: Evaluation (Part3)
  Protection mainstreaming
  Is defined as “the inclusion of humanitarian protection principles into the crisis response by ensuring that any response is provided in a way that avoids any unintended negative effects (do no harm),
  Is delivered according to needs, prioritizes safety and dignity, is grounded on participation and empowerment of local capacities and ultimately holds humanitarian actors accountable vis-à-vis affected individuals and communities”.

## Slide 26
Lecture10
Session 5: Evaluation (Part3)
  The following are some questions that can be considered for both the monitoring and evaluation of protection as a cross-cutting theme and to ensure adherence to the protection principles:
  Are monitoring processes designed to ensure that access to humanitarian assistance by all groups is being regularly monitored?
  Are procedures in place to mitigate risks resulting from unintended consequences of activities on protection issues?
  While providing assistance, is the safety and security of beneficiaries taken into consideration? If barriers to services and assistance are identified, are measures being taken to mitigate these barriers?
  Have procedures for informed consent been established and are they being used appropriately?
  Are all affected population and beneficiary groups and subgroups (such as boys, girls, men and women, abled and disabled, marginalized) being involved in monitoring and/or the evaluation processes?

## Slide 27
Lecture10
Session 5: Evaluation (Part3)
  Is specific attention being given to access services by different beneficiary groups and subgroups and in different project locations?
  Are referral pathways for protection incidents established and in use?
  Is sensitive data being managed appropriately and in line with the Data Protection Principles?
  Is feedback from affected populations and beneficiaries regularly collected and used to improve programming to better suit their needs?
  Are self-protection capacities being utilized within the framework of the project?
  Are State and local actors regularly consulted and involved in the implementation of protection measures?
  What impact has been achieved after the introduction of protection mainstreaming considerations during the project design, implementation and monitoring?

## Slide 28
Lecture10
Session 5: Evaluation (Part3)
Below are some key tips for including protection mainstreaming into evaluation:
  Consider a participatory evaluation approach to ensure inclusion of all beneficiary groups.
  Consider how evaluation findings could be used to improve future actions, propose course correctors and ensure that findings that are deemed to be of interest to the larger community are shared.
  Consider to which extent and how protection should be further integrated into intervention activities as a cross-cutting issue

## Slide 29
Lecture10
Session 5: Evaluation (Part3)
  Environmental sensitivity and sustainability
Environmental sensitivity must be addressed by all interventions that should safeguard the environment. Intervention should not have a direct negative impact on the environment, and all possible measures should be taken to prevent harm to biodiversity and ecosystems, such as the destruction or contamination of natural resources.
Environmental sustainability is about addressing human needs without jeopardizing the ability of future generations to meet their needs and preventing irreversible damage to the world. Where sufficient resources and expertise are available, projects should strive towards environmental sustainability.
Environmental issues should be identified and analyzed throughout the intervention as part of the initial risk analysis, as well as addressed as a part of the risk management plan where environmental risks are inevitable.
Mainstreaming environmental sustainability “requires integrating the principles of sustainable management, protection, conservation, maintenance and rehabilitation of natural habitats and their associated biodiversity and ecosystem functions.”

## Slide 30
Lecture10
Session 5: Evaluation (Part3)
How to monitor and evaluate environmental considerations
When interventions are not specifically designed to address environmental issues – such as programs addressing disaster preparedness and disaster risk reduction to prevent forced migration that results from environmental factors, or those for relocation of populations from zones affected by environmental degradations – there are various elements that can be taken into account for monitoring and evaluating the inclusion of environmental sensibility and sustainability as a cross-cutting issue.

## Slide 31
Lecture10
Session 5: Evaluation (Part3)
Considerations | Monitoring or evaluating in the context of an intervention
Environmental factors have always been a cause of migration. | Ensure that environmental factors are included in the rationales of interventions whenever relevant and how the intervention mitigates this.
It is often difficult to isolate the environmental and climatic factors from socioeconomic factors, but an increasing number of studies show that environmental challenges are clearly a factor that impact the decision to move or to stay. | When relevant and feasible, these factors should be identified and how the intervention indirectly address them as a cross-cutting theme. The linkage of these factors may often be explained in a ToC.
Climate change is expected to have major impacts on human mobility as the movement of people is and will continue to be affected by natural disasters and environmental degradation. | As a cross-cutting theme in interventions dealing with mobility, the role and impact of the environment should be identified, if not specifically addressed by an objective and outcome.
Environmental migration may take many complex forms: forced and voluntary, temporary and permanent, internal and international. | When examining the role and impact of the environment on IOM interventions dealing with migration, it could be relevant to identify if it can be categorized as “environmental migration” and if the intervention addresses it properly.

## Slide 32
Lecture10
Session 5: Evaluation (Part3)
The following are a series of questions that could be included in the evaluation ToR to ensure that environmental sensitivity and sustainability were properly integrated.
Would it have been relevant to conduct an environmental impact assessment for this intervention?
Was the project successfully implemented without any negative impact on the environment that could have affected human well-being?
Has environmental damage been caused or likely to be caused by the project? What kind of environmental impact mitigation measures have been taken?
Were appropriate environmental practices followed in project implementation?
Does the project respect successful environmental practices identified ?
What are the existing capacities (within project, project partners and project context) dealing with critical risks that could affect project effectiveness such as climate risks or risks of natural disasters?
Will the achievement of project results and objectives likely to generate increased pressure on fragile ecosystems (such as natural forests, wetlands, coral reefs and mangroves) and scarce natural resources (such as surface and groundwater, timber and soil)?
Did the intervention bring relevant benefits and innovation for environmental sensitivity and sustainability?

## Slide 33
Lecture10
Session 5: Evaluation (Part3)
Evaluative approaches: Most significant change
A most significant change (MSC) is a type of participatory monitoring and evaluation. It involves gathering personal account of change and determining which of these accounts is the most significant and why. It is participatory because it involves multiple stakeholders in deciding what type of change to record and analyze.
It is also a form of monitoring, because gathering of data occurs throughout the implementation cycle and provides information for decision makers.
Finally, MSC is a form of evaluation, because it provides information on higher-level results, such as outcomes and impact, which can be useful to assess implementation performance as a whole.

## Slide 34
Lecture10
Session 5: Evaluation (Part3)
Incorporating cross-cutting themes in evaluation
Cross-cutting themes can be defined as additional considerations or areas that intersect with an intervention, or that can be easily integrated into it, without losing focus on the main goals of the intervention. Mainstreaming a cross-cutting theme is generally understood as a strategy to make the specific theme, given its importance, an integral dimension of the organization’s design, implementation and M&E of policies and interventions. The inclusion of themes can evolve over time and new themes can be added; they are not necessarily the same for all organizations and not all may be relevant to be considered in an intervention.

## Slide 35
Lecture10
Session 5: Evaluation (Part3)
The following are a series of questions that could be included in the evaluation ToR to ensure that environmental sensitivity and sustainability were properly integrated.
Would it have been relevant to conduct an environmental impact assessment for this intervention?
Was the project successfully implemented without any negative impact on the environment that could have affected human well-being?
Has environmental damage been caused or likely to be caused by the project? What kind of environmental impact mitigation measures have been taken?
Were appropriate environmental practices followed in project implementation?
Does the project respect successful environmental practices identified in project?
What are the existing capacities (within project, project partners and project context) dealing with critical risks that could affect project effectiveness such as climate risks or risks of natural disasters?

## Slide 36
Lecture10
Session 5: Evaluation (Part3)
Evaluative approaches: the most important change
The most important change is the type of participatory monitoring and evaluation. It involves collecting the personal account of the change and determining which of these accounts is the most important and why. It is participatory because it involves multiple stakeholders in determining the type of change to be recorded and analyzed.
It is also a form of monitoring, because data collection takes place throughout the implementation cycle and provides information to decision makers.
Finally, one of the most important changes is in the form of evaluation, as it provides information on higher-level outcomes, such as outcomes and impact, that can be useful for assessing implementation performance as a whole.

## Slide 37
Lecture10
Session 5: Evaluation (Part3)
.
When to use it
MSC had different names, one of which is “monitoring-without-indicators” or “story approach”, as it does not make use of performance indicators and the answer to how change occurred is formulated in a story. In this sense, MSC is very helpful instrument in explaining how and when change comes about, which makes it useful to support the development of a Theory of Change.
How it is done
Scholars may disagree on the number of steps in using MSC, but in essence, these can be summarized into three basic steps:
Panels of key stakeholders at different hierarchical levels (such as field staff, programme staff, managers and donors) decide together on what type of significant change accounts/stories should be collected. As these stories come from the field, key stakeholders identify general domains of change and the frequency to be monitored, such as changes in people’s lives for example.

## Slide 38
Lecture10
Session 5: Evaluation (Part3)
The most significant change is identified at each level along with a detailed explanation of the selection criteria.
Stories are shared, values and selection criteria are discussed with stakeholders and in this way contribute to learning.
Points of strength and weakness
As it provides information about unintended/intended impact, but also helps articulate the values held by various stakeholders in terms of what success looks like. Note that MSC by itself is not sufficient for an impact analysis, as it does not adequately explain why change occurred and provides information about extremes, rather than the usual experience. One of its limitations is that it is time consuming and requires thorough follow-up and multiple meetings with stakeholders.

## Slide 39
Lecture9