## ورقة1
student name |  | Nouf Alhuzaim | student Id | 2021206113
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | To establishment of the hyperloop project, there must be a completely suitable environment for the construction of the infrastructure of hyperloop lines and pipelines | high | high | Geographical terrain | Work to prepare an appropriate and appropriate environment for the Hyperloop project | Project Manger | مشروع الهايبر لوب
2 | THREATS | Mechanical failure | high | low | Breakdowns | long term maintenance plan, continuance engineering counselling, 24/7 shift technical support | Engineering Dir. / Mainten. Dir. | مشروع الهايبر لوب
3 | OPPORTUNITIES | reducing emissions | high | high | Low emission transportation model | capitalize on the fact that this technology has low emissions | CEO/ Environmental Dir. /Engineering Dir. | مشروع الهايبر لوب
4 | OPPORTUNITIES | sustainable; controlled weather | high | high | efficient way of transportation during bad weather | offer more trips during bad weather season | Operation Dir. | مشروع الهايبر لوب
5 | OPPORTUNITIES | job opportunities , Better distribution of manpower, competencies and specialized expertise at the level of one country | high | moderate | Employment need | Recruitment of competencies Contracting with recruitment companies | HR maneger | مشروع الهايبر لوب
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low