## Slide 1
PMG510
Project Risk Management
Prepared by Dr. Salahaldin Abuabdou
Approaches to defining risk
Lecture 1

## Slide 2
Reference

## Slide 3
Course Outlines
Approaches to defining risk | Risk management standards
Impact of risk on organizations | establishing the context
Types of risks | enterprise risk management
Scope of risk management | Alternative approaches
Principles and aims of risk management | Risk assessment considerations

## Slide 4
Lecture Outlines
Risk management in context
Nature of risk
Risk management terminology
Benefits of risk management
Features of risk management
Definitions of risk
Types of risks
Risk description
Inherent level of risk
Risk classification systems
Risk likelihood and magnitude

## Slide 5
Risk Management Introduction
Risk management in context:
We all face risks in our everyday lives. Risks arise from personal activities and range from those associated with travel through to the ones associated with personal financial decisions.
There are considerable risks present in the domestic component of our lives, and these include fire risks in our homes and financial risks associated with home ownership.
Indeed, there are also a whole range of risks associated with domestic and relationship issues, but these are outside the scope of this course.
This course is primarily concerned with business and commercial risks and the roles that we fulfil in our job or occupation.
However, the task of evaluating risks and deciding how to respond to them is a daily activity, not only at work but also at home and during leisure activities.

## Slide 6
Risk Management Introduction
Nature of risk:
Recent events in the world have brought risk into higher profile. Terrorism, extreme weather events and the global financial crisis represent the extreme risks that are facing society and commerce, and finally covid19.
Evaluating the range of risk responses available and deciding the most appropriate one in each case is at the heart of risk management.
Responding to risks should produce benefits for us as individuals, as well as for the organizations where we work and/or are employed.
Fire and accident are the types of risks that can only have negative outcomes, and they are often referred to as hazard risks.
Compliance requirements are viewed by many organizations as hazard risks, whereby failure to comply can only be negative

## Slide 7
Risk Management Introduction
Nature of risk:
However, other organizations have the view that achieving compliance can bring additional benefits or deliver the ‘upside of risk’.
Some other risks have established or required responses that are imposed on us as individuals and/or on organizations as mandatory requirements
Examples,
In our personal lives, buying insurance for a car is usually a legal requirement, whereas buying insurance for a house is often not, but is good risk management and very sensible.
Keeping your car in good mechanical order will reduce the chances of a breakdown. However, even vehicles that are fully serviced and maintained do occasionally break down. Maintaining your car in good mechanical order will reduce the chances of breakdown, but will not eliminate them completely.

## Slide 8
Risk Management Introduction
Nature of risk:
These types of risks that have a large degree of uncertainty associated with them are often referred to as control risks.
As well as hazard and control risks, there are risks that we take because we desire (and probably expect) a positive return.
Example, you will invest money in anticipation that you will make a profit from the investment. Likewise, placing a bet or gambling on the outcome of a sporting event is undertaken in anticipation of receiving positive payback.
People participate out of choice in motor sports and other potentially dangerous leisure activities.
In these circumstances, the return may not be financial, but can be measured in terms of pride, self-esteem or peer group respect. Undertaking activities involving risks of this type, where a positive return is expected, can be referred to as taking opportunity risks.

## Slide 9
Risk Management Introduction
Risk management:
Organizations face a very wide range of risks that can impact the outcome of their operations
The events that can impact an organization may inhibit what it is seeking to achieve (hazard risks), enhance that aim (opportunity risks), or create uncertainty about the outcomes (control risks).
Risk management needs to offer an integrated approach to the evaluation, control and monitoring of these three types of risk.
Risk management also has an important part to play in the success of not-for-profit organizations such as charities and (for example) clubs and other membership bodies.
the risk management framework is presented and described in different ways in the range of standards, guides and other publications that are available.
The key components of a successful risk management framework are the communications and reporting structure (architecture), the overall risk management strategy that is set by the organization (strategy) and the set of guidelines and procedures (protocols) that have been established.

## Slide 10
Risk Management Introduction
Risk management terminology:
Most risk management publications refer to the benefits of having a common language of risk within the organization.
Many organizations manage to achieve this common language and common understanding of risk management processes and protocols at least internally.
However, it is usually the case that within a business sector, and sometimes even within individual organizations, the development of a common language of risk can be very challenging.
Reference and supporting materials use a great range of terminologies.
The different approaches to risk management, the different risk management standards that exist and the wide range of guidance material that is available often use different terms for the same feature or concept. This is regrettable and can be very confusing, but it is inescapable.

## Slide 11
Risk Management Introduction
Risk management terminology:
Attempts are being made to develop a standardized language of risk, and ISO Guide 73 has been developed as the common terminology that should be used in all ISO standards.
The terminology set out in ISO Guide 73 is used throughout this course as the default set of definitions wherever possible.
However, the use of a standard terminology is not always possible and alternative definitions may be required.
Indeed, ISO itself also publish a terminology guide, ISO/IEC Guide 51:1999, entitled ‘Safety Aspects: – Guidelines for Their Inclusion in Standards’, and the definitions in Guide 51 are not fully aligned with those in Guide 73.

## Slide 12
Risk Management Introduction
Benefits of risk management:
There are a range of reasons why organizations undertake risk management activities
These reasons are summarized in this course as mandatory, assurance, decision making and effective and efficient core processes (MADE2)
Mandatory refers to risk management activities designed to ensure that an organization complies with legal and regulatory obligations, as well as customer or client requirements.
The board of an organization will require assurance that significant risks have been identified and appropriate controls put in place
In order to ensure that correct business decisions are taken, the organization should undertake risk management activities that provide additional structured information to assist with business decision making.
Finally, a key benefit from risk management is to enhance the effectiveness and efficiency of operations within the organization.

## Slide 13
Risk Management Introduction
Benefits of risk management:
It should help ensure that business processes (including process enhancements by way of tactics, projects and other change initiatives) are also effective and efficient
Risk management inputs are required in relation to strategic decision making, but also in relation to the effective delivery of projects and programmes of work, as well as in relation to the routine operations of the organization.
Strategy, tactics and operations are underpinned by the need to achieve compliance.
Strategic, tactical, operational and compliance (STOC) core processes and activities encompass the whole range of processes of an organization

## Slide 14
Risk Management Introduction
Features of risk management:
Failure to adequately manage the risks faced by an organization can be caused by inadequate risk recognition, insufficient analysis of significant risks and failure to identify suitable risk response activities.
Also, failure to set a risk management strategy and to communicate that strategy and the associated responsibilities may result in inadequate management of risks.
It is also possible that the risk management procedures or protocols may be flawed, such that these protocols may actually be incapable of delivering the required outcomes.
The consequences of failure to adequately manage risk can be disastrous and may result in ineffective and/or inefficient operations, projects that are not completed on time and strategies that are not delivered, or were incorrect in the first place.
In order to be successful, the risk management initiative should be proportionate, aligned, comprehensive, embedded and dynamic (PACED).

## Slide 15
Risk Management Introduction
Features of risk management:
Proportionate means that the effort put into risk management should be appropriate to the level of risk that the organization faces.
Risk management activities should be aligned with other activities within the organization.
Activities will also need to be comprehensive, so that any risk management initiative covers all the aspects of the organization and all the risks that it faces.
As with all management activities and processes in an organization, risk management needs to be adapted and modified to align with the core processes, and organizational culture.
In relation to risk management, an organization will first need to specifically respond to statutory obligations and the requirements of regulators.
Once they have been satisfied, most organizations can work on the basis that whatever works within the organization and delivers the required benefits, outputs and outcomes is the correct and appropriate approach to (Enterprise Risk Management) ERM for that organization

## Slide 16
Chapter 1 Approaches to defining risk
The definition of at risk is ‘exposed to danger’.
Risk is used to signify negative consequences. However, taking a risk can also result in a positive outcome. A third possibility is that risk is related to uncertainty of outcome.
Ex. Take the example of owning a motor car. For most people, owning a car is an opportunity to become more mobile and gain the related benefits. However, there are uncertainties in owning a car that are related to maintenance and repair costs. Finally, motor cars can be involved in accidents, so there are obvious negative outcomes that can occur. It is also important to remember the legal obligations associated with car ownership and the rules that must be obeyed when the car is being driven on a road.
Definitions of risk :

## Slide 17
Chapter 1 Approaches to defining risk
Definitions of risk can be found from many sources, and some key definitions are set out in the following table (Definitions of risk ):
Organization | Definition of risk
ISO Guide 73 ISO 31000 | Effect of uncertainty on objectives. Note that an effect may be positive, negative, or a deviation from the expected. Also, risk is often described by an event, a change in circumstances or a consequence
Institute of Risk Management (IRM) | Risk is the combination of the probability of an event and its consequence. Consequences can range from positive to negative.
Orange Book from HM Treasury | Uncertainty of outcome, within a range of exposure, arising from a combination of the impact and the probability of potential events.
Institute of Internal Auditors | The uncertainty of an event occurring that could have an impact on the achievement of the objectives. Risk is measured in terms of consequences and likelihood.
Definitions of risk :

## Slide 18
Chapter 1 Approaches to defining risk
It is generally accepted that risk is best defined by concentrating on risks as events, as in the definition of risk provided in ISO 31000 and the definition provided by the Institute of Internal Auditors
perhaps a risk can simply be considered to be ‘an unplanned event with unexpected consequences’. Greater clarity is likely to be brought to the risk management process if the focus is on events.
Ex. What could disrupt a theatre performance “The events that could cause disruption include a power cut, the absence of a key actor, or a substantial transport failure or road closures that delay the arrival of the audience, as well as the illness of a significant number of staff. Having identified the events that could disrupt the performance, the management of the theatre needs to decide what to do to reduce the chances of one of these events causing the cancellation of a performance. “
Definitions of risk :

## Slide 19
Chapter 1 Approaches to defining risk
Risk may have positive or negative outcomes or may simply result in uncertainty. Therefore, risks may be considered to be related to an opportunity or a loss or the presence of uncertainty for an organization.
Risks are divided into four categories:
Compliance (or mandatory) risks;
Hazard (or pure) risks;
Control (or uncertainty) risks;
Opportunity (or speculative) risks
Types of risks:

## Slide 20
Chapter 1 Approaches to defining risk
In general, organizations will seek to minimize compliance risks, mitigate hazard risks, manage control risks and embrace opportunity risks.
It is important to note that there is no ‘right’ or ‘wrong’ subdivision of risks. Whatever the theoretical discussions, the most important issue is that an organization adopts the risk classification system that is most suitable for its own circumstances
There are certain risk events that can only result in negative outcomes. These risks are hazard risks or pure risks, and these may be thought of as operational or insurable risks.
In general, organizations will have a tolerance of hazard risks, and these need to be managed within the levels that the organization can tolerate. A good example of a hazard risk faced by many organizations is that of theft.
Types of risks:

## Slide 21
Chapter 1 Approaches to defining risk
There are other risks that give rise to uncertainty about the outcome of a situation. These can be described as control risks and are frequently associated with project management.
In general, organizations will have an aversion to control risks. Uncertainties can be associated with the benefits that the project produces, as well as uncertainty about the delivery of the project on time, within budget and to specification.
organizations deliberately take risks, especially marketplace or commercial risks, in order to achieve a positive return. These can be considered as opportunity or speculative risks, and an organization will have a specific appetite for investment in such risks.
Opportunity risks relate to the relationship between risk and return. The purpose is to take action that involves risk to achieve positive gains. The focus of opportunity risks will be towards investment.
Types of risks:

## Slide 22
Chapter 1 Approaches to defining risk
Hazard risks are the most common risks associated with operational risk management, including occupational health and safety programmes.
Control risks are associated with unknown and unexpected events. They are sometimes referred to as uncertainty risks and they can be extremely difficult to quantify.
There are two main aspects associated with opportunity risks. There are risks/ dangers associated with taking an opportunity, but there are also risks associated with not taking the opportunity. Opportunity risks may not be visible or physically apparent, and they are often financial in nature.
Although opportunity risks are taken with the intention of obtaining a positive outcome, this is not guaranteed.
Types of risks:

## Slide 23
Chapter 1 Approaches to defining risk
The following items list the range of information that must be recorded to fully understand a risk.
Name or title of risk
Statement of risk, including scope of risk and details of possible events and dependencies
Nature of risk, including details of the risk classification and timescale of potential impact
Stakeholders in the risk, both internal and external
Risk attitude, appetite, tolerance, limits for the risk and/or risk criteria
Likelihood and magnitude of event and consequences should the risk materialize at current /residual level
Control standard required, target level of risk or risk criteria
Incident and loss experience
Risk description:

## Slide 24
Chapter 1 Approaches to defining risk
The following items list the range of information that must be recorded to fully understand a risk. (cont.)
Existing control mechanisms and activities
Responsibility for developing risk strategy and policy
Potential for risk improvement and level of confidence in existing controls
Risk improvement recommendations and deadlines for implementation
Responsibility for implementing improvements
Responsibility for auditing risk compliance
Risk description:

## Slide 25
Chapter 1 Approaches to defining risk
The example below is intended to distinguish between these four types of risk.
Risk description:
Example: Range of computer risks:
In order to understand the distinction between compliance, hazard, control and opportunity risks, the example of the use of computers is helpful.
Operating a computer system involves fulfilling certain legal obligations; in particular, data protection requirements and these are the compliance risks.
Virus infection is an operational or hazard risk and there will be no benefit to an organization suffering a virus attack on its software programs.
When an organization installs or upgrades a software package, control risks will be associated with the upgrade project.
The selection of new software is also an opportunity risk, where the intention is to achieve better results by installing the new software, but it is possible that the new software will fail to deliver all of the functionality that was intended and the opportunity benefits will not be delivered. In fact, the failure of the functionality of the new software system may substantially undermine the operations of the organization

## Slide 26
Chapter 1 Approaches to defining risk
It is important to understand the uncontrolled level of all risks that have been identified.
This is the level of the risk before any actions have been taken to change the likelihood or magnitude of the risk.
Although there are advantages in identifying the inherent level of risk, there are practical difficulties in identifying this with some types of risks
Identifying the inherent level of the risk makes it possible to identify the importance of the control measures in place.
The IIA has previously held the view that the assessment of all risks should commence with the identification of the inherent level of the risk.
The guidance from the IIA has previously stated that: ‘in the risk assessment, we look at the inherent risks before considering any controls.’
Inherent level of risk:

## Slide 27
Chapter 1 Approaches to defining risk
Often, a risk matrix is used to show the inherent level of the risk in terms of likelihood and magnitude.
The residual or current level of the risk can then be identified, after the control or controls have been put in place.
The effort that is required to reduce the risk from its inherent level to its current level can be clearly indicated on the risk matrix.
The inherent level of risk is sometimes referred to as the absolute risk or gross risk.
The current level of risk is often referred to as the residual level, net level or the managed level of risk.
Inherent level of risk:

## Slide 28
Chapter 1 Approaches to defining risk
The following example provides an example of how inherently high-risk activities are reduced to a lower level of risk by the application of sensible and practical risk response options.
Inherent level of risk:
Ex. Crossing road
Crossing a busy road would be inherently dangerous if there were no controls in place and many more accidents would occur.
When a risk is inherently dangerous, greater attention is paid to the control measures in place, because the perception of risk is much higher.
Pedestrians do not cross the road without looking and drivers are always aware that pedestrians may step into the road. Often, other traffic calming control measures are necessary to reduce the speed of the motorists or increase the risk awareness of both motorists and pedestrians.

## Slide 29
Chapter 1 Approaches to defining risk
Risks can be classified according to the nature of the attributes of the risk, such as timescale for impact, and the nature of the impact and/or likely magnitude of the risk.
They can also be classified according to the timescale of impact after the event occurs
The source of the risk can also be used as the basis of classification. In this case, a risk may be classified according to its origin, such as counterparty or credit risk.
A further way of classifying risks is to consider the nature of the impact.
Some risks can cause detriment to the finances of the organization, whereas others will have an impact on the activities or the infrastructure. Further, risks may have an impact on the reputation of the organization, or on its status and the way it is perceived in the marketplace.
Risk classification systems:

## Slide 30
Chapter 1 Approaches to defining risk
Risks may also be classified according to the component or feature of the organization that will be impacted
Ex, Risks can be classified according to whether they will impact people, premises, processes or products.
An important consideration for organizations when deciding their risk classification system is to determine whether the risks will be classified according to the source of the risk, the component impacted or of the consequences of the risk materializing.
Individual organizations will decide on the risk classification system that suits them best, depending on the nature of the organization and its activities.
Risk classification systems:

## Slide 31
Chapter 1 Approaches to defining risk
Also, many risk management standards and frameworks suggest a specific risk classification system. If the organization adopts one of these standards, then it will tend to follow the classification system recommended.
The risk classification system that is selected should be fully relevant to the organization concerned.
There is no universal classification system that fulfils the requirements of all organizations.
Risk classification systems:

## Slide 32
Chapter 1 Approaches to defining risk
Risk likelihood and magnitude are best demonstrated using a risk matrix.
Risk matrices can be produced in many formats. Whatever format is used for a risk matrix, it is a very valuable tool for the risk management practitioner.
The basic style of risk matrix plots the likelihood of an event against the magnitude or impact should the event materialize.
The following figure is an illustration of a simple risk matrix, also referred to as a risk map or heat map.
This is a commonly used method of illustrating risk likelihood and the magnitude (or severity) of the event should the risk materialize.
The use of the risk matrix to illustrate risk likelihood and magnitude is a fundamentally important risk management tool
Risk likelihood and magnitude:

## Slide 33
Chapter 1 Approaches to defining risk
Risk likelihood and magnitude:
The use of the risk matrix to illustrate risk likelihood and magnitude is a fundamentally important risk management tool.
The risk matrix can be used to plot the nature of individual risks, so that the organization can decide whether the risk is acceptable and within the risk appetite and/or risk capacity of the organization.

## Slide 34
Chapter 1 Approaches to defining risk
The term likelihood is used rather than frequency, because the word frequency implies that events will definitely occur and the risk matrix is registering how often these events take place.
Likelihood is a broader word that includes frequency, but also refers to the chances of an unlikely event happening. However, in risk management literature, the word ‘probability’ will often be used to describe the likelihood of a risk materializing
The word magnitude is used rather than severity, so that the same style of risk matrix can be used to illustrate compliance, hazard, control and opportunity risks.
Severity implies that the event is undesirable and is, therefore, related to compliance and hazard risks.
The magnitude of the risk may be considered to be its gross or inherent level before controls are applied.
Risk likelihood and magnitude:

## Slide 35
Chapter 1 Approaches to defining risk
Figure 1.1 plots likelihood against the magnitude of an event. However, the more important consideration for risk managers is not the magnitude of the event, but the impact of the event and the consequences that follow.
Example, a large fire could occur that completely destroys a warehouse of a distribution and logistics company. Although the magnitude of the event may be large, if sufficient insurance is in place, the impact in terms of financial costs for the company could be minimal, and if the company has produced plans to cope with such an event, the consequences for the overall business may be much less than would otherwise be anticipated.
Risk likelihood and magnitude:

## Slide 36
Chapter 1 Approaches to defining risk
The magnitude of an event may be considered to be the inherent level of the event and the impact can be considered to be the risk-managed level.
Because the impact (and the associated consequences) of an event is usually more important than its magnitude (or severity), every risk matrix used in the remainder of this COURSE will plot impact against likelihood, rather than magnitude against likelihood.
Risk likelihood and magnitude:

## Slide 37
Thanks