## Slide 1
PROJECT MONITORING
Lecture 08
PMG333
Dr. Bassel alhassan
Prepared by
COST& TIME MONITORING 1

## Slide 2
1 - 2
Lecture
08
Lecture Contents

## Slide 3
1 - 3
Lecture
08

## Slide 4
1 - 4
Lecture
08
ISO 21508:2018

## Slide 5
1 - 5
Lecture
08
Scope & Objective of ISO 21508:2018

## Slide 6
1 - 6
Lecture
08
EVM Implementation Steps

## Slide 7
1 - 7
Lecture
08
EVM Implementation Steps

## Slide 8
1 - 8
Lecture
08
Step 1: Decompose the Project Scope

## Slide 9
1 - 9
Lecture
08
General Concepts of WBS
Notes: لتحقيق هذا التقسيم الدقيق، نستخدم أداة أساسية ولا غنى عنها تسمى "هيكل تقسيم العمل" أو (Work Breakdown Structure - WBS). من المهم جداً أن نصحح مفهوماً خاطئاً شائعاً: الـ WBS ليس مجرد قائمة مهام (To-Do List) نكتبها على ورقة، بل هو هيكل هرمي منظم يركز بشكل أساسي على "المخرجات" (Deliverables) وليس على الأنشطة. نحن نهتم بما سنقوم بتسليمه، وليس فقط بما سنقوم بفعله.
القاعدة الذهبية هنا، والتي ينص عليها المعيار بصرامة، هي "قاعدة الـ 100%". ماذا تعني هذه القاعدة في الواقع العملي؟ تعني أن الـ WBS يجب أن يشمل 100% من العمل المطلوب في المشروع، ولا شيء خارج نطاق المشروع. رياضياً ومنطقياً، مجموع العمل في المستويات الدنيا (الفروع) يجب أن يساوي تماماً 100% من العمل في المستوى الأعلى (الجذر). إذا نسينا أي جزء، مهما كان صغيراً، فإن ميزانيتنا وجدولنا الزمني سيكونان غير دقيقين منذ اليوم الأول، وسنواجه مفاجآت غير سارة لاحقاً. وإذا أضفنا عملاً غير مطلوب، سنكون قد أهدرنا موارد المشروع.

## Slide 10
1 - 10
Lecture
08
Characteristics of an Effective WBS

## Slide 11
1 - 11
Lecture
08
Work Packages & WBS Dictionary

## Slide 12
1 - 12
Lecture
08
Practical Example 1

## Slide 13
1 - 13
Lecture
08
Practical Example 2: Smartphone App Development

## Slide 14
1 - 14
Lecture
08
Takeaways

## Slide 15
1 - 15
Lecture
08
Step2: Assign Responsibility

## Slide 16
1 - 16
Lecture
08
Guidelines for Assigning Responsibility

## Slide 17
1 - 17
Lecture
08
Practical Example: Software Development

## Slide 18
1 - 18
Lecture
08
Step 3: Schedule Work

## Slide 19
1 - 19
Lecture
08
Guidelines for Developing Project Schedules

## Slide 20
1 - 20
Lecture
08
Practical Example: Retaining Wall Construction

## Slide 21
1 - 21
Lecture
08
Step 4: Develop Time- Phased Budget

## Slide 22
1 - 22
Lecture
08
Practical Example: Time- Phased Budget for Retaining Wall

## Slide 23
1 - 23
Lecture
08
Step 5: Assign Performance Metrics

## Slide 24
1 - 24
Lecture
08
Guidelines for Performance Metrics

## Slide 25
1 - 25
Lecture
08
Practical Example: Assigning Metrics to Retaining Wall

## Slide 26
1 - 26
Lecture
08
Step 6: Establish PMB (Performance Management Baselines )

## Slide 27
1 - 27
Lecture
08
Step 6: Establish PMB (Performance Management Baselines )

## Slide 28
1 - 28
Lecture
08
Step 7: Authorize & Execute Work (ISO 21508:2018)

## Slide 29
1 - 29
Lecture
08
Step 8: Data Collection (ISO 21508:2018)

## Slide 30
1 - 30
Lecture
08
Step 9: Performance Analysis (EVM)

## Slide 31
فا
1 - 31
Lecture
08
The requirement is to deliver ten tables in ten days at a cost of one thousand per table
As a result, one table is delivered daily at a unit cost of one thousand
Review of Previous Session

## Slide 32
1 - 32
Lecture
08
By day four, the planned completion is four tables at a cost of 4,000
However, upon reviewing the actual progress on day four, three tables had been completed at a cost of 5,000
Review of Previous Session

## Slide 33
1 - 33
Lecture
08
Actual Cost of Work Performed (ACWP)= 5000
Budget Cost of Work Schedule (BCWS)= 4000
Budget Cost of Work Performed (BCWP)=3000
Review of Previous Session

## Slide 34
1 - 34
Lecture
08
Schedule Variance (SV)
= BCWP-BCWS
= 3000-4000=-1000<0
behind schedule
Lecture
Cost Variance (CV)
= BCWP-ACWP
= 3000- 5000= -2000<0
over budget
Review of Previous Session

## Slide 35
1 - 35
Lecture
08
Schedule performance Index (SPI)
= BCWP / BCWS
= 3000/4000=0.75<1
behind schedule
Cost performance Index (CPI)
= BCWP / ACWP
= 3000/5000=0.6<1
over budget
Review of Previous Session

## Slide 36
1 - 36
Lecture
08
Estimated Final Time (EFT)
EFT = TAC / SPI
EFT= 10/0.75= 13.33= 14
Review of Previous Session

## Slide 37
1 - 37
Lecture
08
EAC = BAC / CPI
        EAC = 10000 / 0.6=16667(Estimated at complete )
Estimated Cost At Completion (EAC)
  EAC = ACWP+ Original Remaining Budget
Review of Previous Session

## Slide 38
1 - 38
Lecture
08
ETC = EAC – ACWP(estimated to complete )
ETC= 16667-5000=11667
Estimated To Complete (ETC)
VAC = BAC – EAC
VAC= 10000-16667=-6667
Variance At Completion (VAC)
Variance At Completion= Budget Cost At Completion - Estimated Cost At Completion
Review of Previous Session

## Slide 39
1 - 39
Lecture
08
EVM Graph
In the adjacent graph, we observe that the curve representing the Earned Value (in red) lies below the curve representing the Planned Value. Consequently, the Schedule Variance (SV) value will be negative, indicating that the project is behind schedule."
"Similarly, we observe that the curve representing the Earned Value (in red) lies below the curve representing the Actual Cost. Consequently, the Cost Variance (CV) value will be negative, which means the project is over budget based on the current performance

## Slide 40
1 - 40
Lecture
08
In the adjacent chart, we observe that until week six, the curve representing the Earned Value was higher than the curve representing the Planned Value. Therefore, the schedule variance was positive, and the project was ahead of schedule. However, starting from the sixth week, the Earned Value curve fell below the Planned Value. Consequently, schedule performance declined, the schedule variance became negative, and a delay relative to the planned value will occur."
"Throughout the entire duration of the project, the curve representing the Earned Value remained higher than the curve representing the Actual Cost. Therefore, the cost performance is excellent, and the project will be completed under the contractual budget
EVM Graph

## Slide 41
Thank You