## Slide 1
Project Monitoring Course
Prepared & presented by:
Dr. Dhouha Melliti
2022-2023
Lecture 02: Part(1)
Norms, standards and management
for monitoring and evaluation

## Slide 2
General Introduction
Lecture 2
«The future was created to be changed» Paolo Coelho

## Slide 3
Lecture 2
By the end of this session, the participants will be able to:
Understand conceptual frameworks, principles, and guidelines necessary for the effective design and operation of project monitoring and evaluation systems,
To highlight results-based monitoring and evaluation and the key steps for implementation.
To set out the key principles for developing indicators.
Understand what elements are essential to successful M&E, and what must be avoided.
Session Learning Outcomes:

## Slide 4
pre-requisites
Lecture 2
1. small reminder...
What is M&E?
M&E is a process of continual gathering of information and assessment of it in order to determine whether progress is being made towards pre-specified goals and objectives, and to highlight whether there are any unintended (positive or negative) effects from a project and its activities. It is an integral part of the project cycle and of good management practice.

## Slide 5
Lecture 2
Monitoring is carried out in order to track progress and performance as a basis for decision-making at various steps in the process of an initiative or project.
Evaluation, on the other hand is a more generalised assessment of data or experience to establish to what extent the initiative has achieved its goals or objectives.
pre-requisites

## Slide 6
pre-requisites
Lecture 2
The key reasons for M&E can be summarised under
4 headings
For accountability: demonstrating to donors, taxpayers, beneficiaries and implementing partners that expenditure, actions and results are as agreed or can reasonably be expected in the situation.
2. For operational management: provision of the information needed to co-ordinate the human, financial and physical resources committed to the project or programme, and to improve performance

## Slide 7
Session 1: General introducton
Lecture 2
3. For strategic management: provision of information to inform setting and adjustment of objectives and strategies.
4. For capacity building: building the capacity, self-reliance and confidence of beneficiaries and implementing staff and partners to effectively initiate and implement development initiatives.

## Slide 8
Monitoring and evaluation of projects can be a powerful means to measure their performance, track progress towards achieving desired goals, and demonstrate that systems are in place that support organisations in learning from experience and adaptive management.
Used carefully at all stages of a project cycle, monitoring and evaluation can help to strengthen project design and implementation and stimulate partnerships with project stakeholders.
Session 1: General introducton
Lecture 2

## Slide 9
2. Why a M&E system?
Improve project and programme design through the feedback provided from mid- term, terminal and ex post evaluations;
Inform and influence sector and country assistance strategy through analysis of the outcomes and impact of interventions, and the strengths and weaknesses of their implementation, enabling governments and organisations to develop a knowledge base of the types of interventions that are successful (ie what works, what does not and why?
Session 1: General introducton
Lecture 2

## Slide 10
Session 1: General introducton
Provide regular feedback on project performance and show any need for ‘mid- course’ corrections
identify problems early and propose solutions
monitor access to project services and outcomes by the target population;
Evaluate achievement of project objectives
measure the impact of the project on various indicators (including those relating to project objectives and other areas of concern)
Incorporate stakeholder views and promote participation, ownership and accountability
provide the evidential basis for building consensus between stakeholder
Lecture 2

## Slide 11
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.1- M&E systems and common deficiencies
A monitoring and evaluation system is made up of the set of interlinked activities that must be undertaken in a co-ordinated way to plan for M&E, to collect and analyse data, to report information, and to support decision-making and the implementation of improvements.
Lecture 2

## Slide 12
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
6 components of a project M&E system
–Clear statements of measurable objectives for the project .
–A structured set of indicators covering: inputs, process, outputs, outcomes, impact, and exogenous factors.
–Data collection mechanisms capable of monitoring progress over time, including baselines and a means to compare progress and achievements against targets.
–Where applicable building on baselines and data collection with an evaluation framework and methodology capable of establishing causation (ie capable of attributing observed change to given interventions or other factors).
–Clear mechanisms for reporting and use of M&E results in decision-making.
–Sustainable organisational arrangements for data collection, management, analysis, and reporting.
–
Lecture 2

## Slide 13
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.2-Key design principles for project monitoring and evaluation
Project M&E design can be guided by the concept of project logic and logical framework analysis.
Implicitly or explicitly a good project design will be based on a clear and logical project strategy.
This is usually made explicit in the form of a logical hierarchy of relationships between the various project elements; progress at each level being a precondition for achievement at the next higher level.

## Slide 14
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
A logical structure for project monitoring and evaluation
Project logic | Types of indicator | Focus of M&E | Characteristics
Goal | Impact | Results monitoring | long-term widespreadimprovementinsociety
Purpose | Outcome |  | intermediateeffectsforbeneficiaries
Outputs | Output | Implementation monitoring | capitalgoods,productsandservicesproduced
Activities | Process |  | tasks undertaken to transforminputsto outputs
Inputs | Input |  | humanandmaterialresources

## Slide 15
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
  Moving from monitoring to evaluation requires the use of criteria, defines core criteria commonly used in the evaluation of development projects, and of sector and policy level interventions.

## Slide 16
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Evaluation criteria
The effect of the project on its wider environment
Impact
The appropriateness of project objectives to the problems intended to be addressed
Relevance
How the outputs contributed to the achievement of project purpose and goal(s)
Effectiveness
Whether project outputs have been achieved at reasonable cost
Efficiency
Benefits produced by the project continue to flow after external funding has ended.
Sustainability

## Slide 17
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
  2.3- The challenges of outcome and impact monitoring and evaluation
  ‘inputs’, ‘activities’ and ‘outputs’ are within the direct control of project management, ‘implementation monitoring’ and evaluation is a core management function, and achievable largely through internal record-keeping and analysis.
  Indicators of inputs, process and outputs are usually generated by project management, and/or by government and funding agency accounting and reporting requirements.

## Slide 18
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
The key points to note here are that the monitoring and evaluation of outcome and impact indicators will require considerable time and resources.
This particularly applies when ‘formal’ methods that can produce results with statistical validity are to be used, but it also applies to the use of more qualitative methods and to a focus on processes as well as outcomes and impacts.
Thus adequate human resources and expertise are essential for what is, for all practical purposes, these methodological challenges and requirements for staff with applied research skills may be beyond the capacity of the project management organisation, and the services of external specialists (consultants) will be required.

## Slide 19
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.4-The role of leading indicators
Whether ‘results monitoring’ and evaluation is carried out by project management or by specialists, information about project outcomes and impact will rarely be available to inform and improve project management during the early or mid stages of the project.
It will therefore usually be important for project managers to identify and use some ‘leading indicators’ of project performance during the early stages of implementation.

## Slide 20
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Leading indicators, sometimes also called ‘early outcome indicators’, are those that can provide an early indication of whether an expected change will occur, before project implementation is complete, and before the expected change has taken place.
This approach has also been referred to in the literature as ‘beneficiary contact monitoring’
Other leading indicators might be identified to provide early warning about the non- fulfilment of necessary external conditions

## Slide 21
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
For both leading and final indicators of outcomes and impact a degree of pragmatism may often be necessary in the choice of indicators and data collection methods, depending on project characteristics and available resources
It is also pragmatic to recognise that the practical problems of attributing causality, and the complexity of the statistical analysis involved, may mean that it is more cost- effective to rely on leading indicators such as delivery of services and beneficiary response than to attempt to measure actual impacts for many projects.

## Slide 22
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.5-Results-based monitoring and evaluation
Results-based monitoring and evaluation:
Places particular emphasis on outcomes and impact.
Emphasises that it is not sufficient simply to determine that planned outputs have been delivered on time and on budget.
Needs to build up on monitoring and evaluation systems that are initially focused on the implementation and performance of projects, but which can progress to evaluation of outcomes and impact as implementation proceeds.

## Slide 23
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
A results-based management approach should enhance public sector performance, and for which ‘inputs’, ‘activities’ and ‘outputs’ may not be fully specified in advance.
For all projects, a focus on results-based management also puts pressure on the project manager and other members of the task team to change or adapt the project if it is not demonstrating that it can achieve the desired outcomes; looking ahead at achievements, rather than inwardly and narrowly at processes.

## Slide 24
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
2.7-Contemporary evaluation challenges and responses
‘Outcome mapping’ is an approach that focuses on change processes and their outcomes.
It defines the limits of a project’s or programme’s influence, promotes strategies that fit the situation and recognises the importance of the actions and contributions of all the stakeholders involved.
M&E focuses on monitoring and reporting the changes in behaviour of the actors involved in or directly influenced by the project, with project performance assessed in terms of its contribution in making those changes.

## Slide 25
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
The logical framework sequence including pathways between different elements

## Slide 26
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
3. COMPONENTS OF MONITORING AND EVALUATION SYSTEMS
This section provides guidance on how to plan and implement a project M&E system. It reviews the main steps and approaches required and concludes with a discussion of how to create a learning environment for project implementation.

## Slide 27
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
3.1-Planning and implementing a project monitoring and evaluation system
Setting up a project M&E system involves nine steps.
These need to be considered in the planning stage and then fulfilled at project start-up and throughout project implementation.

## Slide 28
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Steps in planning a project M&E system
1. Assess the existing readiness and capacity for monitoring and evaluation
2. Establish the purpose and scope of M&E
3. Identify and agree with stakeholders the project’s outcomes and development goal(s)
4. Select key indicators and an evaluation framework
5. Set baselines and plan data collection and analysis
6. Select results targets
7. Plan monitoring, data analysis, communication and reporting
8. Plan the form and timing of critical reflection and interim evaluations
9.Plan for the necessary conditions and capacities

## Slide 29
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
Key points for each of these nine steps
(1)Assess the existing readiness and capacity for monitoring and evaluation
Review current capacity within the organisation and its partners which will be responsible for project implementation, covering: technical skills, managerial skills, existence and quality of data systems, available technology and existing budgetary provision.
Identify any barriers to M&E of the project such as a lack of political will, expertise or experience.
What other organisations such as universities, private consultants or government agencies have the capacity to provide technical assistance and/or training?

## Slide 30
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(2)Establish the purpose and scope
Why is M&E needed and how comprehensive should the system be?
What are national requirements with regard to M&E?
In particular, what should be the scope and degree of rigour of the evaluation of final project impact?
Should the M&E process be participatory?
In planning and implementing project M&E it is important to recognise the potential benefits of stakeholder participation. There can be benefits from this at all stages of the project cycle including monitoring and evaluation.

## Slide 31
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(3)Identify and agree with main stakeholders the project’s outcomes and development objective(s)
Setting a development goal and the project purpose or expected outcomes is essential in building a M&E system.
In project design the specification of outputs, activities and inputs follows from this, and the expectation that achievement of outcomes will contribute to the higher level development goal(s) provides the justification for the project.
In M&E design, indicators, baselines and targets are similarly derived from the setting of goals and outcomes.

## Slide 32
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(4)Select key indicators and an evaluation framework
Indicators are the qualitative or quantitative variables that measure project performance and achievements.
Indicators should be developed for all levels of project logic, indicators are needed to monitor progress with respect to inputs, activities, outputs, outcomes and impact, to feedback on areas of success and where improvement is required.
Each indicator initially selected for inclusion in the M&E programme needs to be carefully scrutinised and tested before acceptance. Criteria against which indicators can be tested to ensure that they are suitable for inclusion.

## Slide 33
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(5)Set baselines and plan data collection and analysis
The baseline is the first measurement of an indicator, which sets the pre- project condition against which change can be tracked and evaluated.
Baseline data must be gathered for the key indicators and this may require implementation of a baseline survey unless existing data sources are adequate.
Subsequent data gathering and repeat surveys for the implementation period of the project and beyond should then be planned.

## Slide 34
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(6)Select results targets
Following definition of outcomes, indicators and baselines, target setting is a key step in building a results-based approach.
A target is a specification of the quantity, quality, timing and location to be realised for a key indicator by a given date.
Starting from the baseline level for an indicator the desired improvement is defined taking account of planned resource provision and activities, to arrive at a performance target for that indicator.
Most targets are set annually, but some could be set quarterly or for longer periods. Targets do not have to be single numerical values and sometimes a range of achievement may be more appropriate.

## Slide 35
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(7)Plan monitoring, data analysis, communication, and reporting
‘Implementation monitoring’ tracking the inputs, activities and outputs in annual or multiyear work plans, and ‘results monitoring’ tracking achievement of outcomes and impact, are both needed.
The demands for information at each level of management need to be established, responsibilities allocated, and plans made for:
– what data to be collected and when;
– how data are collected and analysed;
–who collects and analyses data;
–who reports information, and in what form, to whom and when?

## Slide 36
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(8) Plan the form and timing of critical reflection and interim evaluations
For managers evaluation should be a continuously available mode of analysis utilised whenever evaluation results can be useful. Scheduling of events such as management team meetings can, however, be useful to ensure that analysis of progress and critical reflection takes place.
Similarly, periodic project review workshops to facilitate analysis and discussion with project partners and other stakeholders may be necessary.
Supervision requirements of governments and funding agencies may require periodic and formalised evaluations to take place.

## Slide 37
Lecture 2
Session2. DESIGN AND IMPLEMENTATION OF M&E SYSTEMS
(9)Plan for the necessary conditions and capacities
It is necessary to plan the organisational structure for M&E including whether a M&E unit specific to the project is needed.
Appropriate organisational structures for M&E should be discussed with partners and other stakeholders. Each partner’s responsibilities and information requirements should be considered.
Planning should cover: staffing levels and types, responsibilities and internal linkages, incentives and training needs, relationships with partners and stakeholders, horizontal and vertical lines of communication and authority, physical resource needs and budget.
Monitoring and ongoing evaluation should normally be the responsibility of the project managers. Impact evaluation may often require the expertise and capacity of external specialists.

## Slide 38
Lecture 2
Criteria | Description
Relevant | Indicators must be representative of the most important aspects of implementation and of the out comes and impactsintended.
Clear | I Any adjectives used to describe the qualities of anindicatorneedtobepreciselydefined.Forexample:whatismeantby‘improvedservicedelivery?’an indicator may be ‘the area of degraded land’ but whatcriteriawillbeusedtoclassifysuchland?for households what is included in ‘farm income’ and whatin‘non-farm income?’
Measurable | There must be practical ways to measure the indicator, either inquantitative or qualitative terms,that are within the capability of the monitoring organisation. It must be possible to collect,process and analyse data intime and within budget.
Criteria for selection of indicators

## Slide 39
Lecture 2
Criteria for selection of indicators
Specific | Indicators should measure specific changes,and be specific to at timeframe,location and target orother stakeholder group.
Consistent | The values of the indicators should be reliable and comparable over time when collected using the same methods
Sensitive | Indicators should be sensitive to the expected changes. It is especially important that leading indicators are capable of revealing short-term movements.
Attributable | Based on an established or probable relationship expected to cause the intended change

## Slide 40
Lecture 2