## Slide 1
Project Time Management
Lecture 7
PMG 212
www.midocean.ae
Prepared by Dr. Nael Yousry
Presented by Dr. Amira Elfekky

## Slide 2
Prepared by Dr. Nael Yousry
Project Time Management
Lecture 7
PMG 212
Presented by Dr. Amira Elfekky

## Slide 3
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 4
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 5
Scheduling
www.midocean.ae
Chapter
07
If PLANNING is an Art form based on Experience and Knowledge, then SCHEDULING is a Systematic exercise in using applied Logic.

## Slide 6
www.midocean.ae
Scheduling
Chapter
07

## Slide 7
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 8
Who is the Scheduler
www.midocean.ae
Chapter
07

## Slide 9
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 10
Attributes of Planner/Scheduler
Possess PEOPLE skills!
  Exercise humility and salesmanship
  Exercise care when recommending various approaches
  Do not alienate the managing parties
  Ease off when needed
  Emphasize his/her role is to coordinate and integrate ideas and plans into a coherent project schedule.
امتلاك المهارات الشخصية (عدم الاعتماد على البرامج الحاسوبية)
  التحلي بمهارات التواصل بين أقسام المشروع
  العناية الشديدة عند التوصية بإستخدام أساليب مختلفة
  العمل على عدم نفور الأطراف ذات الصلة
  الحد من المشكلات عند الحاجة
  تنسيق ودمج الأفكار والخطط في جدول زمني متماسك
www.midocean.ae
Chapter
07

## Slide 11
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 12
Importance of the Schedule
www.midocean.ae
Depicts يصورthe Scope of work
Improves the probability for the project team to meet its goals
Establishes overall schedule parameters
Aids in determining staffing requirements
Chapter
07

## Slide 13
Importance of the Schedule
www.midocean.ae
Resource loading basis
Identifies long lead items
Identifies the phases in the project
Chapter
07

## Slide 14
Importance of the Schedule
Standardized scheduling techniques motivates the project team to:
  Think through the entire project
  Predict a realistic project completion
  Recognize impacts of unexpected events
www.midocean.ae
Chapter
07

## Slide 15
Importance of the Schedule
Standardized scheduling techniques motivates the project team to:
  Identify claims or time extensions
  Coordinate interfaces and reduce conflicts
  Plan resource requirements and cash flow
  Serve as a record of the project’s progress
  Communication Tool
www.midocean.ae
Chapter
07

## Slide 16
  Tells you where you’ve been.
  Tells you where you are.
  But most importantly, it tells you where are you going!
Must have sufficient detail to control the project
  To much detail is cumbersome to maintain.
  Not enough detail and the analysis of the schedule is difficult.
www.midocean.ae
Importance of the Schedule
Chapter
07

## Slide 17
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 18
Scheduling Tools
P6 (Primavera)
Microsoft Project Planner (MSP)
Suretrak (Primavera)
Milestones, etc.. - Bar Chart
TILOS- Linear Scheduling
www.midocean.ae
07
Chapter

## Slide 19
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 20
Scheduling Methodology
www.midocean.ae
Chapter
07

## Slide 21
Critical Path Method
The calculation of the earliest and latest start and finish dates of activities based on their duration's and relationships to other activities
a resource-utilization algorithm for scheduling a set of project activities
Item | Price
A | 100
B | 100
C | 100
D | 100
E | 100
F | 100
Sum | 600
www.midocean.ae
Chapter
07

## Slide 22
Activities
The Basic element into which a project is subdivided for scheduling a network (CPM)
  Has a definable start and finish
  Consumes resources
  Is assignable
  Is measurable
  Is defined by a Work Package
  Is a Physical Task for Construction
www.midocean.ae
Chapter
07

## Slide 23
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 24
Scheduling Terminology: Work Package
A group or number of Engineering/Construction Deliverables that will enable Procurement or Construction to accomplish a meaningful task. WP is the lowest level of a WBS.
  All of the Data Sheets & Specifications required for a Purchase Order.
  All of the Drawings & Details necessary to Locate, Excavate, Form and Pour a Foundation
  Earthwork
  Foundation
  Cabling
www.midocean.ae
Chapter
07

## Slide 25
Scheduling Terminology:
Work Package Template
www.midocean.ae
Chapter
07

## Slide 26
Scheduling Terminology: Milestone
Is a GOAL to be achieved.
    Can be either a Start or Finish Achievement
    Is a single point in Time
    Has no duration
    Has no resources
    Has a specific and unique Definition
    It is either YES or NO
www.midocean.ae
Chapter
07

## Slide 27
Scheduling Terminology
Predecessor = An activity that must occur before another activity. A predecessor activity controls the start or finish date of its successor(s). An activity can have multiple predecessors, each with a different relationship to it.
Successor = An activity that must occur after another activity. An activity can have multiple successors, each with a different relationship to it.
www.midocean.ae
Chapter
07

## Slide 28
Scheduling Terminology
Predecessor and Successor Synonymsمرادفات
Dependencies
Prerequisites
Interface requirements
Links
Logic relationships “To” and “From”
التابعين (الاعتماديين)
المتطلبات المسبقة
متطلبات الواجهة/الربط
الروابط
العلاقات المنطقية "إلى" و "من"
www.midocean.ae
Chapter
07

## Slide 29
Agenda
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types
www.midocean.ae
07
Agenda
Chapter

## Slide 30
Relationships (Logic) – 4 Types
  Finish to Start - FS - A relationship in which the predecessor activity must Finish before its successor activity can Start.
www.midocean.ae
Chapter
07

## Slide 31
  Finish to Finish - FF - A relationship in which the Finish of a successor activity depends on the Finish of its predecessor activity.
www.midocean.ae
Relationships (Logic) – 4 Types
Chapter
07

## Slide 32
  Start to Finish - SF - A relationship in which the Start of the predecessor activity controls the Finish of a successor activity. Not used
www.midocean.ae
Relationships (Logic) – 4 Types
Chapter
07

## Slide 33
  Start to Start - SS - A relationship in which the Start of the predecessor activity controls the Start of a successor activity .
SS 0
A
B
www.midocean.ae
Relationships (Logic) – 4 Types
Chapter
07

## Slide 34
Thank You
www.midocean.ae