## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | Supplier prices increase | high | moderate | issues /delay | stock on some potential items those might be increased it prices | procurement Manager | مشروع مترو الرياض
2 | THREATS | delay worker visas | high | low | issues /delay | Relaying on a local cader of workers with previous work experience | project manager | مشروع مترو الرياض
3 | OPPORTUNITIES | discounted transprtions fee | high | high | high society coopration | cooperation with ministry of Transport and logistic services | Transportation manager | مشروع مترو الرياض
4 | OPPORTUNITIES | Reduce traffic jam and carbon emissions | high | high | high society coopration , saftey and health | Hold a wareness sessions | Transportation manager | مشروع مترو الرياض
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low