## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | traffic interception on some places | moderate | low | coopration of project | move another place | manger of project | مشروع مترو الرياض
2 | THREATS | commitment to measures from the municipality | high | low | coopration of project | stop the municipality to implement some measures | manger of project | مشروع مترو الرياض
3 | OPPORTUNITIES | reduce traffic | high | high | coopration of people | ................. | manger of project | مشروع مترو الرياض
4 | OPPORTUNITIES | strengthening the economy | high | high | coopration of people | ................... | manger of project | مشروع مترو الرياض
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low