## ورقة1
Student name |  | Dooaa Abdulgafor | Student Id | 2021206145
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | Formalin gas leakage inside the Medical laboratory | High | High | Staff injury | Stop all work and make sure to provide adequate ventilation for the laboratory the PPEs | Safety manager | King Faisal Hospital
2 | THREATS | Danger of improper storage of hazardous materials | High | High | Fire danger | Provide sufficient and appropriate space for storing hazardous materials, with a mark indicating the content of the substance, in addition to placing fire extinguishers | manager director And Safety manager | King Faisal Hospital
3 | OPPORTUNITIES | Employment Opportunities | High | Moderate | Attracting new experiences | Assigning the Human Resources Department to attract the appropriate scientific expertise | HR Manegar | King Faisal Hospital
4 | OPPORTUNITIES | Provides a high budget | High | Moderate | Providing laboratory equipment | Holding a meeting with employees, experts and officials, and communicating with companies to provide the appropriate tools | Financial management | King Faisal Hospital
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low