## Slide 1: PMG 622 Agile Project Management M
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 2: PMG 622 Agile Project Management LECTURE 01: An Introduction to Agile
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 3: Agile Manifesto / “4 Values”
We are uncovering better ways of developing software by doing it and helping others do it.
Through this work we have come to value:
That is, while there is value in the items on the right, we value the items on the left more.
Working products
Customer collaboration
Over
Over
Process and tools
Comprehensive documentation
Responding to change
Individuals and interactions
Contract negotiation
Following and plan
Over
Over

## Slide 4: The 12 principles behind the agile manifesto [1/4]
Our highest priority is to satisfy the customer through early and continuous delivery of valuable software.
Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage.
Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter
Notes: ONE
- 3.1 Characteristics of Project Life Cycles
5.2.7 Execution Practices that Help Teams Deliver Value
TWO
5.2.3 Backlog Refinement
THREE
5.2 Common Agile Practices

## Slide 5: The 12 principles behind the agile manifesto [2/4]
Business people and developers must work together daily throughout the project.
Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.
The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.
Notes: FOUR
4.2 Servant Leadership Empowers the Team
5.2.2 Backlog Preparation
5.2.3 Backlog Refinement
FIVE
4.3 Team Composition
5.1 Charter the Project and the Team
5.2.1 Retrospectives
SIX
4.3.4 Team Structures
5.2.4 Daily Standups

## Slide 6: The 12 principles behind the agile manifesto [3/4]
Working software is the primary measure of progress.
Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.
Continuous attention to technical excellence and good design enhances agility.
Notes: SEVEN
5.2.7 Execution Practices that Help Teams Deliver Value
5.2.8 How Iterations and Increments Help Delivery
Working Product
EIGHT
5.1 Charter the Project and the Team
NINE
5.2 Common Agile Practices

## Slide 7: The 12 principles behind the agile manifesto
Simplicity–the art of maximizing the amount of work not done is essential.
The best architectures, requirements, and designs emerge from self organizing teams.
At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.
Notes: TEN
5.2.2 Backlog Preparation
5.2.3 Backlog Refinement
ELEVEN
4.3 Team Composition
TWELVE
5.2.1 Retrospectives

## Slide 8: Declaration of interdependence
Increase return on investment by making continuous flow of value our focus.
Deliver reliable results by engaging customers in frequent interactions and shared ownership.
Expect uncertainty and manage for it through iterations, anticipation and adaptation.
Unleash creativity and innovation by recognizing that individuals are the ultimate source of value, and creating an environment where they can make a difference.
Boost performance through group accountability for results and shared responsibility for team effectiveness.
Improve effectiveness and reliability through situationally specific strategies, processes, and practices.

## Slide 9: TWO strategies to fulfill agile values and principles [1/2]
The first is to adopt a formal agile approach, intentionally designed and proven to achieve desired results.
  Then take time to learn and understand the agile approaches before changing or tailoring them.
  Premature and haphazard tailoring can minimize the effects of the approach and thus limit benefits.

## Slide 10: TWO strategies to fulfill agile values and principles [2/2]
The second strategy is to implement changes to project practices in a manner that fits the project context to achieve progress on a core value or principle.
  Use time boxes to create features, or specific techniques to iteratively refine features.
  Consider dividing up one large project into several releases, if that works for the specific project context.
  Implement changes that will help the project succeed— the changes do not need to be part of the organization's formal practices.
  The end goal is not to be agile for its own sake, but rather to deliver a continuous flow of value to customers and achieve better business outcomes.

## Slide 11: Approaches for managing uncertain projects
These approaches use:
  Very short feedback loops,
  Frequent adaptation of process,
  Reprioritization,
  Regularly updated plans, and
  Frequent delivery.

## Slide 12: When to apply iterative, incremental and agile approaches?
These iterative, incremental, and agile approaches work well for projects that involve:
  New or novel tools, techniques, materials, or application domains.
  Require research and development;
  Have high rates of change;
  Have unclear or unknown requirements, uncertainty, or risk; or
  Have a final goal that is hard to describe.

## Slide 13: Overcoming Uncertainty
By building a small increment and then testing and reviewing it, the team can explore uncertainty at a low cost in a short time, reduce risk, and maximize business value delivery.

## Slide 14: PMG 622 Agile Project Management LECTURE 02: LIFE CYCLE SELECTION
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 15: Types of PM LIFECYCLES
  Predictive life cycle. A more traditional approach, with the bulk of planning occurring upfront, then executing in a single pass; a sequential process.
  Iterative life cycle. An approach that allows feedback for unfinished work to improve and modify that work.
  Incremental life cycle. An approach that provides finished deliverables that the customer may be able to use immediately.
  Agile life cycle. An approach that is both iterative and incremental to refine work items and deliver frequently.

## Slide 16: Characteristics of Four Categories of Life Cycles

## Slide 17: Predictive life cycles
Take advantage of things that are known and proven.
This reduced uncertainty and complexity allows teams to segment work into a sequence of predictable groupings.

## Slide 18: Iterative life cycles
Allow feedback on partially completed or unfinished work to improve and modify that work

## Slide 19: Incremental life cycles
Provide finished deliverables that the customer may be able to use immediately

## Slide 20: Agile life cycles
Leverage both the aspects of iterative and incremental characteristics.
When teams use agile approaches, they iterate over the product to create finished deliverables.
The team gains early feedback and provides customer visibility, confidence, and control of the product.
Because the team can release earlier, the project may provide an earlier return on investment because the team delivers the highest value work first.

## Slide 21: CHARACTERISTICS OF PREDICTIVE LIFE CYCLES
Predictive life cycles expect to take advantage of high certainty around firm requirements, a stable team, and low risk
Project activities often execute in a serial manner
These projects succeed when potential changes are restricted (plans, team members, requirements)
Articulate the constraints
Serialized sequence of work
Do not typically deliver business value until the end of the
project

## Slide 22: CHARACTERISTICS OF ITERATIVE LIFE CYCLES
Iterative life cycles improve the product or result through successive prototypes or proofs of concept
Iterations help identify and reduce uncertainty in the project
Projects benefit from iterative life cycles when:
  complexity is high
  when the project incurs frequent changes
  when the scope is subject to differing stakeholders’ views of the desired final product
Notes: “We will know the requirements when we deliver a prototype that the business approves.” = MOCK UP

## Slide 23: CHARACTERISTICS OF Incremental LIFE CYCLES
Optimize work for delivering value to sponsors or customers more often than a single, final product
Delivery of smaller deliverables
Speed of delivery
Customers receive a subset of the overall solution frequently
The degree of change and variation is less important than ensuring customers get value sooner than at the end of the project.
Notes: For example, builders may want to show a finished room or floor of a building
before they continue with the remainder of the building. In that case, they may
complete a floor with fixtures, paint, and everything else intended for the
finished floor before proceeding to the next floor. The customer is able to see
and approve of the style, color, and other details, allowing adjustments to be
made before further investments of time and money are made. This reduces
potential rework and/or customer dissatisfaction.

## Slide 24: CHARACTERISTICS OF agile LIFE CYCLES
Agile life cycles are those that fulfill the principles of the Agile Manifesto
Customer satisfaction increases with early and continuous delivery of valuable products
An incremental deliverable that is functional and provides value is the primary measure of progress
Adapt to high degrees of change and deliver project value more often
Incremental delivery uncovers hidden or misunderstood requirements
Iteration-Based Agile
Flow-Based Agile
The iterative and incremental approaches provide feedback to better plan the next part of the project

## Slide 25: CHARACTERISTICS OF iteration-based agile LIFE CYCLES
The team works in iterations (time-boxes of equal duration) to deliver completed features
The team works on the most important feature, collaborating as a team to finish it
Then the team works on the next most important feature and finishes it
The team may decide to work on a few features at a time, but the team does not address all of the work for the iteration at once
Notes: (i.e., does not address all of the requirements, followed by all of the analyses, etc.).

## Slide 26: CHARACTERISTICS OF flow-based agile LIFE CYCLES
In flow-based agile, the team pulls features from the backlog based on its capacity to start work rather than on an iteration-based schedule
The team defines its workflow with columns on a task board and manages the work in progress for each column
Each feature may take a different amount of time to finish
Teams keep work-in-progress sizes small to better identify issues early and reduce rework should changes be required
Without iterations to define planning and review points, the team and business stakeholders determine the most appropriate schedule for planning, product reviews, and retrospectives
Notes: WIP

## Slide 27: PMG 622 Agile Project Management LECTURE 03: IMPLEMENTING AGILE: CREATING AN AGILE ENVIRONMENT
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 28: START WITH AN AGILE MINDSET
How can the project team act in an agile manner?
What can the team deliver quickly and obtain early feedback to benefit the next delivery cycle?
How can the team act in a transparent manner?
What work can be avoided in order to focus on high-priority items?
How can a servant-leadership approach benefit the achievement of the team's goals?
Notes: Managing a project using an agile approach requires that the project team
adopt an agile mindset. The answers to the following questions will help to
develop an implementation strategy:

## Slide 29: SERVANT LEADERSHIP
Servant leadership is the practice of leading through service to the team, by focusing on understanding and addressing the needs and development of team members in order to enable the highest possible team performance
The role of a servant leader is to facilitate the team's discovery and definition of agile.
Servant leaders practice and radiate agile
Servant leadership = facilitative skills

## Slide 30: Servant leaders approach project work in this order:
Purpose. Work with the team to define the “why” or purpose so they can engage and coalesce around the goal for the project. The entire team optimizes at the project level, not the person level.
People. Once the purpose is established, encourage the team to create an environment where everyone can succeed. Ask each team member to contribute across the project work.
Process. Do not plan on following the “perfect” agile process, but instead look for the results. When a cross-functional team delivers finished value often and reflects on the product and process, the teams are agile. It does not matter what the team calls its process

## Slide 31: servant leadership: enables project leaders to become more agile
Promoting self-awareness;
Listening;
Serving those on the team;
Helping people grow;
Coaching vs. controlling;
Promoting safety, respect, and trust; and
Promoting the energy and intelligence of others

## Slide 32: SERVANT LEADER RESPONSIBILITIES
Manage relationships to build communication and coordination within the team and across the organization
These relationships help the leaders navigate the organization to support the team
This kind of support helps to remove impediments and facilitates the team to streamline its processes
Because servant leaders understand agile and practice a specific approach to agile, they can assist in fulfilling the team's needs

## Slide 33: SERVANT LEADERS PAVE THE WAY FOR OTHERS’ CONTRIBUTION
In agile, the team manages its work process and its work product.
Servant leaders work to fulfill the needs of the teams, projects, and organization.
The servant leader focuses on paving the way for the team to do its best work.
The servant leader influences projects and encourages the organization to think differently.
Notes: Servant leaders may work with facilities for a team space, work with management to enable the team to focus on one project at a time, or work with the product owner to develop stories with the team.
Some servant leaders work with auditors to refine the processes needed in regulatory environments, and some servant leaders work with the finance department to transition the organization to incremental budgeting.

## Slide 34: examples of the responsibilities a servant leader may have:
Educate stakeholders around why and how to be agile
Support the team through mentoring, encouragement, and support.
Advocate for team members training and career development.
Help the team with technical project management activities like quantitative risk analysis.
Celebrate team successes and support and bridge building activities with external groups.
Create upward spirals of appreciation and good will for increased collaboration.

## Slide 35: PROJECT MANAGERS USE SERVANT LEADERSHIP
When working on an agile project, project managers shift from being the center to serving the team and the management.
In an agile environment, project managers are servant leaders, changing their emphasis to coaching people who want help, fostering greater collaboration on the team, and aligning stakeholder needs.
As a servant leader, project managers encourage the distribution of responsibility to the team: to those people who have the knowledge to get work done.

## Slide 36: TEAM COMPOSITION

## Slide 37: Benefits of optimizing the flow of value
People are more likely to collaborate.
Teams finish valuable work faster.
Teams waste much less time because they do not multitask and have to re-establish context.

## Slide 38: AGILE TEAMS [1/2]
Agile teams focus on rapid product development so they can obtain feedback
The most effective agile teams tend to range in size from 3 to 9
Ideally, agile teams are co-located in a team space
Team members are 100% dedicated to the teams
Agile encourages self-managing teams
Notes: * No. of communication channels = (n(n-1))/2
* Dr. Jeff Sutherland recommends 7 +/- 2 team members
Also 6 +/- 3
Agile encourages self-managing teams, where team members decide who will perform the work within the next period's defined scope
* That is because the teams collectively own the work and together have all of the necessary skills to deliver completed work

## Slide 39: AGILE TEAMS [2/2]
Agile teams thrive with servant leadership
The leaders support the teams’ approach to their work
Cross-functional agile teams produce functional product increments frequently
The teams collectively own the work and together have all of the necessary skills to deliver completed work
Notes: * No. of communication channels = (n(n-1))/2
* Dr. Jeff Sutherland recommends 7 +/- 2 team members
Also 6 +/- 3
Agile encourages self-managing teams, where team members decide who will perform the work within the next period's defined scope
* That is because the teams collectively own the work and together have all of the necessary skills to deliver completed work

## Slide 40: Attributes of Successful Agile Teams [1/2]
Attribute | Goal
Dedicated people | Increased focus and productivity Small team, fewer than ten people
Cross-functional team members | Develop and deliver often Deliver finished value as an independent team Integrate all the work activities to deliver finished work Provide feedback from inside the team and from others, such as the product owner
Colocation or ability to manage any location challenges | Better communication Improved team dynamics Knowledge sharing Reduced cost of learning Able to commit to working with each other

## Slide 41: Attributes of Successful Agile Teams [2/2]
Attribute | Goal
Mixed team of generalists and specialists | Specialists provide dedicated expertise and generalists provide flexibility of who does what Team brings their specialist capabilities and often become generalizing specialists, with a focus specialty plus breadth of experience across multiple skills
Stable work environment | Depend on each other to deliver Agreed-upon approach to the work Simplified team cost calculations (run rate) Preservation and expansion of intellectual capital

## Slide 42: AGILE ROLES
Cross-functional team members,
Product owner, and
Team facilitator.
Notes: SCRUM ARTIFICATS
  Product Backlog
  Sprint Backlog
  Increment
SCRUM ROLES
  Product Owner
  Development Team Members
  Scrum Master
SCRUM CERMONIES
  Sprint Planning.
  Daily Scrum.
  Sprint Review.
  Sprint Retrospective.

## Slide 43: Cross-functional team member
Cross-functional teams consist of team members with all the skills necessary to produce a working product.
In software development, cross-functional teams are typically comprised of designers, developers, testers, and any other required roles.
The cross-functional development teams consist of professionals who deliver potentially releasable product on a regular cadence.
Cross-functional teams are critical because they can deliver finished work in the shortest possible time, with higher quality, without external dependencies.

## Slide 44: Product owner [1/3]
The product owner is responsible for guiding the direction of the product.
Product owners rank the work based on its business value.
Product owners work with their teams daily by providing product feedback and setting direction on the next piece of functionality to be developed/delivered.

## Slide 45: Product owner [2/3]
The product owner works with stakeholders, customers, and the teams to define the product direction.
Typically, product owners have a business background and bring deep subject matter expertise to the decisions.
Sometimes, the product owner requests help from people with deep domain expertise, such as architects, or deep customer expertise, such as product managers.
Product owners need training on how to organize and manage the flow of work through the team.

## Slide 46: Product owner [3/3]
In agile, the product owners create the backlog for and with the team.
The backlog helps the teams see how to deliver the highest value without creating waste.
A critical success factor for agile teams is strong product ownership.
Without attention to the highest value for the customer, the agile team may create features that are not appreciated, or otherwise insufficiently valuable, therefore wasting effort.
*That means the work is small, often small enough to be described on one index card.

## Slide 47: Team facilitator
A servant leader.
This role may be called a project manager, scrum master, project team lead, team coach, or team facilitator.
People need time to build their servant leadership skills of facilitation, coaching, and impediment removal.
Initially, many organizations invite external agile coaches to help them when their internal coaching capability is not yet fully developed.
External coaches have the advantage of experience, but the disadvantage of weak relationships in the client organization.
Internal coaches, on the other hand, have strong relationships in their organization, but may lack the breadth of experience that would make them highly effective.

## Slide 48: PMG 622 Agile Project Management LECTURE 04: IMPLEMENTING AGILE: DELIVERING IN AN AGILE ENVIRONMENT [Part 1 of 2]
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 49: CHARTER THE PROJECT AND THE TEAM
Project Charter
Team Charter

## Slide 50: PROJECT CHARTER
Why this project matters
Where the team is headed
What the project objective is
The WHY
The HOW
The WHAT
Why are we doing this project? This is the project vision.
Who benefits and how? This may be part of the project vision and/or project purpose.
What does done mean for the project? These are the project's release criteria.
How are we going to work together? This explains the intended flow of work.
Notes: A servant leader may facilitate the chartering process

## Slide 51: TEAM CHARTER
Team norms
Understanding of how to work together
Teams do not need a formal process for chartering as long as the teams understand how to work together.
Some teams benefit from a team chartering process.
  Team values, such as sustainable pace and core hours;
  Working agreements, such as what “ready” means so the team can take in work; what “done” means so the team can judge completeness consistently; respecting the time-box; or the use of work-in-process limits;
  Ground rules, such as one person talking in a meeting; and
  Group norms, such as how the team treats meeting times.
Notes: The servant leader together with the team may decide to address other behaviors.
Remember that the team's social contract—its team charter—is how the team members interact with each other. The goal of the team charter is to create an agile environment in which team members can work to the best of their ability as a team.

## Slide 52: RETROSPECTIVES [1/2]
The single most important practice is the retrospective because it allows the team to learn about, improve, and adapt its process
Retrospectives help the team learn from its previous work on the product and its process
One of the principles behind the Agile Manifesto is: “At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.”
Teams benefit from allocating enough time to learn, either from an interim retrospective or an end-of-the-project retrospective
Notes: The HOW
Lessons Learnt
Continuous Improvement

## Slide 53: RETROSPECTIVES [2/2]
Teams need to learn about their work product and work process.
First and foremost, a retrospective is not about blame;
The retrospective is about looking at the qualitative (people's feelings) and
quantitative (measurements) data, then using that data to find root causes, designing countermeasures, and developing action plans.
The project team may end up with many action items to remove impediments
A facilitator from the team leads them through an activity to rank the importance of each improvement item.
Once the improvement items are ranked by the team, the team chooses the appropriate number to work on for the next iteration (or adds work to the flow if flow-based).
Notes: Acronyms and Definitions (glossary at the end of the book)

## Slide 54: Team members may decide to retrospect at these key times:
Many teams use iterations—especially 2-week iterations—because the iteration prompts a demonstration and a retrospective at the end
  When the team completes a release or ships something. It does not have to be a monumental increment. It can be any release, no matter how small.
  When more than a few weeks have passed since the previous retrospective.
  When the team appears to be stuck and completed work is not flowing through the team.
  When the team reaches any other milestone.

## Slide 55: BACKLOG PREPARATION
The backlog is the ordered list of all the work, presented in story form, for a team.
There is no need to create all of the stories for the entire project before the work starts—only enough to understand the first release in broad brushstrokes and then sufficient items for the next iteration.
Product owners might produce a product roadmap to show the anticipated sequence of deliverables over time. The product owner re-plans the roadmap based on what the team produces.
Notes: Index cards or sticky notes
Rolling Wave

## Slide 56: DAILY STANDUPS
Teams use standups to micro-commit to each other, uncover problems, and ensure the work flows smoothly through the team.
Time-box the standup to no longer than 15 minutes. The team “walks” the Kanban or task board in some way, and anyone from the team can facilitate the standup.

## Slide 57: daily stand-up questions
iteration-based agile (TIME-BOXED) SCRUM | flow-based agile (INCREMENT) KANBAN
What did I complete since the last standup? | What do we need to do to advance this piece of work?
What am I planning to complete between now and the next standup? | Is anyone working on anything that is not on the board?
What are my impediments (or risks or problems)? | What do we need to finish as a team?
 | Are there any bottlenecks or blockers to the flow of work?

## Slide 58: DEMONSTRATIONS/REVIEWS
As the team completes the features usually in the form of user stories, the team periodically demonstrates the working product.
The product owner sees the demonstration and accepts or declines stories.
In iteration-based agile, the team demonstrates all completed work items at the end of the iteration.
In flow-based agile, the team demonstrates completed work when it is time to do so, usually when enough features have accumulated into a set that is coherent.

## Slide 59: PMG 622 Agile Project Management LECTURE 05: IMPLEMENTING AGILE: DELIVERING IN AN AGILE ENVIRONMENT [Part 2 of 2]
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 60: Agile Pain Points and Troubleshooting Possibilities [1/8]
Pain Point | Troubleshooting Possibilities
Unclear purpose or mission for the team | Agile chartering for purpose–vision, mission, and mission tests
Unclear working agreements for the team | Agile chartering for alignment–values, principles, and working agreements
Unclear team context | Agile chartering for context–boundaries, committed assets, and prospective analysis
Notes: Agile approaches were born out of the need to solve issues associated with
high rates of change, uncertainty, and complexity on projects. Due to these
origins, they contain a variety of tools and techniques for dealing with issues that
present problems in predictive approaches. Refer to

## Slide 61: Agile Pain Points and Troubleshooting Possibilities [2/8]
Pain Point | Troubleshooting Possibilities
Unclear requirements | Help sponsors and stakeholders craft a product vision. Consider building a product roadmap using specification by example, user story mapping, and impact mapping. Bring the team and product owner together to clarify the expectations and value of a requirement. Progressively decompose roadmap into backlog of smaller, concrete requirements.
Poor user experience | User experience design practices included in the development team involve users early and often.
Notes: Agile approaches were born out of the need to solve issues associated with
high rates of change, uncertainty, and complexity on projects. Due to these
origins, they contain a variety of tools and techniques for dealing with issues that
present problems in predictive approaches. Refer to

## Slide 62: Agile Pain Points and Troubleshooting Possibilities [3/8]
Pain Point | Troubleshooting Possibilities
Inaccurate estimation | Reduce story size by splitting stories. Use relative estimation with the entire team to estimate. Consider agile modeling or spiking to understand what the story is.
Unclear work assignments or work progress | Help the team learn that they self-manage their work. Consider kanban boards to see the flow of work. Consider a daily standup to walk the board and see what work is where.

## Slide 63: Agile Pain Points and Troubleshooting Possibilities [4/8]
Pain Point | Troubleshooting Possibilities
Team struggles with obstacles | A servant leader can help clear these obstacles. If the team doesn't know the options they have, consider a coach. Sometimes, the team needs to escalate stories the team or servant leader has not been able to remove.
Work delays/overruns due to Insufficiently refined product backlog items | Product owner and team workshop stories together. Create a definition of ready for the stories. Consider splitting stories to use smaller stories
Defects | Consider the technical practices that work for the environment. Some possibilities are: pair work, collective product ownership, pervasive testing (test-driven and automated testing approaches) and a robust definition of done.

## Slide 64: Agile Pain Points and Troubleshooting Possibilities [5/8]
Pain Point | Troubleshooting Possibilities
Work is not complete | Team defines definition of done for stories including acceptance criteria. Also add release criteria for projects.
Technical debt (degraded code quality) | Refactoring, agile modeling, pervasive testing, automated code quality analysis, definition of Done
Slow or no improvement in the teamwork process | Capture no more than three items to improve at each retrospective. Ask the servant leader to help the team learn how to integrate those items.

## Slide 65: Agile Pain Points and Troubleshooting Possibilities [6/8]
Pain Point | Troubleshooting Possibilities
Too much product complexity | For software and non-software encourage the team always to be thinking “What is the simplest thing that would work?” and apply the agile principle of “Simplicity--the art of maximizing the amount of work not done”. These help reduce complexity.
Too much upfront work leading to rework | Instead of much upfront work, consider team spikes to learn. In addition, measure the WIP during the beginning of the project and see what the team's options are to deliver value instead of designs. Shorten iterations and create a robust definition of done.

## Slide 66: Agile Pain Points and Troubleshooting Possibilities [7/8]
Pain Point | Troubleshooting Possibilities
False starts, wasted efforts | Ask the product owner to become an integral part of the team.
Inefficiently ordered product backlog items | Rank with value including cost of delay divided by duration and other value models
Rush/wait uneven flow of work | Plan to the team's capacity and not more. Ask people to stop multitasking and be dedicated to one team. Ask the team to work as pairs, a swarm, or mob to even out the capabilities across the entire team.

## Slide 67: Agile Pain Points and Troubleshooting Possibilities [8/8]
Pain Point | Troubleshooting Possibilities
Impossible stakeholder demands | Servant leadership to work with this stakeholder (and possibly product owner).
Unexpected or unforeseen delays | Ask the team to check in more often, use Kanban boards to see the flow of work and work in progress limits to understand the impact of the demands on the team or product. Also track impediments and impediment removal on an impediment board.
Siloed teams, instead of cross-functional teams | Ask the people who are part of projects to selforganize as cross-functional teams. Use servant leadership skills to help the managers understand why agile needs cross-functional teams.

## Slide 68: Velocity,
The sum of the story point sizes for the features actually completed in this iteration, allows the team to plan its next capacity more accurately by looking at its historical performance.

## Slide 69: Flow-based agile teams measurements:
Lead time (the total time it takes to deliver an item, measured from the time it is added to the board to the moment it is completed)
Cycle time (the time required to process an item)
Response time (the time that an item waits until work starts)
Teams measure cycle time to see bottlenecks and delays, not necessarily inside the team.

## Slide 70: The downside of relative estimation
There is no way to compare teams or add velocity across teams