## Slide 1
Prepared by Dr. Amira Elfekky
Project Time Management
Lecture 9
PMG 212
مقرر: إداره وقت المشروع

## Slide 2
Top Project Management Cases
Case study
Acceleration and Schedule Compression
Why Schedule Matters
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression vs. Crash
Schedule Compression Techniques
Agenda

## Slide 3
Top Project Management Cases
Case study
Acceleration and Schedule Compression
Why Schedule Matters
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression vs. Crash
Schedule Compression Techniques
Agenda

## Slide 4
AstraZeneca During Covid 19
AstraZeneca was under pressure during the pandemic to develop and distribute the COVID-19 vaccine as quickly as possible. The company needed to work in collaboration with Oxford University for the research and the clinical trials.
AstraZeneca created an effective project management infrastructure to face challenges like establishing an internal government contracting organization, finding personnel for vaccine development, and amping up the manufacturing facility.
Top Project Management Cases
09
Chapter

## Slide 5
Saudi Aramco
This oil company in Saudi was managing two ambitious oil and gas programs called Marjan and Zuluf. The biggest challenge was to manage multiple contractors working simultaneously on the congested oil fields. Their project team tackled this challenge by simplifying construction, using contracting strategies and marine management techniques.
Top Project Management Cases
09
Chapter

## Slide 6
Apple iPhone
The project of developing and launching Apple’s iPhone is one of the most important ones in history. The company spent $150 million on this project, which turned out to be its best investment. The main challenges in managing this project were hiring the best talent, maintaining high quality, and keeping the project a secret despite so many people working on it.
Top Project Management Cases
09
Chapter

## Slide 7
Healthcare.gov
It is an example of the consequences of poor project management. Due to a lack of proper planning and coordination, the website could only register six users out of 4 million on its launch day.
Top Project Management Cases
09
Chapter

## Slide 8
Top Project Management Cases
Case study
Acceleration and Schedule Compression
Why Schedule Matters
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression vs. Crash
Schedule Compression Techniques
Agenda

## Slide 9
Case study
Road Network
A
B
C
D
1
1
3
2
1
3
2
4
3
2
3
2
1
09
Chapter

## Slide 10
Case study – Create WBS
09
Chapter

## Slide 11
Case study – Create WBS
Click
09
Chapter

## Slide 12
Case study – Create WBS
09
Chapter

## Slide 13
Case study – Create activity code
Activity | Code
Excavation | EX
Replacement | RE
Ferma Layer | FR
Base Layer | BA
Prime Coat | PR
Layer Bond | LB
Tack Coat | TA
Asphalt Layer | AS
Curbs | CU
Sign Traffic | ST
Draw Axis | DR
Pavement Layer | PV
09
Chapter

## Slide 14
Case study – Create activity
09
Chapter

## Slide 15
Case study – Create activity
09
Chapter

## Slide 16
Case study – Create activity
09
Chapter

## Slide 17
Case study – Scheduling
09
Chapter

## Slide 18
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 19
Project duration versus cost
09
Chapter

## Slide 20
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 21
Construction projects require contractual delivery dates for control and accountability
“Time is of the essence” highlights economic and operational importance
Delays impact revenue, overhead, financing, and stakeholder commitments
Acceleration = adding resources/hours to reduce duration
Schedule compression = completing the project earlier with optimal cost balance
Acceleration & Schedule Compression – Overview
09
Chapter

## Slide 22
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 23
Acceleration = adding labor, shifts, overtime, or resources
Must focus on critical path tasks to impact overall duration
Accelerating noncritical tasks has limited benefit
Shortening schedule typically increases direct costs
Requires detailed analysis of remaining duration and resources
Acceleration – Definition & Key Principles
09
Chapter

## Slide 24
Acceleration
Delivering on time or ahead of schedule is important for all parties, from subcontractors all the way up to the owner.
Finishing within or under budget is another important goal.
The real achievement, however, is doing both simultaneously. Unfortunately, this may not always be possible.
09
Chapter

## Slide 25
Acceleration
At the point where an accelerated pace of the work is diagnosed as the cure
for delay, the project manager may have to make the decision to spend money.
Acceleration is defined as the addition of resources or work hours to a task
or project.
Acceleration results in schedule compression or reducing the duration of the task or shortening the entire project without diminishing the scope of the
project.
09
Chapter

## Slide 26
Acceleration
The acceleration must be applied to the critical path or a critical task.
To accelerate a noncritical task rarely benefits the schedule.
There are three different types of acceleration that the average project may potentially encounter.
Acceleration is issued in the form of written direction from the owner to the contractor and can be classified in three categories: actual, constructive, and forced.
09
Chapter

## Slide 27
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 28
Three main types:
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Can occur between owner–contractor or contractor–subcontractor
May be compensable or non-compensable
Requires careful contractual and financial evaluation
Types of Acceleration
09
Chapter

## Slide 29
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 30
Actual Acceleration
Actual acceleration is the directive to complete the project ahead of the accepted or contractual schedule.
This directive comes from the owner to the contractor through the architect, and is then passed on to the subcontractors.
09
Chapter

## Slide 31
Owner directs early completion via formal change order
Costs are compensable
Requires modification of Substantial Completion date
Typically involves overtime, second shifts, weekend work
Requires precise calculation (no second chance after approval)
Actual Acceleration
09
Chapter

## Slide 32
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 33
Constructive Acceleration
Constructive acceleration occurs when the contractor requests an extension of time and is denied.
If the delay that resulted in the request for an extension of time is an excusable delay, the extension should be granted.
09
Chapter

## Slide 34
Occurs when:
There is an excusable delay
Contractor requests time extension
Extension is denied
Contractor is required to meet original completion date
Additional costs are incurred
➡ May result in a valid claim for compensation
Constructive Acceleration
09
Chapter

## Slide 35
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 36
Forced Acceleration
There is also a need for acceleration when delay occurs as a result of nonperformance.
This type of acceleration is sometimes referred to as forced acceleration.
This occurs frequently when a subcontractor on the critical path is falling behind.
While this is not acceleration in the truest sense of the definition, it does require an increase in production.
09
Chapter

## Slide 37
Caused by subcontractor nonperformance
Requires increased production to recover delay
Typically non-compensable
May involve workforce supplementation
Must be handled carefully to avoid contractual disputes
Forced Acceleration
09
Chapter

## Slide 38
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 39
Schedule Compression
The decision to accelerate work and incur costs must have a tangible benefit to the project.
Schedule compression is not always about the shortest duration of the task.
It is more about the balance of getting the shortest duration for the least
cost.
09
Chapter

## Slide 40
Schedule Compression
Schedule compression is generally defined as modifying the plan and/or schedule to complete critical tasks or the project early.
Schedule compression is the resequencing or rescheduling of tasks with minimal or no cost impact.
09
Chapter

## Slide 41
Examples include:
Timely review of submittals
Improved material procurement
Adding shifts or overtime
Off-site fabrication
Resequencing tasks to utilize float
Incentives for performance
Application of new technology
Schedule Compression Techniques
09
Chapter

## Slide 42
Top Project Management Cases
Case study
Project duration versus cost
Acceleration and Schedule Compression
Acceleration – Definition & Key Principles
Types of Acceleration
Actual Acceleration
Constructive Acceleration
Forced Acceleration
Schedule Compression Techniques
Time–Cost Trade-Off Analysis
Agenda

## Slide 43
Used to determine which tasks to accelerate.
Key Concepts:
Normal Duration vs. Crash Duration
Normal Cost vs. Crash Cost
Focus on critical path tasks
Select tasks with lowest cost per day saved first
Time–Cost Trade-Off Analysis
09
Chapter

## Slide 44
Thank You