## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | delay on orange lane due to it’s length and passing through various overcrowded urbans | high | high | delay on schedule | preparing Necessary permits for crashing - multi-phases | who roject manager , public relations manager | مشروع مترو الرياض
2 | THREATS | lake of talented / experienced planning and excution teams | moderate | moderate | design conflict | contracting with international (matter expert) consulting firm | project manager | مشروع مترو الرياض
3 | OPPORTUNITIES | local availability of core materials. | high | high | strategic cooperation with sourcing supplier | issuing full quantity purchasing order | procurement manager , public relations manager | مشروع مترو الرياض
4 | OPPORTUNITIES | 50% of yellow lane area is undergo by another govermental project which will ends within nex 6 months | high | high | completion of design phase for mentioned area. | cooperating with governmental project administration to start execution on that area saving time and effort of issuing the required permits and cost of mobilization. | public relations manager, project manager | مشروع مترو الرياض
5 | THREATS | Delay of glass houses deliverables may couse failure of oil rigging | high | moderate | if Schedual performance indicator is less than 90% | managing excution closeley and maximize recources on critical path activities. | Project Mnager, Construction Manager | مشروع مرآة للطاقة الشمسية
6 | THREATS | the project could run out of funding of cashflow could manged poorly cousing progress issues. | moderate | low | lack of cashflow planning. | Multiple funding sources shall be identified early with focus on cashflow. A cashflow forcast for both pre- and post-construction stages will be created and 30-days payment pushed to the supply chain. | Project Mnager | مشروع مرآة للطاقة الشمسية
7 | OPPORTUNITIES | Using extra supplied power to supply nearby houses | moderate | moderate | power supplied to oil rigging is suffecent | preparing the neccessarly arrangment to use surplus power at homes | Project Mnager | مشروع مرآة للطاقة الشمسية
8 | OPPORTUNITIES | using water vapour on saline water treatment | moderate | high | Complition of the first generation station | preparing the necessary arrangement to use existed heater for water treatment | Project Mnager, procurment manager | مشروع مرآة للطاقة الشمسية
9 | THREATS | Materials delivery is delayed | moderate | low | Excution is in hold | Managing supplier closely and finding alternative supplier standing by | Project managed | مشروع الهايبر لوب
10 | THREATS | No control over staff priorities | moderate | low | Delay on planned date of aquiring recources | The Project Sponsor will brief senior management on the importance of the project. Soft book resources as early as possible and then communicate final booking dates, after the scheduling workshops. Identify back ups for each human resource on the project. | Project Sponsor ,Project manager | مشروع الهايبر لوب
11 | OPPORTUNITIES | availability of power source in 20 % of project area | low | high | starting excution phase | communicating with rlated authorities | public relations manager, project manager | مشروع الهايبر لوب
12 | OPPORTUNITIES | saving time could bring fainancial benefits in reducing funding | moderate | moderate | Delay on rushed schedual | access how much money there is to be saved per month on funding by finishing early. Offering bonus to the contractor per month to finish the target. | Project managed | مشروع الهايبر لوب
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low