High-Level Plan

| Phase | Activity | Timeline |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 |
| 1 | Chapter 3: Methodology |  |  |  |  |  |  |  |  |  |  |
| 2 | Data Preparation & Model Development |  |  |  |  |  |  |  |  |  |  |
| 3 | Model Evaluation & Optimization |  |  |  |  |  |  |  |  |  |  |
| 4 | Chapter 4: Experimental Results and Discussion |  |  |  |  |  |  |  |  |  |  |
| 5 | Chapter 5: Conclusion and Future Work |  |  |  |  |  |  |  |  |  |  |
| 6 | Writing Optimization & Finalization |  |  |  |  |  |  |  |  |  |  |
| 7 | Final Presentation |  |  |  |  |  |  |  |  |  |  |

Detailed Plan

| Phase | Input | Description | Activities to be Done | Expected Results (Official Output) | Timeline | Expected Challenges | Challenges Mitigation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Chapter 3: Methodology | UCI Thyroid Dataset, research objectives, selected ML models | Define dataset structure, preprocessing, model selection, and justify dataset choice | - Explore dataset- Perform cleaning & preprocessing- Select key features (TSH, T3, T4)- Justify dataset selection (benchmarking & reproducibility)- Define validation strategy (train/test split)- Document methodology- Specify tools (Python, Scikit-learn) | Completed Chapter 3: Methodology (dataset justification, preprocessing, model design, validation approach, tools) | WK1–WK2 | Data quality issues or missing values | Apply preprocessing and remove inconsistent records |
| Data Preparation & Model Development | Clean dataset, selected features, ML algorithms (DT, RF), tools (Python) | Develop ML models for thyroid classification using structured data | - Split dataset (e.g., 80/20)- Train Decision Tree- Train Random Forest- Generate predictions- Save model outputs | Trained ML models with validated prediction outputs | WK2–WK5 | Model instability or low performance | Use simple models and avoid over-complex tuning |
| Model Evaluation & Optimization | Model outputs, actual labels | Evaluate performance, visualize results, and select best model | - Calculate Accuracy, Precision, Recall, F1-score- Compare models- Generate visualizations (confusion matrix, charts)- Select best-performing model | Final Model Evaluation Report including metrics, visualizations, and selected model | WK5–WK6 | Misinterpretation of evaluation metrics | Focus on key metrics (Accuracy, F1-score) and clear explanation |
| Chapter 4: Experimental Results and Discussion | Evaluation results, literature review (Chapter 2), conceptual framework | Analyze results, relate findings to literature, and present hybrid framework concept | - Present results (tables, charts)- Interpret findings- Compare with literature- Explain model behavior- Present conceptual hybrid framework (symptom + lab integration) | Completed Chapter 4: Results and Discussion including interpretation and framework explanation | WK5–WK7 | Weak linkage to literature | Use direct comparison with cited studies |
| Chapter 5: Conclusion and Future Work | Final results, research objectives | Summarize findings, highlight contributions, define limitations and future work | - Summarize findings- Highlight contributions- Discuss limitations (dataset, lack of symptoms)- Propose future work (hybrid system implementation) | Completed Chapter 5: Conclusion and Future Work including limitations and contributions | WK6–WK8 | Weak contribution or repetition | Focus on insights, novelty, and practical value |
| Writing Optimization & Finalization | Complete thesis document | Improve clarity, structure, and consistency; finalize document | - Edit and refine writing- Ensure formatting consistency- Cross-check references and sections- Perform plagiarism check- Final review | Final Thesis Document Ready for Submission | WK8–WK9 | Time constraints or formatting issues | Prioritize clarity over perfection; use standard formatting |
| Final Presentation | Final thesis, key results | Prepare and practice for thesis defense | - Prepare presentation slides- Summarize key sections- Practice defense- Prepare answers for expected questions | Final Presentation Slides and Defense Readiness | WK10 | Nervousness or unexpected questions | Practice and prepare standard answers |