## Slide 1
PMG 312
S3 - Developing project scope.
Ch.6 - Defining a project
Project Management Technologies
Prepared by Lecturer Waseem Tabbaa
Chapter 6

## Slide 2
Introduction
Chapter
06
Section III: Developing project scope
Chapter 6 Defining a project .....................................................................77
Scope planning and definition....................................................................... 77
Staffing and team management..................................................................... 79
Scope statement........................................................................................... 79
Project and product objectives......................................................... 80
Product or service requirements and characteristics ................... 80
Product acceptance criteria .............................................................. 81
Project boundaries............................................................................. 81
Project requirements and deliverables ........................................... 81
Project constraints ............................................................................. 82
Project assumptions .......................................................................... 82
Project organization/team assessment........................................... 83
Defined risks ...................................................................................... 83
Milestones........................................................................................... 84
Work definition .................................................................................. 84
Cost estimate ...................................................................................... 85
Project configuration management requirements ........................ 85
Approval requirements..................................................................... 86
Summary........................................................................................................... 86
References ......................................................................................................... 87

## Slide 3
Developing project scope
Chapter
06
This section of the book focuses on translating the original project goal into a work unit-oriented structure with initial time and cost estimates.
Scope definition is considered as the key initiation step for a project and one that is necessary for future success.
The chapters in this section have the following learning objectives:
  Develop the scope management plan as part of the scope planning process.
  Develop the scope statement as part of the scope definition process
  Identify, analyze, refine, and document project requirements, assumptions, and constraints to produce a technical project and product scope definition.
  Development of a deliverables-oriented WBS created from the initial project charter, scope statement, and other project specification documents. From this definition, step technical work units are defined and will be used to facilitate detailed project planning, which is then used in the executing, monitoring and controlling, and closing processes.
  Estimating tools and techniques are described to show how development of project work unit specifications leads to a total project budget.
  Introduce the relationship of scope, time, cost, and resources into the overall management equation.

## Slide 4
Developing project scope
Chapter
06
There are many ways in which project management mechanics could be presented.
In this book, Sections III and IV have been defined as representing the core mechanics that every PM should follow and generally in the sequence described.
Section III segments the process for defining project scope and techniques for estimating the defined work.
Section IV will expand that into measurable output for time and cost.
Scope is considered to be the prerequisite event because it is difficult to execute a project if there is no clear definition of its goals and work requirement.
Many projects fail because this step is not done well.
The creation of the scope management plan and scope statement establishes the foundation for the WBS development.
The main artifact to support this goal is the WBS which is considered to be one of the most important project artifacts.
Much of the following text uses this definition to bridge into various other management processes.
Figure III.1 illustrates the process linkage between the three initial holy trilogy knowledge areas.

## Slide 5
Developing project scope
Chapter
06
The sequential flow of project plan development is illustrated in Figure III.1 and is important in that a formal scope definition provides the foundation for schedule development and the resulting schedule then becomes the base artifact for project cost and budget definition.
Many projects start off with these assumptions reversed. Schedule and cost can in fact be hard constraints, but the sequence defined here is that the flow of plan development should start with scope and let that dictate cost and schedule.
If the three components do not match internal constraints, the tweaking process should then work iteratively until a viable solution is found.
What exactly is this variable, it is called project scope? Basically, it is a formal definition of work required to produce the defined project goal.
This process defines the deliverables, work processes, and other information relevant to that result.
Scope definition is considered to be the first element of three core project management attributes called the holy trilogy.
From the scope specification, project time and cost are derived.
Even though there is a lot more to project planning than these base elements, they are the most visible plan output parameters and frankly represent more than many organizations do for project planning.

## Slide 6
Developing project scope
Chapter
06
Emulating real-world practices is not necessarily a route to success.
In some cases, project failure is not one of deficient planning, but getting the organizational participants to follow the plan.
Just recognize that a good plan is not the only condition for success.
It is a road map, but there is always unexpected environmental roadblocks found along the way.
Think of the planning process as a pathway to get from point A to point B.
Each road increment is a work unit that consumes time and resources that when added together constitutes the total trip.
Any change in this pathway has the potential to extend the estimates.
The reader must recognize that many real-world project managers will take many shortcuts in developing a plan.
Personal experience suggests that few projects follow the full management rigor as outlined in this book.
Nevertheless, each management shortcut brings with it certain negatives that may derail the resulting value of the final project.
One must know what the ideal case is and what risks are inherent in any shortcuts before selecting that route.

## Slide 7
Defining a project
Chapter
06
The basic roles for a charter were also discussed which consisted of formally giving delegation of authority to the PM and formally displaying management approval for the project.
The objective of this chapter is to address the next step in the launch process which is to develop the scope planning.
This that yields a scope management plan, and the scope definition results in an updated scope management plan, scope statement and requested changes to the project scope (PMI 2008).
PMI (2008) describes a scope management plan as how the project scope will be defined, developed, and verified.
It will also describe how the WBS will be created and defined.
Therefore, the scope management plan provides guidance on how the project scope will be managed and controlled by the PM and the team.
It is contained within or a subsidiary of the project management plan.

## Slide 8
Defining a project
Chapter
06
A project scope statement contains a description of the project scope which consists of information such as the deliverables, assumptions, constraints, and a description of the work that is to be accomplished by the project.
The scope statement for the project is documented, so it will be the basis for making future project decisions and for confirming or developing a common understanding of project scope among the stakeholders.
The creation of the scope management plan and scope statement establishes the foundation for the WBS development.
Successful projects are just as much about managing relationships as they are about managing change, so the PM must be vigilant in controlling the project outcome (Bourne and Walker 2005).
There is a management concept that says you cannot control what has not been defined, and scope definition is the important beginning step for project definition.
Our primary goal now is to begin our journey through planning and defining project scope.

## Slide 9
Scope planning and definition
Chapter
06
As discussed previously, the scope planning process yields a scope management plan, and the scope definition results in an updated scope management plan, scope statement and requested changes to the project scope (PMI 2008).
The input into scope planning is organizational factors such as an organizational culture, project charter, preliminary scope
statement, project management plan, and organizational process assets defined by PMI (2008) as information, policies, or procedures external to a project.
The process in scope planning used by organizations to produce the output, scope management plan, is templates and expert judgment.
The scope definition input is similar to the scope planning input as it not only has organizational process assets, project charter, preliminary scope statement, but also has the project scope management plan and approved project scope change requests.

## Slide 10
Scope planning and definition
Chapter
06
The process used to produce the outputs of the project scope statement, requested changes, and updated scope management plan consists of the methods and techniques used to translate project objectives into project deliverables, expert judgment, and management of stakeholder’s needs, wants, and expectations.
A scope statement typically is a text document used to develop and confirm a common understanding of the project scope.
It should include project justification, brief description of the project’s deliverables, and summary of all project deliverables and a statement of what determines project success.
The scope statement is a first translation of the vague charter language into more specific technical language.
Just as every organization may have a slightly different way of approaching the official launch of a project, an organization also has different approaches to scope planning and definition.

## Slide 11
Scope planning and definition
Chapter
06
However, the proper outcome is scope statement used to drive the subsequent scope planning and the scope management plan for scope definition.
The difference is that the scope management plan is procedural input into development of the very detailed scope statement.
The scope management plan will either already contain the level of detail that is found in a scope statement or will be broader leaving the details to be found in the scope statement.
Therefore, the discussion of this chapter revolves around the development of the detailed scope statement since this will discuss all of the necessary scope input needed prior to the next chapter that focuses on development of the WBS.

## Slide 12
Scope planning and definition
Chapter
06
Identification of the team members is an important part of the launch process as the team will then assist the PM in creation of the scope statement as teamwork is a vital ingredient for success for the project team (Little 2011; Redesigning project management 2002; Swan and Khalfan 2007).
Assembling the project team requires the right mix of individuals and composition of skills that will successfully be able to accomplish the project goals (Maddalena 2012).
Unclear objectives, unrealistic deadlines, and unclear management roles and lines of authority are weaknesses in project management (Redesigning project management 2002). As discussed in Chapter 5, if any part of the project is being outsourced, the role of the outsourced tasks must be carefully and clearly defined.
A clearly defined line of authority to include an accountability framework must be established (Maddalena 2012).
Clearly defined goals are the first step prior to assigning individuals to different tasks that lead to each of the defined goals.

## Slide 13
Staffing and team management
Chapter
06
Chapter 7 outlines more specifics in WBS creation and Chapter 23 provides additional team management tools that a PM can utilize in defining role and responsibility-type matrices as the way to establish an accountability framework to be certain that the entire team understands overlapping and individual project responsibilities.
The tools in Chapter 23 will also help one to provide expectations to all team members related to communication internal and external to the project team.
Examples of these are documents that identify which tasks belong to which individuals and they also include detailed information of individual responsibilities.
Time planning tools will also emerge, and they will define the amount of time needed to conduct each project task and specific work assignments for the team members.
These tools collectively communicate how project team members are accountable for achieving the project goals and related deliverables.
Organizational charts such as those discussed in Chapter 3 also provide official and therefore formal lines of authority for those internal and external to the team.
All these supporting tool's aid in the task organizational processes required to produce not only the scope definition but are also used through the rest of the life cycle as well.

## Slide 14
Scope statement
Chapter
06
The scope statement can be highly detailed or broad depending on the organization and the needs of the project (PMI 2008).
The team guided by the PM’s leadership establishes the project’s objectives, deliverables, requirements, and/or specifications as well as criteria for success in terms of realistic, clear, and measurable objectives. Also, many of these steps can occur in parallel.
It is important to limit the scope to include only the project-related (versus adding nonprojected scope) specific objectives, deliverables, requirements, specifications as well as criteria for success because including additional requests without going through the change control process will spiral the project out of control and the result unmanageable.
A scope statement created by the team can assist in making the team cohesive in developing a shared blueprint for how the team operates (Peled 2000).
Developing this with input from stakeholders also facilitates buy-in from that segment about the project’s need for existence and ultimate purpose.
A sample template for the scope statement is displayed in Table 6.1.

## Slide 15
Project and product objectives
Chapter
06
Objectives are defined as something that is to be accomplished by the project which can be in the form of a tangible product or possibly less tangible project items such as status reports, quality control documents, and other items related to running the project.
A project objective would be items such as delivering the defined outputs on-time, on-budget, and within scope.
A product objective would be to make sure the software is user-friendly, technical specifications met, and so on.
A clear statement of objectives is important since this drives the subsequent WBS and control process.
There will obviously be changes requested during the project life cycle.
It is important to manage this process as undue volume of these will doom a project.
Chapter 18 will describe that aspect of the life cycle.

## Slide 16
Product or service requirements and characteristics
Chapter
06
After describing stakeholders’ needs, wants, and expectations, the team must translate that into the work requirements necessary to produce that output.
Requirements need to be listed in priority order as typically there will not be enough resources or time to deliver every item.
Once the requirements have been identified in terms of very concise statements that no two individuals would interpret differently, the requirements should then be communicated back to the stakeholders to be certain that their needs, wants, and expectations have been properly collected and documented.
It is also important that the stakeholders agree with the prioritized listing identified.
Examples of requirement statements for a product could be stating that a cabinet be specific dimensions or that a portable game system has the ability to connect to other user’s same portable game system through Wi-Fi.
An example of a service requirement is that user’s emailed feedback comments will be responded to within 72 hours. Or a caller to the help center will be sent an email after the caller’s issue has been resolved to survey the satisfaction the user had by the technical or customer service received.
These examples demonstrate that requirements go beyond just describing what the physical product will do.

## Slide 17
Product acceptance criteria
Chapter
06
The project scope statement outlines the criteria for which the project will be approved and therefore is a definitional guide to measuring success.
One example of acceptance criteria would be the requirement of submission of all project close-out documentation and all program code to the customer.
Another common example is schedule or cost criteria.
In an information technology projects, examples of these could be goals related to performance and quality.
For instance, system response times or transaction rates would be performance criteria, where the number of known defects that were not corrected by the completion of the project would be quality criteria (McBride et al. 2007).
All acceptance criteria should be written in very concise statements so that no two individuals would interpret the requirement differently.

## Slide 18
Project boundaries
Chapter
06
Project boundaries need to be set so that the PM does not find himself/herself being placed in a position where the amount of funds provided is firm, yet the scope of the project work keeps growing.
Boundaries need to be identified in the scope statement so that there will be no confusion as to what exactly will or will not be accomplished during the course of the project.
It is important to point out what is in scope and what is out of scope.
This will be important later as conflicts emerge on what is within scope of the project, and it protects the project team in these situations.
Physical documentation is very important for this purpose, as well as obtaining signatures from key stakeholders so that there is understanding of the scope.
This process is an important one to help deal with scope definition and scope creep issues that may occur later in the life cycle.
Creeping requirements can be avoided through having a project boundaries section (Cervone 2006).

## Slide 19
Project requirements and deliverables
Chapter
06
A project requirement can be defined as anything that needs to be accomplished as part of the project.
PMI (2008) further defines a requirement as a system, product, service, result, standard, or anything else that is desired by a stakeholder.
Just as discussed above in the product requirements section, it is important to communicate with the stakeholders to collect and confirm their needs, wants, and expectations.
Then, the team needs to produce requirement statements that are very concise statements that no two individuals would interpret differently.
Then, the requirement statements should be taken back to the stakeholders to be certain that their needs, wants, and expectations are linked to specific requirements so that the team gets feedback that the stakeholders’ needs, wants, and expectations were correctly interpreted.
The deliverables definition should identify the specific items that are to be produced.
These can be systems, websites, products, program codes, password documents, new processes, or technical manuals.

## Slide 20
Project constraints
Chapter
06
Most projects have constraints which limit their degrees of freedom.
Many times, these are not recognized and therefore not obeyed.
This section provides a means for formally communicating to the key stakeholders what these constraints are for the project and its environment.
Politically, it may not be recommended to identify all constraints but, when possible, it provides clear communication internal and external to the project team.
Constraints are merely restrictions that exist such as funds, timelines, contracts in place requiring that purchases be made from certain suppliers, system interfaces produced to be compatible with existing organization’s systems, or even space availability.
The PM as part of his/her role is responsible for realistically identifying tasks and timelines based around these constraints.

## Slide 21
Project assumptions
Chapter
06
Assumptions are statements that the PM believes to be true such as access to some defined level of organizational resources such as all team members are provided adequate computer workstations, office supplies, equipment, and so on.
These can even be opportunities for the project.
It may also state that some external organizational group will provide support to the team.
This section is again just a way to communicate to all parties' different constraints related to the project.
This section will also contain a statement regarding the impact to the project if the assumptions are incorrect such as a project falling behind schedule if promised resources are not provided.
Likely, one of the most important assumptions to document and make clear to the management approval group is that of resource availability.
A perfect plan that is not supported with resources is worthless.
The supplying organizations need to be made explicitly aware that failure to support the plan will result in undesirable outcomes.
Throughout the life cycle, it is a good idea to review assumptions and verify that they are still valid.

## Slide 22
Project organization/team assessment
Chapter
06
The team membership section of the project scope statement will likely have very little information at this stage since the project is not completely defined yet.
However, in a few cases the scope statement may have additional details if this information has already been defined.
The information in this section is more likely to not exist at this stage but instead in the final scope subsidiary plan.
Project organization and team assessment information include each team member’s name, contact information, and position.
This section will further contain the authority that was granted to the PM in the project charter discussed in the last chapter. In addition, it will contain the details on the responsibilities of each team member.
The scope statement may list the specialty area held by various team members such as computer programmer, architecture, engineer, and so on.
It will identify the degree of involvement each team member has in terms of full-time team member, part-time team member, advisory board member, and so on.
It is often difficult to interpret the degree of authority that different team members have, so this information may be integrated into the scope statement.

## Slide 23
Project organization/team assessment
Chapter
06
It could be as simple as to list an alternative PM signifying that a team member has the signing power in the absence of the PM.
However, this information needs to be clearly documented, so there is no room to misinterpret the degree of authority held by team members.
Generally, the team member section will identify certain team members as leads over different areas of the project which is an easy and clear way of identifying the different degrees of authority on the project charter.
There may also be a section of the scope statement that identifies the means of assessment of team members.
It may be a statement of biannual performance review assessments that are conducted.
It may even list out key areas of assessment for team members.
These assessment areas may revolve around the same performance assessments that the PM is held to such as meeting the project schedule or quality of deliverables.
The assessments can even be in terms of how well a team member works as part of the team to collectively meet the project goals and objectives.
As mentioned earlier in this section, the information above likely would not exist at this stage but it is mentioned in case an organization already has this information defined.

## Slide 24
Defined risks
Chapter
06
The risk management process at this stage is of high level.
This process provides a way to reduce project outcome uncertainty through providing awareness, assessment, and handling of risks, thereby minimizing future threats, seizing opportunities, and achieving improved results.
It also identifies the degree to which a risk may occur and the outcome it could have in terms of impacting project success.
Risk management is a process entity of its own and therefore is described in more detail in Chapters 11 and 22.
Time spent in risk management up front allows those involved to not be in a crisis mode later when identifying the best way to manage the unplanned event.
Project risk management involves the identification of potential risks affiliated with a project.
Potential risk events can be identified by reviewing previous project data and other company historical records to see which risk factors have previously occurred. In addition to this, brainstorming sessions are a potential process to further identify items that may have never occurred before but still pose a threat to the project.

## Slide 25
Defined risks
Chapter
06
Vargas-Hernadez (2011) suggests categorizing risks using major category headings such as environment, technical, resources, integration, management, marketing, and strategy.
For instance, the project may have a risk under the category of environment—that is, bad weather during some time frame.
At this stage in the project, the risk assessment is of very high level.
The more detailed assessment and quantification process will come later in the planning process which will be discussed later in the book.
At this early stage, the goal is to give the decision-makers a high-level view of this aspect of the project.

## Slide 26
Milestones
Chapter
06
Milestones are any significant events, deliverables or achievements within a project or schedule (PMI 2008).
A significant event could signify that Phase I has been completed and Phase II is beginning.
Another example is that all system testing is completed or that a system implementation is complete at a specific location.
Completion at each location may be defined as a project milestone event.
Furthermore, it is common to signify a milestone at the end of a project to indicate that it has officially been completed which could even be to have a formal close-out celebration event if appropriate.
At this point, timeline estimates may be included indicating target milestones.
At this stage, the term “target” might be more descriptive, but eventually these same points often become official milestones and will be met but this may not be listed in this document since the WBS discussed in the next chapter has to be developed to have an accurate timeline.

## Slide 27
Work definition
Chapter
06
The initial WBS for the project is very high level and subject to significant error is prediction since the speciation details are not yet completed.
As the planning process unfolds, the level of definition and accuracy improves.
At this stage of the project, it is common to quote ranges of values in the ±100% category for projects that are not similar to previous ones.
The goal of the initial WBS at this stage is to logically organize the work estimate.
The level of detail and accuracy at this point is based on whether the project is similar to others that have been undertaken, or a new initiative.
If similar, then these data will be more detailed.
A WBS is a common artifact to logically divide the work estimate.
This initial view will be expanded as the scoping process unfolds.
Chapter 7 will explain the WBS process in more detail.

## Slide 28
Cost estimate
Chapter
06
This section will describe the budget based on the requirements at this point which produces a high-level estimate.
As with the time and initial WBS, cost estimates will often be quite broad regarding the amount of the budget for different aspects of the project such as equipment, labor, facilities, technology, and so on.
It will also address where the funds are from in terms of funding from a specific program or department or combination of different organizational departments if this information is known.
Finally, within MS Project 2010, the project’s budget resource feature can be used to define the budget for different categories of items.
In some projects, it may state how some of the project income is generated from sales such as a project responsible for hosting one or more events where tickets are sold.
The event may be able to pay for entertainment, food, and so on based on the income that comes in from ticket sales.

## Slide 29
Project configuration management requirements
Chapter
06
Configuration management is how the entire project is managed from procedures to set-up project documentation to tracking of the project milestones to team interactions.
At this point within the project, this section may be incomplete.
Each team will have different rules of engagement so to speak which are internal team processes.
These rules may be on conducting meetings, keeping sensitive information confidential, communicating within the team, tracking product quality, and so on.
The scope statement may have a section devoted to team guidelines.
The PM will likely not publish all of the rules of engagement but there may be rules that make sense to formally display on the project scope statement.
Inaccurate configuration control is a risk that is particularly present in information technology projects (Cervone 2006).

## Slide 30
Project configuration management requirements
Chapter
06
As part of the configuration management requirements, a system could be set-up to centralize all data and information pertaining to the project (Perkins-Munn and Chen 2004).
This would increase the speed of information being delivered to team members. Statistics of which information has been read or not read by team members could also be tracked.
Team members could be given read access and other stakeholders given access only to specific folders of information.
The PM then could be the only one with write access or would control which members have write access.
This would be a way of making sure every team member is using the most up-to-date team information.
One aspect of configuration management is having a procedure in place for how to handle any additions, deletions, and modifications made to the project documentation.
This aspect will be discussed in greater detail in Chapter 18.

## Slide 31
Approval requirements
Chapter
06
Approval requirements is for the protection of the PM and the project sponsor for signatures to be obtained so that everyone agrees to the requirements contained within the project scope statement.
Just like the analogy used in the last chapter regarding the charter, the same press release analogy applies for this chapter too as the scope statement should be sent to the project team and anyone that is affected by the project.

## Slide 32
Summary
Chapter
06
A determination is made to identify the skills needed to carry out the project to include identification of, some of the team members and the project sponsor(s).
The PM will lead the establishing of the project’s scope and criteria for success in terms of clear and measurable objectives.
After completing scope planning and definition, the next step is to further define the work by breaking it into manageable pieces which is accomplished in the following chapter.
If the scope planning and definition processes are successful, then it will help one to improve the accuracy of time, cost, and resource estimates which span over many of the book chapters.
It also defines a baseline for performance measurement discussed in Chapter 14 which focuses on the key performance indicators as well as project control.
It will also aid in communicating clear work responsibilities which is further addressed in Chapter 23 which focuses on Team Tools.

## Slide 33
QUESTIONS
Chapter
06
Review questions
  Describe the inputs and outputs of the scope planning process.
  Describe the inputs and outputs of the scope definition process.
  What is a scope management plan?
  What is a project scope statement?
In-class question
  Find a scope management plan template on the Internet and describe the sections contained within it.
  Find a scope statement template on the Internet and describe the sections contained within it.
EXERCISE
  1. Create a scope management plan for the car case study using the scope statement sections described in this chapter or found online.
  2. Create a scope statement for the car case study using the scope statement sections described in this chapter or found online.

## Slide 34
References
Chapter
06
2002. Redesigning project management at Kimberly−Clark Europe. Training Strategies for Tomorrow 16(6):8–11.
Bourne, L. and D.H.T. Walker. 2005. The paradox of project control. Team Performance Management 11(5–6):157–178.
Cervone, H.F. 2006. Managing digital libraries: The view from 30,000 feet, project risk management. International Digital Library Perspectives 22(4):256–262.
Little, B. 2011. The principles of successful project management. Human Resource Management International Digest 19(7):36–39.
Maddalena, V. 2012. A primer on project management. Leadership in Health Services 25(2):80–89.
McBride T., B. Henderson-Sellers, and D. Zowghi. 2007. Software development as a design or a production project: An empirical study of project monitoring and control. Journal of Enterprise Information Management 20(1):70–82.
Peled, A. 2000. Creating winning information technology project teams in the public sector. Team Performance Management 6(1):6–15.

## Slide 35
References
Chapter
06
Perkins-Munn, T.S. and Y.T. Chen. 2004. Streamlining project management through online solutions. Journal of Business Strategy 25(1):45–48.
Project Management Institute (PMI). 2008. PMBOK® Guide, 4th ed. Newtown Square, PA: Project Management Institute.
Swan, W. and M.M.A. Khalfan. 2007. Mutual objectives setting for partnering projects in the public sector. Engineering, Construction and Architectural Management 14(2):119–130.
Vargas-Hernadez, J.G. 2011. Modeling risk and innovation management. Advances in Competitiveness Research 19(3–4):45–57.

## Slide 36
Thank You
Chapter
04 - 05
The End..
Thank You