## ورقة1
student name |  | Faraj A. Alkhlaf | student Id | 2021206123
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | The invention of a new type of solar panels with low price and higer efficiency | moderate | moderate | Economic boom that might introduce new products in the market | Selecting panels that can be modified | Procurement manager | مشروع مرآة للطاقة الشمسية
2 | THREATS | Environmental disasters | moderate | high | Rapid climate changes | Selecting the right place to reduce possibilities of environmental disasters affecting the solar panels | Project manager | مشروع مرآة للطاقة الشمسية
3 | OPPORTUNITIES | High oil prices, which may positively affect investment in the field of solar energy | high | moderate | economic boom that might incraces the oil prices | increase the invest in Solar energy | Project manager | مشروع مرآة للطاقة الشمسية
4 | OPPORTUNITIES | Reduce environmental pollution | high | high | power up using solar energy instead of oil based electric power up | increase the invest in Solar energy | Project manager | مشروع مرآة للطاقة الشمسية
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low