## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | labor unavailability | high | low | Time delays in achieving key milestones | Have a training deparment for new workers/source employees from other countries | Project manager | مشروع مترو الرياض
2 | THREATS | Economic inflation | moderate | moderate | Increase in the cost of materials and labor | Sign effective futures contracts with suppliers | Project manager
3 | OPPORTUNITIES | Support from regulatory authorities and government | high | high | Good relationship with authorities and faster approvals | Exploit the opportunity to ensure probability of occurrence is 100% | Senior management
4 | OPPORTUNITIES | Good relationship with local community | high | moderate | Positive public perception and opinion | Run campaigns to shape public opinion and support local community programs | Project manager
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low