## Slide 1
Project Monitoring Course
Prepared & presented by:
Dr. Dhouha Melliti
2022-2023
Lecture 12:
Project Monitoring Course Revision

## Slide 2
Lecture11
Session6:Course Revision
What is M&E?
M&E is a process of continual gathering of information and assessment of it in order to determine whether progress is being made towards pre-specified goals and objectives, and to highlight whether there are any unintended (positive or negative) effects from a project and its activities. It is an integral part of the project cycle and of good management practice.
Monitoring is carried out in order to track progress and performance as a basis for decision-making at various steps in the process of an initiative or project.
Evaluation, on the other hand is a more generalised assessment of data or experience to establish to what extent the initiative has achieved its goals or objectives.

## Slide 3
Lecture11
Session6:Course Revision
Why a M&E system?
Improve project and programme design through the feedback provided from mid- term, terminal and ex post evaluations;
Inform and influence sector and country assistance strategy through analysis of the outcomes and impact of interventions, and the strengths and weaknesses of their implementation, enabling governments and organisations to develop a knowledge base of the types of interventions that are successful (ie what works, what does not and why?
Provide regular feedback on project performance and show any need for ‘mid- course’ corrections
identify problems early and propose solutions
monitor access to project services and outcomes by the target population;
Evaluate achievement of project objectives
Measure the impact of the project on various indicators (including those relating to project objectives and other areas of concern)
Incorporate stakeholder views and promote participation, ownership and accountability
provide the evidential basis for building consensus between stakeholder

## Slide 4
Lecture11
Session6:Course Revision
how to monitor ?
A strong project design is the foundation for successful monitoring. The proposal development stage clearly articulates the desired results an intervention aims to achieve, how it achieves them and stipulates how progress towards these results will be measured

## Slide 5
Lecture11
Session6:Course Revision
Program theory
The Programme theory is a key aspect of implementation design and explains how an intervention (project/programme, strategy and policy) is expected to contribute to a chain of results.
It is a representation of all the building blocks that are required to bring about a higher- level change or results.
It is usually formulated at the proposal development stage.
It can therefore be useful in providing a conceptual framework for monitoring, as well as for evaluation.
Theory of Change
Is a comprehensive description and explanation of how and why a desired change is expected to happen in a particular context.
Specifically, it focuses on mapping out what an intervention or change initiative does (its activities) and how these lead to achievement of the objective through results (outputs, outcomes, objectives). In this way, a ToC articulates hypotheses about how change happens by explaining the connection between an intervention and its effect. It does so by surfacing the logic and rationale for an intervention and articulating the assumptions inherent in the approach (multiple pathways).

## Slide 6
Lecture11
Session6:Course Revision
  Results Matrix
As previously mentioned, also belonging to program theory is the logical framework, which helps identify an intervention’s operational design and is a foundation for M&E.
It is an overview of an intervention’s intended approach to attain results, based on the situation and problem analysis undertaken during the conceptualization stage.
Specifically, it uses a matrix to summarize the logical sequence in which an intervention aims to achieve desired results, the activities required to attain these results and the indicators and sources of verification that help measure progress towards achieving results.

## Slide 7
Lecture11
Session6:Course Revision
When selecting a data source, the following should be considered:
Will there be access to the information?
Where will the information be attained from?
Can the data source provide quality data?
How will the information be attained given limited resources?
How costly and feasible is collecting the information?
Key considerations in setting indicator baselines
Depending on the context and nature of an intervention, baseline data may not always be available during its development phase. In such cases, it may be appropriate to propose collecting baseline data (and subsequently the targets) once the intervention begins, in agreement with other key counterparts and donors.
In some cases, a baseline study or assessment may be required to identify the appropriate baseline data, if a budget is available for it, as it may have costly implications. For instance, in cases where changes to the general population are of interest, a census can be used as a baseline; however, this may not always be available, and it would be costly to conduct one related to the intervention

## Slide 8
Lecture11
Session 5:Course Revision
  In other scenarios, it may not be possible to conduct a needed baseline study due to security restrictions or other reasons outside of control.
  In such cases, data collected during the first monitoring visit, when a specific indicator is measured for the first time, can be considered a baseline for that indicator.
  Particularly in multiphase programs, baseline data may be available through other previously implemented interventions.
  However, in all cases, it is critical to be consistent in the way data is presented within the intervention, at the development phase and throughout reporting, as well as to always have a solid understanding and justification for why baseline data is presented in a particular way.

## Slide 9
Lecture11
Session 6:Course Revision
Types of monitoring
A variety of elements can be monitored in an intervention and what to monitor will depend on the specific information needs of an intervention:
1. Activity monitoring tracks progress, gaps and delays in activities against a detailed workplan.
A manager should already have a basic workplan from the intervention proposal. At the start of implementation, this basic workplan should be further developed into a detailed workplan. The detailed workplan includes the activities and tasks identified within the Results Matrix, along with all other activities and tasks related to implementation. It includes, for example, a section for ongoing monitoring, evaluation and reporting activities. Ideally, the development of the detailed workplan should be undertaken by the intervention team, under the overall leadership of the manager.
2. Results monitoring tracks results: This type of monitoring is used to determine whether an intervention is on or off track towards its intended results (outputs, outcomes, objective).
It is also recommended to reflect on and identify any unintended positive or negative effect. An example of this could be if training participants independently created a working group and continued to meet beyond the time frame of that training.
3. Financial monitoring tracks costs by input against the planned expenditures as per the approved budget.
It is often done in conjunction with compliance and process monitoring .
4. Risk monitoring tracks whether previously identified risks are still pertinent, if new risk has emerged and assesses whether the likelihood and timeline of previously identified risks remain accurate.

## Slide 10
Lecture11
Session 6:Course Revision
Planning and designing data collection tools
Rigorous planning and designing for data collection can improve the quality of the approach and methods of data collection and, therefore, the quality of collected data.
It is imperative to identify the approach intended for use to monitor or evaluate an intervention, and then to establish a data collection plan. Selecting an appropriate approach will also allow a relevant assessment of the monitoring or evaluation questions guiding any review, taking into account the specific context, existing constraints, access, timing, budget and availability of data.
Data governance
Represents the framework used to manage the organizational structures, policies, fundamentals and quality that ensures accurate and risk-free migration data and information.
It establishes standards, accountability and responsibilities and ensures that migration data and information use are of maximum value, while managing the cost and quality of handling the information.
Data governance enforces the consistent and integrated of all members of the project.
Data governance allows to view data as an asset in every intervention and, most importantly, it is the foundation upon which all initiatives can rest.
It is important to keep in mind the migration data life cycle throughout the whole project cycle.
This includes the planning and designing, capturing and developing, organizing, storing and protecting, using, monitoring and reviewing, and eventually improving, the data or disposing of it.
Key concepts to look out for:Data steward, Roles and responsibilities,Data quality, Data classification for security and privacy and Data processing, including collection and use.

## Slide 11
Lecture11
Session6:Course Revision
    Types of measurement
  When planning for data collection and analysis, knowing the type of measurement, that is how data will be measured, may influence the decision to choose the appropriate methodology. This is of particular importance to inform the design of data collection tools such as surveys.
  Measures of indicators identified in a Results Matrix or Evaluation Matrix can include categorical (qualitative) and/or numerical (quantitative) variables. A variable is any characteristic or attribute that differs among and can be measured for each unit in a sample or population .
  Categorical variables represent types of qualitative data that can be divided into groups or categories.
  Such groups may consist of alphabetic (such as gender, hair colour or religion) or numeric labels (such as female = 1, male = 0), or binary labels (such as yes or no) that do not contain information beyond the frequency counts related to group membership.
  Numerical variables (also known as quantitative variables) are used to measure objective things that can be expressed in numeric terms such as absolute figures, such as the number of persons trained, disaggregated by sex, a percentage, a rate or a ratio.

## Slide 12
Lecture11
Session6:Course Revision
  Methods, approaches and tools for monitoring and evaluation
  Methods for and approaches to data collection are systematic procedures and useful to support the process of designing data collection tools. Generally, a mixture of qualitative and quantitative methods and approaches to data collection are used.
  Although there are multiple definitions for these concepts, quantitative methods and approaches can be viewed as being based on numerical data that can be analysed using statistics.
  They focus on pinpointing what, where, when, how often and how long something occurs and can provide objective, hard facts, but cannot explain why something occurs. Qualitative methods and approaches for data collection are based on data that are descriptive in nature, rather than data that can be measured or counted. Qualitative research methods can use descriptive words that can be examined for patterns or meaning and, therefore, focus on why or how something occurs.
Impact evaluations aim to identify a proper counterfactual and whether impact can be confidently attributed to an intervention. Specifically, this may be done by assessing the situation of the beneficiaries “before and after” and “with or without” the intervention.
By comparing the before and after and/or with or without scenarios, any differences/changes observed can be attributed to the intervention, with some reservations as it is not always straightforward and attribution may be more complex to assess than by answering the above scenarios.
While there is a range of impact evaluation designs, there is also a range of methods that are applicable within these designs.To answer the specific evaluation questions, methods are flexible and can be used in different combinations within impact evaluation designs. Experimental, quasi-experimental and non-experimental are three types of impact evaluation design.

## Slide 13
Lecture11
Session6:Course Revision
Collecting and managing data
Once the M&E design has been identified and the method(s) and tools have been developed, the data collection can start. It is also recommended to organize a training with the data collection team(s) on the methodology. The training should cover in detail each data collection tool that will be used and include practical exercises of how to implement them.
Developing a data collection guide with clear instructions for the enumerators is a useful reference tool, both during the training and after, for the actual data collection; see the example provided below for an excerpt from a survey included in a data collection guide.
Diagnosis: Once the suspect data has been identified, the next step is to review all the respondent’s answers to determine if the data makes sense given the context in which it was collected. Following this review, there are several possible diagnoses for each suspect data point identified:
      The data point is missing. Missing data can be a result of omitted answers by the respondents (no response), questions that are skipped over by the enumerator (erroneous entry or skip pattern) or the data entry agents, or there are dropouts (for longitudinal research).
      The data point is a true extreme value. True extreme values are answers that seem high but can be justified by other answers.
      The data point is a true normal value. True normal values are valid answers.

## Slide 14
Lecture11
Session 5:Course Revision
Treatment
Once the problematic observations have been identified, these need to be treated before the data can be analysed.
The following are some of the key approaches to dealing with data errors:
      Leave the data unchanged. This approach is the most conservative as it entails accepting the erroneous data as valid response(s) and making no changes.
      For large-n studies, leaving one erroneous response may not affect the analysis. However, for small-n studies, the decision of leaving the data unchanged may be more problematic.
      Correct the data, however without modification of the intention of or meaning given by the respondent.
      Delete the data. It is important to remember that leaving out data can make it seem as if the data is being “cherry-picked” to obtain the desired results.
General decision-making rules: If the person doing the data entry has entered values different from the ones in the survey, the value should be changed to what was recorded in the survey form.
When variable values do not make sense and there is no data entry error nor notes to determine where the error comes from, the value should be left as it is. Any changes will bias the data.
When blank cases are present for questions that required an answer, or if erroneous values cannot be corrected, these may be deleted from the data file.
When there are still suspect and true extreme values after the diagnostic phase, it is necessary to next examine the influence of these data points, both individually and as a group, on the results before deciding whether or not to leave the data unchanged.
Any data points taken out of the data set should be reported as “excluded from analysis” in the methodology chapter of the final report.

## Slide 15
Lecture11
Session 6:Course Revision
Evaluation overview
Evaluation is defined as the systematic and objective assessment of an ongoing or completed intervention, including a project, program, strategy or policy, its design, implementation and results.
Evaluation is about accountability and learning by informing stakeholders on the extent to which resources have been used efficiently and effectively to achieve results, and providing empirical knowledge about which elements of an intervention worked or did not work.
There are four important roles to distinguish within the evaluation process: (a) the evaluation commissioner, (b) the evaluation manager; (c) the evaluator and (d) the evaluation user.
The evaluation commissioner is the party or stakeholder who decides that an evaluation should take place. This could be the program manager, relevant chief of mission (CoM), a thematic specialist or unit(s) from Headquarters and/or from a regional/country office, the donor or any combination of these stakeholders.
The evaluation manager is the person who is in charge of managing the evaluation. It is possible that the evaluation manager is from the same entity or office that commissioned the evaluation. Most often, the evaluation manager is the program or project manager. It is important to note that, at times, several stakeholders may be part of an evaluation management committee, overseeing the evaluation process together.
An evaluator is charged with conducting the evaluation. Evaluators can be external consultants, donors, partner organizations and governments.
The evaluation users are key players for guaranteeing the full utilization and benefits of evaluation. They can be direct users, who are, for instance, directly concerned with the implementation of the recommendations and accountability purposes, as well as indirect users that can be more interested with the learning dimension of the evaluation. In addition to these roles, there are other stakeholder engagement and reference groups that play an important role, for instance in terms of quality assurance

## Slide 16
Lecture11
Session6:Course Revision
    The evaluation stages
1. Planning for evaluation: Define the purpose and evaluability of evaluation
Prepare evaluation terms of reference & Select evaluator(s).
2. Undertaking evaluation: Supervise evaluation implementation and workplan Evaluation deliverables
Provide feedback on all phases of the evaluation & Ensure evaluation quality.
3. Follow-up and using evaluation: Follow-up on the implementation of recommendations and use of the report using and disseminating the evaluation.

## Slide 17
Lecture11
Session 5: Course Revision
key components of terms of reference
The evaluation context section provides a summary description of the political, economic, social, environmental and/or legal contexts in which the intervention is being implemented.
The evaluation purpose/objective section explains why the evaluation is being conducted and the main objective of the evaluation itself. In this section, the intended audience for the evaluation and how the evaluation will be used are also included. These are important elements that provide information on its utilization for both accountability and learning purposes, as well as who may be concerned by its recommendations.
An evaluation scope specifies what will be covered by the evaluation, including, for instance, the components or phases of the intervention that will be assessed, the period of the intervention to be covered (relevant phases or given years), any other intervention(s) that should also be considered or the geographical area to be covered.
The evaluation criteria are those described in the previous section of this chapter. The criteria selected for the evaluation should be listed clearly in this section of the ToR
Evaluation questions should be developed based on the evaluation criteria selected. The questions should be categorized per the criteria.
methodology section can be proposed by evaluators in the proposals submitted during the selection process or during the inception phase. This section describes the type of data collection and analysis methods to be used in the evaluation and inform the evaluator accordingly.
Ethics, norms and standards for evaluation Include the following statement at the end of the ToR.

## Slide 18
Lecture11
Session 5:Course Revision
Accountability and learning from evaluation
The benefits of using information derived from evaluations are numerous. Practitioners must effectively apply this information to enhance accountability, improve performance, as well as strengthen decision- making through learning.
Accountability can be defined as “the obligation to demonstrate that work has been conducted in compliance with agreed rules and standards or to report fairly and accurately on performance results vis-à-vis mandated roles and/or plans. This may require a careful, even a legally sound, demonstration that the work is consistent with the contract terms”.
Learning, on the other hand, is the process by which individuals or organizations acquire and use skills and knowledge. This section will address the various ways of learning through evaluation and other evaluative approaches and, while the requirements related to accountability in sharing an evaluation report are covered in the previous section, this section will also include accountability considerations for the other evaluative approaches that are discussed.
Knowledge and learning derived from evaluation can feed back into the organizational learning and planning processes through regular reflection, accessibility to the evaluation reports and regular exchange of information through learning sessions.

## Slide 19
Lecture11
Session 6:Course Revision
Incorporating cross-cutting themes in evaluation
Cross-cutting themes can be defined as additional considerations or areas that intersect with an intervention, or that can be easily integrated into it, without losing focus on the main goals of the intervention. Mainstreaming a cross-cutting theme is generally understood as a strategy to make the specific theme, given its importance, an integral dimension of the organization’s design, implementation and M&E of policies and interventions. The inclusion of themes can evolve over time and new themes can be added; they are not necessarily the same for all organizations and not all may be relevant to be considered in an intervention.
Rights-based approach is a conceptual framework and methodological tool for developing policies and practices. RBA is the conscious and systematic integration of rights, norms and standards derived from international law into programming,
Equality and non-discrimination Is the M&E process explicitly designed to detect or measure discrimination against particular groups throughout its objectives and outcomes?
  Is the data collected appropriately disaggregated, such as by age, disability, ethnicity, sex, nationality and migration status, to track any gaps in considering equality and discrimination throughout intervention outputs and outcomes?
Accountability, transparency and rule of lawAre the M&E processes directly linked to any rights such as measuring the realization of specific rights?
  Do the M&E processes account for any form of complaint mechanisms and how are received complaints dealt with?
  Are the findings from the M&E shared publicly in a transparent manner?
  Are the findings from the M&E used to promote changes in law or policy of the State?

## Slide 20
Lecture11
Session 6:Course Revision
How to monitor and evaluate environmental considerations
When interventions are not specifically designed to address environmental issues – such as programs addressing disaster preparedness and disaster risk reduction to prevent forced migration that results from environmental factors, or those for relocation of populations from zones affected by environmental degradations – there are various elements that can be taken into account for monitoring and evaluating the inclusion of environmental sensibility and sustainability as a cross-cutting issue.

## Slide 21
Lecture10
Session 5: Evaluation (Part3)
A final evaluation report. In particular, they can be incorporated into any evaluation summary documents made available to relevant users.
The Evaluation brief template and guidance contains a specific section for the presentation of lessons learned, when required.
In some cases, lessons learned may be of particular interest to relevant thematic specialists for their further dissemination and applicability to other similar interventions.
The “use” of lessons learned is particularly critical in the development of new interventions, at the project or program level, as well as in the development of strong strategic and policy guidance to a particular area of work.
Therefore, evaluation managers should carefully consider with whom to share lessons learned and identified good practices, in order to best incorporate them into future

## Slide 22
Incorporating cross-cutting themes in evaluation
Cross-cutting themes can be defined as additional considerations or areas that intersect with an intervention, or that can be easily integrated into it, without losing focus on the main goals of the intervention. Mainstreaming a cross-cutting theme is generally understood as a strategy to make the specific theme, given its importance, an integral dimension of the organization’s design, implementation and M&E of policies and interventions. The inclusion of themes can evolve over time and new themes can be added; they are not necessarily the same for all organizations and not all may be relevant to be considered in an intervention.

## Slide 23
Lecture9