## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | OPPORTUNITIES | Super fast Transportion | high | moderate | Need high speen Transportion | Adopting new soultion for transportion | Product Manager | مشروع الهايبر لوب
2 | THREATS | High cost for the transportion | moderate | low | high cost | can't exceute without low cost | Finance Manager
3 | THREATS | The need to build large-scale hyperloop networks | high | low | high cost | if there a financial plan as sharing revinew model between cities | Finance Manager
4 | OPPORTUNITIES | New logistic soultion | high | high | The need for transportation tools without human intervention | The participation between countries in the desired benefit from automated transportation | Finance Manager
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low