## Slide 1
Project Time Management
Prepared by Dr. Nael Zabel
Lecture 7
PMG 212
Schedule

## Slide 2
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 3
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 4
Scheduling
Lecture 7
If PLANNING is an Art form based on Experience and Knowledge, then SCHEDULING is a Systematic exercise in using applied Logic.

## Slide 5
Schedule
Lecture 7

## Slide 6
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 7
Who is the Scheduler
Lecture 7

## Slide 8
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 9
Attributes of Planner/Scheduler
Lecture 7
Possess PEOPLE skills!
  Exercise humility and salesmanship
  Exercise care when recommending various approaches
  Do not alienate the managing parties
  Ease off when needed
  Emphasize his/her role is to coordinate and integrate ideas and plans into a coherent project schedule.
امتلاك المهارات الشخصية (عدم الاعتماد على البرامج الحاسوبية)
  التحلي بمهارات التواصل بين أقسام المشروع
  العناية الشديدة عند التوصية بإستخدام أساليب مختلفة
  العمل على عدم نفور الأطراف ذات الصلة
  الحد من المشكلات عند الحاجة
  تنسيق ودمج الأفكار والخطط في جدول زمني متماسك

## Slide 10
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 11
Importance of the Schedule
Lecture 7
Depicts يصورthe Scope of work
Improves the probability for the project team to meet its goals
Establishes overall schedule parameters
Aids in determining staffing requirements

## Slide 12
Importance of the Schedule
Lecture 7
Resource loading basis
Identifies long lead items
Identifies the phases in the project

## Slide 13
Importance of the Schedule
Lecture 7
Standardized scheduling techniques motivates the project team to:
  Think through the entire project
  Predict a realistic project completion
  Recognize impacts of unexpected events

## Slide 14
Importance of the Schedule
Lecture 7
Standardized scheduling techniques motivates the project team to:
  Identify claims or time extensions
  Coordinate interfaces and reduce conflicts
  Plan resource requirements and cash flow
  Serve as a record of the project’s progress
  Communication Tool

## Slide 15
Importance of the Schedule
Lecture 7
  Tells you where you’ve been.
  Tells you where you are.
  But most importantly, it tells you where are you going!
Must have sufficient detail to control the project
  To much detail is cumbersome to maintain.
  Not enough detail and the analysis of the schedule is difficult.

## Slide 16
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 17
Scheduling Tools
Lecture 7
P6 (Primavera)
Microsoft Project Planner (MSP)
Suretrak (Primavera)
Milestones, etc.. - Bar Chart
TILOS- Linear Scheduling

## Slide 18
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 19
Scheduling Methodology
Lecture 7

## Slide 20
Critical Path Method
Lecture 7
The calculation of the earliest and latest start and finish dates of activities based on their duration's and relationships to other activities
a resource-utilization algorithm for scheduling a set of project activities
Item | Price
A | 100
B | 100
C | 100
D | 100
E | 100
F | 100
Sum | 600

## Slide 21
Activities
Lecture 7
The Basic element into which a project is subdivided for scheduling a network (CPM)
  Has a definable start and finish
  Consumes resources
  Is assignable
  Is measurable
  Is defined by a Work Package
  Is a Physical Task for Construction

## Slide 22
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 23
Scheduling Terminology: Work Package
Lecture 7
A group or number of Engineering/Construction Deliverables that will enable Procurement or Construction to accomplish a meaningful task. WP is the lowest level of a WBS.
  All of the Data Sheets & Specifications required for a Purchase Order.
  All of the Drawings & Details necessary to Locate, Excavate, Form and Pour a Foundation
  Earthwork
  Foundation
  Cabling

## Slide 24
Scheduling Terminology:
Work Package Template
Lecture 7

## Slide 25
Scheduling Terminology: Milestone
Lecture 7
Is a GOAL to be achieved.
    Can be either a Start or Finish Achievement
    Is a single point in Time
    Has no duration
    Has no resources
    Has a specific and unique Definition
    It is either YES or NO

## Slide 26
Scheduling Terminology
Lecture 7
Predecessor = An activity that must occur before another activity. A predecessor activity controls the start or finish date of its successor(s). An activity can have multiple predecessors, each with a different relationship to it.
Successor = An activity that must occur after another activity. An activity can have multiple successors, each with a different relationship to it.

## Slide 27
Scheduling Terminology
Predecessor and Successor Synonymsمرادفات
Lecture 7
Dependencies
Prerequisites
Interface requirements
Links
Logic relationships “To” and “From”
التابعين (الاعتماديين)
المتطلبات المسبقة
متطلبات الواجهة/الربط
الروابط
العلاقات المنطقية "إلى" و "من"

## Slide 28
Agenda
Lecture 7
Scheduling
Who is the Scheduler
Attributes of Planner/Scheduler
Importance of the Schedule
Scheduling Tools
Critical Path Method
Scheduling Terminology
Relationships (Logic) – 4 Types

## Slide 29
Relationships (Logic) – 4 Types
Lecture 7
  Finish to Start - FS - A relationship in which the predecessor activity must Finish before its successor activity can Start.

## Slide 30
Relationships (Logic) – 4 Types
Lecture 7
  Finish to Finish - FF - A relationship in which the Finish of a successor activity depends on the Finish of its predecessor activity.

## Slide 31
Relationships (Logic) – 4 Types
Lecture 7
  Start to Finish - SF - A relationship in which the Start of the predecessor activity controls the Finish of a successor activity. Not used

## Slide 32
Relationships (Logic) – 4 Types
Lecture 7
  Start to Start - SS - A relationship in which the Start of the predecessor activity controls the Start of a successor activity .
SS 0
A
B

## Slide 33
Lecture 7
Thank You