## Slide 1
Prepared by Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Agile Project
Management
Lecture 4
PMG 622
Master of Project Management

## Slide 2
Strengths and Weaknesses of the Agile Approach
Lecture 4
PMG 622
Agile Project Management
Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Prepared by

## Slide 3
Learning Objectives
Learn Agile techniques, strengths and weaknesses for:
Scope Management
Time Management
Cost Management
Lecture
04

## Slide 4
Key Points from Previous Lecture
Lecture
04
Traditional and Agile PM Life Cycles have many similarities and also differences
Selection of the RIGHT Life Cycle depends on Degree of Change, Frequency of Delivery, and Context of Project
Traditional Life Cycle can be Incremental (ex. Rolling out a system to many branches)
Agile Life Cycles are usually Incremental, Iterative, and Adaptive
Each Life Cycle has its Strengths, weaknesses, benefits and drawbacks

## Slide 5
Agile Scope
Management
Lecture
04

## Slide 6
Agile Projects have Variable Scope
Lecture
04
Traditional project management treats changing requirements as a sign of failure in upfront planning
Variable Scope through welcoming change helps to immediately and incrementally:
Incorporate Learning and Feedback
Create better Products

## Slide 7: Top Agile Scope Management Characteristics (1/2)
# | Agile Scope Management
1 | Only High-Level requirements are gathered at the beginning of the project
2 | Requirements are gathered and refined throughout the project as knowledge about customer needs and project realities increase
3 | Change is viewed as a positive way to improve the product and Late changes in the project are the most valuable ones
4 | The Product Owner is the responsible person for the project scope (not the Scrum Master), determines the value and priority of new requirements and adds those requirements to the product backlog.
5 | There is no need for Change Management processes, as it is already an inherent part of Agile processes

## Slide 8: Top Agile Scope Management Characteristics (2/2)
# | Agile Scope Management
6 | New features with high priority don’t necessarily cause budget or schedule slip; they simply push out the lowest-priority features
7 | The most valuable features first to guarantee their inclusion and to ship those features as soon as possible
8 | Less valuable features might never be created, which may be acceptable to the business and the customer after they have the highest-value features
9 | Scope is assessed and there is an opportunity to include new requirements or modify/remove existing with every Iteration/Sprint

## Slide 9: Who can suggest a new product feature on an agile project?
Feedback from
User Community
Groups or people who are given an opportunity to preview the product
Managers and
Business Stakeholders
Can see new market opportunities or threats and gave insight into long-term organizational strategies and changes
Scrum Master
and/or Team
They are learning more about the product every day, and are closest to the working product
Product Owner
determines the value and priority of new requirements and adds those requirements to the product backlog.
Product Owner
who often knows the most about the product and the stakeholders’ needs

## Slide 10
Managing Scope Changes
Lecture
04
Assess
Estimate
Prioritize
Product Owner
Product Owner
Product Owner, Scrum Master
and/or Team
Assess if the new requirement should be part of the product, release, or sprint
Estimate the Effort for the new requirement
Prioritize against other requirements in the product backlog and add to the product backlog, in order of priority.

## Slide 11: Adding a New Requirement to the Backlog
Product (or Sprint) Backlog
User Story
User Story
User Story
User Story
User Story
User Story
User Story
User Story
User Story
User Story
New
Project Budget
Removed Story

## Slide 12
Documents used in Agile Scope Management
Lecture
04
Document | Used for
Vision Statement | High level product requirements and used to judge whether new features belong in the scope for the current project.
Product Roadmap | Product scope is part of the product roadmap. Requirements are at a feature level Good for business conversations about what it means to realize the product vision Provides visual communication of the features included in the project
Product Backlog | Detailed requirements in form of features or User Stories Contains all scope features, and new added features New, high-priority features push lower-priority features down on the product backlog
Sprint Backlog | Contains the user stories that are in scope for the current sprint After the sprint-planning meeting, only the team can modify the sprint backlog.

## Slide 13
Agile Time
Management
Lecture
04

## Slide 14
Agile Projects usually have Fixed Deadlines
Lecture
04
Traditional Project Management
Agile Project
Management
Determine Requirements
Determine Schedule based on how much time to achieve those Requirement
Fixed Deadline
Create as much features as you can before the deadline

## Slide 15: Factors Impacting Agile Project Duration
Assigned Deadline
Budget Considerations
Features Completed
Agile projects may have a specified fixed date for business reasons. Ex. Getting a product to market before a shopping season
Project works to create as much functionality as possible from project start until the end date.
Agile projects may have budget considerations that affect the amount of time a project will last.
Ex., a $1,600,000 budget, for a project that costs $20,000 a week, the project will be able to last 80 weeks to create and release as much functionality as possible.
Agile projects may last only until enough functionality is complete.
Project teams may run sprints until the requirements with the highest value are complete, and then determine that the lower-value requirements aren’t necessary.

## Slide 16: Top Agile Time Management Characteristics
# | Agile Time Management
1 | Planning is done on strategic (product roadmap, release plan, product backlog) and tactical (iteration/sprint planning, daily meetings) levels
2 | Team assess and reassess how much work they can complete in a given time frame (using velocity)
3 | Team works in iterations/sprints and complete all the work on the highest-priority, highest-value requirements first, thus reducing overall project risk
4 | Iterations/sprints are timeboxed (fixed duration), unfinished work is returned to product backlog for rescheduling
5 | Execution starts early (as soon as iteration/sprint 1) with minimal planning and design time, usually resulting in shorter project time compared to traditional approach

## Slide 17
Agile Planning
Lecture
04
Size
Estimate
Plan
The Agile Team
How big is the effort?
How quickly can we get it done?
When can we do it?
The Agile Team
The Agile Team
The Agile team is responsible for all steps of Planning (not the Product Owner nor the Scrum Master

## Slide 18
Decomposing Requirements
Lecture
04
Epic
User Story 1
User story 2
Feature 2
User Story 1
Feature 1
User story 2
Epics: the highest level of work, represent large, complex goals that will take multiple sprints to complete. Epics are typically broken down into smaller, more manageable features.
Features: smaller pieces of work that can be completed in a single sprint. Typically, specific and measurable, and they should deliver value to the customer.
User stories: the smallest unit of work in agile. They are written from the perspective of the user, and they describe a specific task or function that the user wants to be able to perform.

## Slide 19
Estimating using Story Points
Lecture
04
Typically use a simple scale to estimate story points, such as 1, 2, 3, 5, 8, 13, 20, 40, 100.
Story points is a measure of EFFORT NOT TIME
Story points size is determined by the team
Story points are all inclusive (include time for documentation and testing
Used to:
    Estimate the effort required to complete a sprint.
    Prioritize stories in the product backlog.
    Track their progress during a sprint.
    Identify bottlenecks and improve their velocity over time
Story Points:
An abstract unit of measure that represents the effort, complexity, and risk required to complete a user story. Story points are relative

## Slide 20
Estimating using T-Shirt Sizing
Lecture
04
# of Story Points
User Stories

## Slide 21
Calculating Velocity
Lecture
04
At the beginning of the project, the team estimates initial velocity
Velocity is then calculated based on actual performance
Velocity is measured in story points
= 11.6
Iteration/ Sprint # | Actual Velocity (in story points)
1 | 10
2 | 12
3 | 13
Current Velocity | 11.6

## Slide 22
Iteration/Sprint Planning using Velocity
Lecture
04
Example:
    After 4 Iterations/Sprints, Current Velocity = 15
# | Description | Estimate (in Story Points)
1 | User Story 10 | 3
2 | User Story 11 | 7
3 | User Story 12 | 5
4 | User Story 13 | 4
5 | User Story 14 | 6
Product Backlog after
Iteration/Sprint 4
# | Description | Estimate (in Story Points)
1 | User Story 10 | 3
2 | User Story 11 | 7
3 | User Story 12 | 5
 | Total Story Points | 15
Iteration/Sprint 5 Backlog
Velocity
Threshold

## Slide 23
Documents used in Agile Time Management
Lecture
04
Document | Used for
Product Roadmap | A prioritized visual view of the high-level requirements and schedule Usually does not have specific dates, it will have general date ranges for groups of functionality and will allow an initial timeline for bringing the product to market
Product Backlog | A complete list of all currently known product requirements The requirements in product backlog will have estimated story points. After knowing team’s velocity, a realistic project end date can be determined using the total number of story points in the product backlog
Release Plan | Contains a release schedule for requirements Has a target release date for a specific goal (epic or set of requirements) Team plan and work on only one release at a time.
Sprint Backlog | Contains the user stories that are in scope for the current sprint During your sprint-planning meeting, you convert estimated story points to time. In Sprint Retrospective, calculate velocity for that sprint based on finished story points

## Slide 24
Agile Cost
Management
Lecture
04

## Slide 25: Top Agile Cost Management Characteristics
# | Agile Cost Management
1 | Project schedule, not scope, has the biggest effect on cost
2 | Projects may have a fixed cost and a fixed amount of time, and then complete requirements that fit into those costs and timeframe
3 | Product owners often secure project funding after the product roadmap stage is complete, not before project start as in traditional approach
4 | Project teams can replace lower-priority requirements with new, equivalently sized high-priority requirements with no effect on time or cost
5 | Project teams can release working, revenue-generating functionality early that can spend on future project activities, creating a self-funding project.

## Slide 26
Agile Project Costs
Fixed Costs
Per Sprint Costs
Fixed Costs (doesn’t change with changing the # of Sprints in a project)
Usually, One-time costs
Can be paid upfront or along the project
Examples:
  Hardware Costs
  Software Licenses
  Training Costs
  Hosting Costs
Variable costs (depends on # of Sprints in a project)
Examples:
  Salaries
  Rent
  Utilities
  Calculated per Sprint (for ex. 2 weeks), i.e. monthly salaries divided by 2 sprints/month

## Slide 27
Creating an Initial Cost Estimate
Lecture
04
Estimate total # of Sprints from Product Roadmap, Release Plan
    Determine:
      Fixed Costs
      Per Sprint Costs

## Slide 28
Managing a Fixed Budget
Lecture
04
Fixed Budget is when you are given a fixed amount for the project
Determine Per Sprint Cost
Determine Fixed Cost
Determine how many Sprints you can do in the project:

## Slide 29
How to Reduce Project Costs
Lecture
04
Increase Velocity, as increased productivity will reduce # of sprints needed
Eliminate low priority features will reduce # of sprints needed

## Slide 30
Example on Managing Fixed Budget
Lecture
04
A project with a fixed budget of $ 200,000
The Project has:
Fixed Cost = $ 0
Per Sprint Costs = $20,000

## Slide 31
Example on Managing Fixed Budget
Lecture
04
The Project is estimated to have 200 story points
If new requirements are added making the project estimate to be 300 story points
What is the Velocity you need to reach to finish the project on budget

## Slide 32
Self-Funding Projects
Lecture
04
A project that generates sufficient revenue to spend on further project activities
    Self –Funding projects enables continuous adding of features that deliver value
Sprint # | Cost | Cumulative Project Cost | Deliverable
Fixed Cost | $ 40,000 | $ 40,000 | 
1 | $10,000 | $ 50,000 | Release 1
2 | $ 10,000 | $ 60,000 | Release 2
3 | $ 10,000 | $ 70,000 | Release 3
4 | $ 10,000 | $ 80,000 | Release 4
5 | $ 10,000 | $ 90,000 | Release 5
Expenses
Release # | Income | Cumulative Income
- | - | -
Release 1 | $ 20,000 | $ 20,000
Release 2 | $ 20,000 | $ 40,000
Release 3 | $ 20,000 | $ 60,000
Release 4 | $ 20,000 | $ 80,000
Release 5 | $ 20,000 | $ 100,000
Income
Self-Funding Point

## Slide 33
Documents used in Agile Cost Management
Lecture
04
Document | Used for
Product Vision | Will usually have the project budget when it is fixed for the project
Product Roadmap | A prioritized visual view of the high-level requirements and schedule Use it to estimate total # of sprints to calculate cost estimates
Release Plan | Contains a release schedule for requirements Use it to estimate total # of sprints to calculate cost estimates
Product Backlog | A complete list of all currently known product requirements Use it to prioritize and eliminate features when managing costs

## Slide 34
Wrapping-Up
Lecture
04

## Slide 35
Key Project Management Events/Ceremonies
Lecture
04
Planning Session
Iteration/Sprint Planning
Iteration/Sprint Retrospective
Product Roadmap
Release Planning
Initial Product Backlog
Initial Cost Estimate
User Stories
Story Mapping
User Stories
Sprint Backlog
Product Backlog Refinement
Product Roadmap Refinement
Release Planning Refinement

## Slide 36: Strengths and Weaknesses of Agile Approach
Strengths
Simplicity
Flexibility
Fast delivery and decision making
Focus on Value Adding
Weaknesses
Lack of Clarity at beginning
Less predictability
Requires motivated and committed team
Difficulties managing large projects

## Slide 37
Key Points
Lecture
04
Agile approach does project scope, time, and cost in a simpler manner
Typically, in Agile projects Scope is variable, Time and Cost are fixed
Estimating time is based on story points for each user story, and Velocity determines how many stories should be put in a Sprint
Cost estimating is based on cost/sprint and velocity
All management activities are done in planning session, iteration planning, and iteration retrospective

## Slide 38
Preparation for discussion panel:
Watch the video:
“Learn Agile Estimating”
Question: what are the benefits of using Agile estimating techniques?
For Discussion Panel
Lecture
04

## Slide 39
Before next lecture:
For Next Lecture, Watch the Video ” Agile Methodologies - XP | Kanban | Lean | Scrum | Crystal | DSDM | ASD”
To study/review the whole course Watch the video:
“Agile Management | Google Project Management Certificate”
For Next Lecture
Lecture
04

## Slide 40
Thank You