## ورقة1
student name |  | Alaa A. AlFarran | student Id | 2021206091
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | OPPORTUNITIES | Hydro Elecric Power plant | high | high | compatible effect of water and generation of power | new opportunities that will enhance the country in many levels such, economical and investments | Fedral Gov.
2 | OPPORTUNITIES | New Career Options in Future | high | high | exceprt and nature of work will require labor, there is a high oppurtunity for labor to learn more on this field and by time they become the experts - thus will also will help in cost redcution | Schools and instituts offer new line and matrials for public | Project manager
3 | THREATS | Transportation and Road network | high | high | week road network connectivity due to the natural geographic of Tanzania | using lower cost paths for logistics supplies | Project manager
4 | THREATS | Civil and nearby Political disputes | high | high | wars can be easlily ignighted on different levels, civil due to the existnce of a huge independt trips and diversity of the region or external as the dominant trait of the area is "go to war first we can fix this later" | pre-agreement among the most powerful tribes. Project location should be away from dispute zones and war areas | Fedral Gov
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low