## ورقة1
student name |  |  | student Id
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | OPPORTUNITIES | job vacancies | high | moderate | reduce unemployment | hiring Saudi people to increase saudization rate and decrease unemployment people rate | HR Manager | Riyadh Metro
2 | OPPORTUNITIES | City Environment | high | moderate | increasing of green land | Reforestation and design of green spaces around the stations | High Commission for the Development of Riyadh | Riyadh Metro
3 | THREATS | stumbling while driving | high | high | traffic jam | The project manager must communicate with the traffic to organize and coordinate traffic during the implementation of the project | Project Manager | Riyadh Metro
4 | THREATS | massive funds need | high | high | Increasing of Ticket Price | Governments must cooperate with each other to support and implement this project to link countries with each other. | countries governments | Virgin Hyperloop
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low