## ورقة1
Student name |  | Mohammad A Barnawy | Student Id | 2021206150
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | The danger of smoking and the absence of guiding and control panels | High | High | Ignition or Fire | Distributing appropriate extinguishers on the site and raising awareness | Safety manager and site supervisor | Binladin Group
2 | THREATS | Lack of attention, poor supervision and inspection, and lack of permits | High | High | Loss of life and property | Increasing oversight and not working without permits | Safety manager and the GM | Binladin Group
3 | OPPORTUNITIES | Installing surveillance cameras and spreading awareness | Moderate | Moderate | Lack of supervision leads to wastage of money | Controlling security oversight on sites and ensuring the safety of everyone and not taking or stealing items | Security Manegent | Binladin Group
4 | OPPORTUNITIES | Staff development courses | High | Moderate | The importance of maintaining employee development | Inclusion of certified and empowered trainers to provide information to employees | Personnel Affairs and Training Department | Binladin Group
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low