## Slide 1
Advanced Project Management
PMG 506
Lecture 5
The Project in the Organizational
Structure

## Slide 2
Lecture
05
The Project in the Organizational Structure

## Slide 3
Lecture
05
The Project in the Organizational Structure
A firm may organize by major subsidiaries at the top level; the subsidiaries organize by product groups; and the product groups organize into customer divisions. These, in turn, may be split into functional departments that are further broken down into production process sections, which are set up as three-shift operating units.
.

## Slide 4
Lecture
05
The Project in the Organizational Structure
In the past decade or so, a new kind of organization structure has appeared in growing numbers—the project organization, “enterprise project management” also known as “managing organizations by projects,” the “project-oriented firm,” and other names. Such organizations have been described as applying “project management practices and tools across an enterprise”. A great many firms, both software and non-software firms alike, have now adopted a system whereby their traditional business is carried out in the traditional way, but anything that represents a change is carried out as a project.

## Slide 6
Lecture
05
The Project in the Organizational Structure
There are many reasons for the rapid growth of project-oriented organizations, but most of them can be subsumed in four general areas:
First, speed and market responsiveness have become absolute requirements for successful competition.

## Slide 7
Lecture
05
The Project in the Organizational Structure
Second, the development of new products, processes, or services regularly requires inputs from diverse areas of specialized knowledge.
Third, the rapid expansion of technological possibilities in almost every area of enterprise tends to destabilize the structure of organizations.
Finally, majority of senior managers rarely feel much confidence in their understanding of and control over a great many of the activities going on in their organizations.

## Slide 8
Lecture
05
5.1 THE PROJECT AS PART OF THE FUNCTIONAL ORGANIZATION
As one alternative for giving the project a “home,” we can make it a part of one of the functional divisions of the firm.
For functionally organized projects, the project is assigned to the functional unit that has the most interest in ensuring its success or can be most helpful in implementing it.

## Slide 9
Lecture
05
5.1 THE PROJECT AS PART OF THE FUNCTIONAL ORGANIZATION
The major advantages are:
There is maximum flexibility in the use of staff.
Individual experts can be utilized by many different projects.
Specialists in the division can be grouped to share knowledge and experience.

## Slide 10
Lecture
05
5.1 THE PROJECT AS PART OF THE FUNCTIONAL ORGANIZATION
4- The functional division also serves as a base of technological continuity when individuals choose to leave the project, and even the parent firm.
5- The functional division contains the normal path of advancement for individuals whose expertise is in the functional area.

## Slide 11
Lecture
05
5.1 THE PROJECT AS PART OF THE FUNCTIONAL ORGANIZATION
The disadvantages are:
The client is not the focus of activity and concern.
The functional division tends to be oriented toward the activities particular to its function.
No individual is given full responsibility for the project.

## Slide 12
Lecture
05
5.1 THE PROJECT AS PART OF THE FUNCTIONAL ORGANIZATION
4- Lack of coordinated effort tend to make response to client needs slow and arduous.
5- There is a tendency to suboptimize the project.
6- The motivation of people assigned to the project tends to be weak.
7- Organizational arrangement does not facilitate a holistic approach to the project.

## Slide 13
Lecture
05
5.2 PURE PROJECT ORGANIZATION
The project is separated from the rest of the parent system. It becomes a self-contained unit with its own technical staff, its own administration, tied to the parent firm by the tenuous strands of periodic progress reports and oversight.
The advantages are:
The project manager has full line authority over the project.
All members of the project work force are directly responsible to the PM.

## Slide 14
Lecture
05
5.2 PURE PROJECT ORGANIZATION
3- Shortened communication lines result in faster communications with fewer failures.
4- The pure project organization can maintain a more or less permanent cadre of experts who develop considerable skill in specific technologies.
5. The project team that has a strong and separate identity of its own tends to develop a
high level of commitment from its members.
6. The ability to make swift decisions is greatly enhanced.
7. Unity of command exists.

## Slide 15
Lecture
05
5.2 PURE PROJECT ORGANIZATION
Pure project organizations are structurally simple and flexible, which makes them relatively easy to understand and to implement.
The organizational structure tends to support a holistic approach to the project.

## Slide 16
Lecture
05
5.2 PURE PROJECT ORGANIZATION
Disadvantages:
When the parent organization takes on several projects, it is common for each one to be fully staffed. This can lead to considerable duplication of effort in every area from clerical staff to the most sophisticated technological support units.
People with critical technical skills may be hired by the project when they are available rather than when they are needed and they tend to be maintained on the project longer than needed, “just in case.”

## Slide 18
Lecture
05
5.2 PURE PROJECT ORGANIZATION
Disadvantages 1 and 2 combine to make this way of organizing projects very expensive.
Individuals engaged with projects develop considerable depth in the technology of
the project, but they tend to fall behind in other areas of their technical expertise.
In the environment of the project, administrative corner cutting is common and easily
justified as a response to the client or to technical exigency.
5. Team members form strong attachments to the project and to each other. A disease
known as projectitis develops.
A strong we–they divisiveness grows, distorting the relationships between project
team members and their counterparts in the parent organization.
Worry about “life after the project ends.”

## Slide 19
Lecture
05
5.3 THE MATRIX ORGANIZATION
The matrix organization is a combination of the two “Project and Functional”. It is a pure project organization overlaid on the functional divisions of the parent firm.
Depending on which of the two extremes (functional or pure project) it most resembles. The “project” or “strong” matrix most resembles the pure project organization. The “functional” or “weak” matrix most resembles the functional form of organization. Finally, the “balanced” matrix lies in between the other two.

## Slide 20
Lecture
05
5.3 THE MATRIX ORGANIZATION
In practice, there is an almost infinite variety of organizational forms between the extremes, and the primary difference between these forms has to do with the relative power/decision authority of the project manager and the functional manager.
Housing the project in a functional organization was simply too constraining. Setting it up as a pure project was workable but expensive because of the need to duplicate expensive technical talent when more than one project was involved. The matrix organization, which allows the PM to draw temporarily on the technological expertise and assistance of all relevant functions, was a way out of the dilemma.

## Slide 22
Lecture
05
5.3 THE MATRIX ORGANIZATION
The advantages are:
The point of emphasis, the PM.
The project has reasonable access to the entire reservoir of technology in all functional divisions.
There is less anxiety about what happens when the project is completed than is typical of the pure project organization.
Response to client needs is as rapid as in the pure project case, and the matrix organization is just as flexible.

## Slide 23
Lecture
05
5.3 THE MATRIX ORGANIZATION
5- Consistency with the policies, practices, and procedures of the parent firm tends to be preserved.
6- Allows a better companywide balance of resources to achieve the several different time/cost/performance targets of the individual projects.
7- There is a great deal of flexibility in how the project is organized so that it can be adapted to a wide variety of projects and is always subject to the needs, abilities, and desires of the parent organization.

## Slide 24
Lecture
05
5.3 THE MATRIX ORGANIZATION
The disadvantages are:
When doubt exists about who is in charge, the work of the project suffers. If the project is successful and highly visible, doubt about who is in charge can foster political infighting for the credit and glory. If the project is a failure, political infighting will be even more brutal to avoid blame.
The movement of resources from project to another to satisfy the several schedules may foster political infighting among the several PMs, all of whom tend to be more interested in ensuring success for their individual projects than in helping the total system optimize organization wide goals.

## Slide 25
Lecture
05
5.3 THE MATRIX ORGANIZATION
3- The projects, having individual identities, resist death. Even in matrix organizations, projectitis is still a serious disease.
4- The ability of the PM to negotiate anything from resources to technical assistance to delivery dates is a key contributor to project success. Success is doubtful for a PM without strong negotiating skills
5-Matrix management “is a charming form of management, full of variety and disorder.”

## Slide 26
Lecture
05
5.3 THE MATRIX ORGANIZATION
Include a few members in the team who already know each other, and make sure one in every six or seven are “boundary spanners” with lots of outside contacts.
Create an online resource for team members to learn about each other (especially how they prefer to work), collaborate, brainstorm, and draw inspiration.
Encourage frequent communication, but not social gatherings (which will occur at more natural times anyway).
Divide the project work into geographically independent modules as much as possible so progress in one location isn’t hampered by delays in other locations.

## Slide 27
Lecture
05
Virtual Projects:
Virtual projects are those in which work on the project team crosses time, space, organizational, or cultural boundaries. Thus, a virtual team may work in different time periods, be geographically dispersed, work in different organizations, or work in different cultures. In all cases, the rise of virtual projects has been facilitated by the use of the Internet and other communication technologies.
Gratton (2007) offers some rules for success:
Only use virtual teams for projects that are challenging and interesting. But also be sure the project is meaningful to the company as well as the team.
Solicit volunteers as much as possible—they’ll be more enthusiastic and dedicated to the success of the project.

## Slide 28
Lecture
05
5.5 CHOOSING AN ORGANIZATIONAL FORM
The choice is determined by the situation, but even so is partly intuitive. There are few accepted principles of design, and no step-by-step procedures that give detailed instructions for determining what kind of structure is needed and how it can be built. All we can do is consider the nature of the potential project, the characteristics of the various organizational options, the advantages and disadvantages of each, the cultural preferences of the parent organization, and make the best compromise we can.

## Slide 29
Lecture
05
5.5 CHOOSING AN ORGANIZATIONAL FORM
In general, the functional form is apt to be the organizational form of choice for projects where the major focus must be on the in-depth application of a technology rather than, for example, on minimizing cost, meeting a specific schedule, or achieving speedy response to change. Also, the functional form is preferred for projects that will require large capital investments in equipment or buildings of a type normally used by the function.

## Slide 30
Lecture
05
5.5 CHOOSING AN ORGANIZATIONAL FORM
If the firm engages in a large number of similar projects (e.g., construction projects), the pure project form of organization is preferred. The same form would generally be used for one-time, highly specific, unique tasks that require careful control and are not appropriate for a single functional area—the development of a new product line, for instance.

## Slide 31
Lecture
05
5.5 CHOOSING AN ORGANIZATIONAL FORM
When the project requires the integration of inputs from several functional areas and involves reasonably sophisticated technology, but does not require all the technical specialists to work for the project on a full-time basis, the matrix organization is the only satisfactory solution. This is particularly true when several such projects must share technical experts. But matrix organizations are complex and present a difficult challenge for the PM.
By understanding the various structures, their advantages and disadvantages, a firm can select the organizational structure that seems to offer the most effective and efficient choice.

## Slide 32
Lecture
05
5.5 CHOOSING AN ORGANIZATIONAL FORM
The criteria for the selection of a project organization:
Define the project with a statement of the objective(s) that identifies the major outcomes desired.
Determine the key tasks associated with each objective and locate the units in the parent organization that serve as functional “homes” for these types of tasks.
Arrange the key tasks by sequence and decompose them into work packages.
Determine which organizational units are required to carry out the work packages and which units will work particularly closely with which others.

## Slide 33
Lecture
05
5.5 CHOOSING AN ORGANIZATIONAL FORM
5-List any special characteristics or assumptions associated with the project—for example, level of technology needed, probable length and size of the project, any potential problems with the individuals who may be assigned to the work, possible political problems between different functions involved, and anything else that seems relevant, including the parent firm’s previous experiences with different ways of organizing projects.
6-In light of the above, and with full cognizance of the pros and cons associated with each structural form, choose a structure.

## Slide 34
Lecture
05
5.6 TWO SPECIAL CASES—RISK MANAGEMENT AND THE PROJECT OFFICE
Two problems remain:
First, in the entire history of projects from the beginning of time until the day after tomorrow, no project has ever been completed precisely as it was planned. Uncertainty is a way of life for PMs and their projects.

## Slide 35
Lecture
05
5.6 TWO SPECIAL CASES—RISK MANAGEMENT AND THE PROJECT OFFICE
Second, the successful execution of a project is a complex managerial task and requires the use of planning, budgeting, scheduling, and control tools with which the neophyte PM may not be completely familiar. In addition, there are contractual, administrative, and reporting duties that must be performed in accord with the law, the wishes of the client, and the rules of the organizational home of the project
Dealing with uncertainties has come to be known as risk management. In order to deal with the managerial and administrative issues in a way that meets the parent organization’s rules for management and administration, many firms have created the project management office (PMO).

## Slide 36
Lecture
05
5.6 TWO SPECIAL CASES—RISK MANAGEMENT AND THE PROJECT OFFICE
Risk Management
Is “the systematic process of identifying, analyzing, and responding to project risk”
Consist of seven subprocesses:
Risk Management Planning—deciding how to approach and plan the risk management activities for a project.
Risk Identification—determining which risks might affect the project and documenting their characteristics.

## Slide 37
Lecture
05
5.6 TWO SPECIAL CASES—RISK MANAGEMENT AND THE PROJECT OFFICE
3-Qualitative Risk Analysis—performing a qualitative analysis of risks and conditions to prioritize their impacts on project objectives.
4-Quantitative Risk Analysis—estimating the probability and consequences of risks and estimating the implications for project objectives.
5-Risk Response Planning—developing procedures and techniques to enhance opportunities and reduce threats to the project’s objectives.

## Slide 38
Lecture
05
5.6 TWO SPECIAL CASES—RISK MANAGEMENT AND THE PROJECT OFFICE
Risk Monitoring and Control—monitoring residual risks, identifying new risks, executing risk reduction plans, and evaluating their effectiveness throughout the project life cycle.
Create and Maintain a Risk Management Data Bank—a permanent record of identified risks, methods used to mitigate or resolve them, and the results of all risk management activities.

## Slide 39
Lecture
05
5.6 TWO SPECIAL CASES—RISK MANAGEMENT AND THE PROJECT OFFICE
The risk management system should maintain an up-to-date data bank that includes, but is not restricted to, the following:
identification of all environments that may impact on the project
identification of all assumptions made in the preliminary project plan that may be the source of risk for the project
all risks identified by the risk management group, complete with their estimated impacts on the project and estimates of their probability of occurring

## Slide 40
Lecture
05
5.6 TWO SPECIAL CASES—RISK MANAGEMENT AND THE PROJECT OFFICE
Risk Management
a complete list of all “categories” and “key words” used to categorize risks, assumptions, and environments so that all risk management groups can access past work done on risk management
the details of all qualitative and quantitative estimates made on risks, on states of the project’s environment, or on project assumptions, complete with a brief description of the methods used to make such estimates
minutes of all group meetings including all actions the group developed to deal with or mitigate each specific risk, including the decision to ignore a risk
the actual outcomes of estimated risks and the results of actions taken to mitigate risk

## Slide 41
Lecture
05
The Project Management Office
There are a variety of forms of PMOs to serve a variety of needs. Some of these are at a low level in the organization and others report to the highest levels. The best PMOs have some common characteristics, including the traits of being run like the best businesses (a business plan, focused, emphasis on results), enjoying strong executive support, being future-oriented learning organizations, and offering the best project leadership in the organization.

## Slide 42
Lecture
05
Purposes of the Project Management Office
Establish project administration procedures for selecting, initializing and planning, budgeting, and scheduling projects as well as to serve as a repository for reports on the performance of the planning, budgeting, scheduling, and resource allocation processes.
Established and maintained standard project processes (practices and procedures), offered consulting help on projects, training and mentoring services, performed project tracking and portfolio management. Maintained a stable of project managers

## Slide 43
Lecture
05
Tasks of the Project Management Office
• Establish and enforce good project management processes such as procedures for
bidding, risk analysis, project selection, progress reports, executing contracts, and
selecting software
• Assess and improve the organization’s project management maturity
• Develop and improve an enterprise project management system
• Offer training in project management and help project managers become certified
• Identify, develop, and mentor project managers and maintain a stable of competent
candidates

## Slide 44
Lecture
05
Tasks of the Project Management Office
• Offer consulting services to the organization’s project managers
• Help project managers with administrative details such as status reports
• Establish a process for estimation and evaluation of risk
• Determine if a new project is a good “fit” for the changing organization
• Identify downstream changes (market, organization) and their impacts on current
projects: Are the projects still relevant? Is there a need to change any project’s scope?
Are there any cost effects on the projects?
• Review and manage the organization’s project risk portfolio, including limiting the
number of active projects at any given time and identifying and reining in runaway
projects as well as managing potential disasters

## Slide 45
Lecture
05
Tasks of the Project Management Office
• Conduct project reviews and audits, particularly early in each project’s life cycle, and
report project progress relative to the organization’s goals
• Maintain and store project archives
• Establish a project resource database and manage the resource pool
• Serve as a champion to pursue project management excellence in the organization and
encourage discussion on the value of individual projects in the firm
• Serve as a “home” for project managers to communicate with each other and with
PMO staff
• Collect and disseminate information and techniques reported in project evaluations
that can improve project management practices
• Assist in project termination

## Slide 46
Lecture
05
Forms of Project Management Office
L1 PMO that represents an information center, reporting on project progress and assessing the organization’s project maturity
L2 PMO may establish project management procedures and practices, promulgate lessons learned from prior projects, create a database for risk analysis, help project managers with administrative and managerial matters, and possibly even offer basic training in project management
L3 PMO may establish a resource database and monitor interproject dependencies, manage the project portfolio to ensure attainment of the organization’s goals, audit and prioritize individual projects, and generally establish an enterprise project management system.

## Slide 47
Lecture
05
Forms of Project Management Office
L1 PMO that represents an information center, reporting on project progress and assessing the organization’s project maturity
L2 PMO may establish project management procedures and practices, promulgate lessons learned from prior projects, create a database for risk analysis, help project managers with administrative and managerial matters, and possibly even offer basic training in project management
L3 PMO may establish a resource database and monitor interproject dependencies, manage the project portfolio to ensure attainment of the organization’s goals, audit and prioritize individual projects, and generally establish an enterprise project management system.

## Slide 48
Lecture
05
5.7 THE PROJECT TEAM
In addition to the PM, the following key team members might be needed, plus an appropriate number of systems architects, engineers, testers, clerks, and the like.
• Systems Architect is in charge of the basic product design and development and is responsible for functional analysis, specifications, drawings, cost estimates, and documentation.
• Development Engineer his task is the efficient production of the product
or process the project engineer has designed, including responsibility for manufacturing engineering, design and production of code, unit testing, production scheduling,
and other production tasks.
• Test Engineer is responsible for the installation, testing, and support of the product (process) once its engineering is complete.
Contract Administrator is in charge of all official paperwork, keeping track of standards compliance, customer changes, billings, questions, complaints, legal aspects, costs, and negotiation of other matters related to the contract authorizing the project.

## Slide 49
Lecture
05
5.7 THE PROJECT TEAM
• Project Controller keeps daily account of budgets, cost variances, labor charges, project supplies, capital equipment status, etc. Makes regular reports and keeps in close touch with both the PM and the company controller.
• Support Services Manager is in charge of product support, subcontractors, data processing, purchasing, contract negotiation, and general management support functions.
Of these top project people, it is most important that the systems architect and the project controller report directly to the PM. This facilitates control over two of the main goals of the project: technical performance and budget.

## Slide 50
Thank You