## Slide 1
Prepared by Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Agile Project Management
Lecture 06
PMG 622
Master of Project Management

## Slide 2
Working with a Framework (Scrum)
Lecture 6
PMG 622
Agile Project Management
Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Prepared by

## Slide 3
Learning Objectives
Apply Scrum framework on a sample project to:
  Develop a Product Vision, Product Roadmap, and Release Plan
  Develop an Initial Product Backlog
  Perform Story Mapping
  Perform Sprint Planning including story splitting, user story development and estimation
  Use Kanban Boards to manage Sprints
  Develop Burndown Charts and calculate Velocity
  Perform Sprint Review and Retrospective
  Perform Backlog Refinement
Chapter
06

## Slide 4: Note for Lecture Exam: Please Review Lecture 2 and Lecture 4 for definitions of terms used in this Lecture.

## Slide 5
Key Points from Previous Lecture
Chapter
06
Scrum is the most widely used Agile Methodology
Some Agile methodologies as Lean, Crystal has no prescribed processes
Most methodologies started in the Software Industry, except for Lean and Kanban who came from manufacturing
You can mix tools from different methodologies together in your Agile project

## Slide 6
There are many different Agile Frameworks
Chapter
06
Scrum
XP
ScrumBan
DSDM
Kanban
Crystal
FDD
Lean
Agile

## Slide 7
The Project: Develop a Calculator Application
Chapter
05
Arithmetic Functions
Algebraic Equations
Trigonometric Functions
Statistical Functions
Works on multiple platforms:
  Web
  IOS
  Android

## Slide 8
Scrum Process
Chapter
06

## Slide 9
Product Vision, Roadmap, and Release Plan
Chapter
06

## Slide 10: Product Vision
Describes the purpose of a Product, the intention with which the Product is being created, what problems it tries to resolve, and what it aims to achieve for customers
VISION: The BEST Calculator APP for Students.
Target Group:
High School Students
University Students
Post-Graduate Students
Needs:
User Friendly
Performs Arithmetic, Algebra, Trigonometry, and statistics Functions
Product:
Multi-Platform (Web, IOS, Android)
Supports Touchscreens
Uses AI to predict input
Business Goals:
Gain 1 M subscribers by end of year 1
Generate 1 M USD/month by end of Month 6

## Slide 11: Product Roadmap
A visual depiction of the product releases and the main components that will be included in each release.
Usually, developed by Product Owner to decide on business priorities with some input from the team.
User Interface
Coding
Design
Alg.
Arith.
Stat.
Web
Trig.
Alg.
Arith.
Stat.
IOS
Trig.
4 Months
3 Months
2 Months
2 Weeks
Alg.
Arith.
Stat.
Android
Trig.
Start

## Slide 12: Product Release Plan
User Interface
Coding
Design
Alg.
Arith.
Stat.
Web
Trig.
Alg.
Arith.
Stat.
IOS
Trig.
Alg.
Arith.
Stat.
Android
Trig.
Rel. #1
Rel. #2
Rel. #3
Rel. #4
Rel. #5
Rel. #6
Rel. #7
Rel. #8
Rel. 10#
Rel. #11
Rel. #12
Rel. #9
4 Months
3 Months
2 Months
2 Weeks
Start

## Slide 13
User Stories, Story Mapping, Product Backlog, and Estimating
Chapter
06

## Slide 14: EPIC vs. Features vs. User Stories
Epics are big chunks of work that has multiple features
Features are divided into multiple User Stories (Story Splitting)
Big User-Stories can be further divided into multiple User Stories (Story splitting)
Product backlog can be developed on feature or user story levels
Epics
Features
User Stories
IOS Application
Web Application
Android Application
User Interface
Coding
Design
Algebraic
Arithmetic
Statistics
Trigonometric
Subtract
Add
Divide
Multiply

## Slide 15: Writing User Stories
A short description of a feature or requirement from the user perspective.
Written on a card in the following format:
User Story #1 (ADD)
As a User
I want to Add 2 Numbers
So that I can perform basic Arithmetic Function
Acceptance Criteria
The user should be able to enter two numbers into the calculator.
The user should be able to select the addition operation.
The calculator should display the sum of the two numbers.
User Story #2 (Subtract)
As a User
I want to Subtract 2 Numbers
So that I can perform basic Arithmetic Function
Acceptance Criteria
The user should be able to enter two numbers into the calculator.
The user should be able to select the subtract operation.
The calculator should display the difference of the two numbers.
User Story #20 (Sin)
As a User
I want to be able to calculate the Sin of a Number
So that I can perform trigonometric Function
Acceptance Criteria
The user should be able to enter a number into the calculator.
The user should be able to select the sin operation.
The calculator should display the sine of a number.

## Slide 16: Story Mapping
Story mapping consists of ordering user stories along two independent dimensions.
Horizontal axis user activities are put roughly in the order in which the user would perform the task.
Vertical axis, user stories are ordered by priority and/or increasing sophistication of the implementation.
Csc
Variance
Radical
Cos
Subtract
Median
Rational
Tan
Multiply
Mode
Exponentials
Sec
Divide
Std. Deviation
Logarithmic
Sin
Add
Mean
Polynomial
Coding
Design
Cot
Count
Arithmetic
Trigonometric
Algebraic
Statistical
Web
IOS
Android
Repeat User Stories
Repeat User Stories
User Interface

## Slide 17: Initial Product Backlog
A prioritized list of all the work that needs to be done to complete the project as new features, changes to existing features, fixes, process changes, or other activities.
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
1 | Design |  | Open | 
2 | Coding |  | Open | 
3 | Add |  | Open | 
4 | Subtract |  | Open | 
5 | Multiply |  | Open | 
6 | Divide |  | Open | 
7 | Sin |  | Open | 
8 | Cos |  | Open | 
9 | Tan |  | Open | 
10 | Sec |  | Open | 
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
11 | Csc |  | Open | 
12 | Cot |  | Open | 
13 | Polynomial |  | Open | 
14 | Rational |  | Open | 
15 | Exponential |  | Open | 
16 | Logarithmic |  | Open | 
17 | Radical |  | Open | 
18 | Mean |  | Open | 
19 | Median |  | Open | 
20 | Mode |  | Open | 
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
21 | Std. Deviation |  | Open | 
22 | Variance |  | Open | 
23 | Count |  | Open | 
24 |  |  |  | 
25 |  |  |  | 
26 |  |  |  | 
27 |  |  |  | 
28 |  |  |  | 
29 |  |  |  | 
40 |  |  |  | 
 |  |  | Total | 

## Slide 18: Estimating
# of Story Points
User Stories
Design: 15
Coding: 20
Add: 3
Subtract: 3
Multiply: 3
Divide: 3
Sin: 5
Cos: 5
Tan: 5
Sec: 5
Csc: 5
Cot: 5
Median: 8
Mode: 8
Mean: 13
StdDev: 13
Var: 13
Poly: 20
Rat.: 20
Rad: 15
Count: 3
Log.: 40
Exp.: 50

## Slide 19: Update Product Backlog with User Story estimates
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
1 | Design |  | Open | 15
2 | Coding |  | Open | 20
3 | Add |  | Open | 3
4 | Subtract |  | Open | 3
5 | Multiply |  | Open | 3
6 | Divide |  | Open | 3
7 | Sin |  | Open | 5
8 | Cos |  | Open | 5
9 | Tan |  | Open | 5
10 | Sec |  | Open | 5
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
11 | Csc |  | Open | 5
12 | Cot |  | Open | 5
13 | Polynomial |  | Open | 20
14 | Rational |  | Open | 20
15 | Exponential |  | Open | 50
16 | Logarithmic |  | Open | 40
17 | Radical |  | Open | 15
18 | Mean |  | Open | 13
19 | Median |  | Open | 8
20 | Mode |  |  | 8
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
21 | Std. Deviation |  | Open | 20
22 | Variance |  | Open | 13
23 | Count |  | Open | 3
24 |  |  |  | 
25 |  |  |  | 
26 |  |  |  | 
27 |  |  |  | 
28 |  |  |  | 
29 |  |  |  | 
40 |  |  |  | 
 |  |  | Total | 287
End of Project Day 1

## Slide 20
Sprint Management
Chapter
06

## Slide 21: Sprint 1: Sprint Planning Meeting
Team decided sprints will be 2 weeks long
Initially we assume velocity, let’s say velocity = 35 Story points/Sprint
All team meets at Sprint 1 Day 1 to perfrorm Sprint Planning
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
1 | Design |  | Open | 15
2 | Coding |  | Open | 20
3 | Add |  | Open | 3
4 | Subtract |  | Open | 3
5 | Multiply |  | Open | 3
6 | Divide |  | Open | 3
7 | Sin |  | Open | 5
8 | Cos |  | Open | 5
9 | Tan |  | Open | 5
10 | Sec |  | Open | 5
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
1 | Design |  | Open | 15
2 | Coding |  | Open | 20
 |  |  | TOTAL | 35
We start taking stories in priority order from the Product Backlog to Sprint Backlog
We stop when the Sprint has user stories around the velocity threshold
Product Backlog
Sprint 1 Backlog

## Slide 22: Sprint Management - Sprint 1 Kanban Board
Chapter
Sprint Backlog
Development
(2)
Testing
(1)
Coding: 20
User Interface Design: 15
Done
Day: 1
Day: 5
Day: 10
Day: 14
Story Splitting: Team may find these stories too big and split them into multiple user stories within the Sprint

## Slide 23: Sprint 1 Review
Team makes a demo
Customer
Finished Work:
User Interface Design and Coding
Feedback:
Customer wants to change Shape of Buttons
Customer wants Two memory Buttons to store results so that they can be recalled in other calculations

## Slide 24: Sprint 1 Retrospective
Scrum Master facilitates a review of the sprint
Team identifies what went good and what can be improved
Feedback:
Development Team can take 3 tasks instead of 2 at the same time
Testing team can take 2 tasks instead of 1 at the same time
Velocity 35 is too much, we need to limit it to 30

## Slide 25: Product Backlog Refinement After Sprint 1
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
1 | Design | 1 | CLOSED | 15
2 | Coding | 1 | CLOSED | 20
3 | Add |  | Open | 3
4 | Subtract |  | Open | 3
5 | Multiply |  | Open | 3
6 | Divide |  | Open | 3
7 | Change Button Shape |  | Open | 5
8 | Add 2 Memory Buttons |  | Open | 15
9 | Sin |  | Open | 5
10 | Cos |  | Open | 5
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
11 | Tan |  | Open | 5
12 | Sec |  | Open | 5
13 | Csc |  | Open | 5
14 | Cot |  | Open | 5
15 | Polynomial |  | Open | 20
16 | Rational |  | Open | 20
17 | Exponential |  | Open | 50
18 | Logarithmic |  | Open | 40
19 | Radical |  | Open | 15
20 | Mean |  | Open | 13
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
21 | Median |  | Open | 8
22 | Mode |  | Open | 8
23 | Std. Deviation |  | Open | 20
24 | Variance |  | Open | 13
25 | Count |  | Open | 3
26 |  |  |  | 
27 |  |  |  | 
28 |  |  |  | 
29 |  |  |  | 
40 |  |  |  | 
 |  |  | Total | 307

## Slide 26: Writing New User Stories
User Story #24 (Change Buttone Shape)
As a User
I want to have squared with round corners button shape
So that It is easier on the eye
Acceptance Criteria
Button should be a square with round corners.
User Story #25 (Memory Functions)
As a User
I want to save up to two results
So that I can use them in other calculations later Function
Acceptance Criteria
The user should be able to save result by pressing one of two memory buttons.
The user should be able to retrieve result by pressing on the memory button again

## Slide 27: Sprint 2: Sprint Planning Meeting
As per team feedback Velocity = 30 Story points/Sprint
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
1 | Design |  | Closed | 15
2 | Coding |  | Closed | 20
3 | Add |  | Open | 3
4 | Subtract |  | Open | 3
5 | Multiply |  | Open | 3
6 | Divide |  | Open | 3
7 | Change Button Shape |  | Open | 5
8 | Add 2 Memory Buttons |  | Open | 15
9 | Sin |  | Open | 5
10 | Cos |  | Open | 5
11 | Tan |  | Open | 5
12 | Sec |  | Open | 5
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
1 | Add |  | Open | 3
2 | Subtract |  | Open | 4
3 | Multiply |  | Open | 3
4 | Divide |  | Open | 3
5 | Change Button Shape |  | Open | 3
6 | Add 2 Memory Functions |  | Open | 15
 |  |  | TOTAL | 32
Product Backlog
Sprint 2 Backlog

## Slide 28: Sprint Management - Sprint 2 Kanban Board
Chapter
Sprint Backlog
Development
(3)
Testing
(2)
Subtract: 3
Add: 3
Done
Day: 1
Day: 5
Day: 10
Day: 14
Multiply: 3
Divide: 3
Change Button Shape: 5
Add 2 Memory Functions: 15

## Slide 29: Daily Scrum Meeting (10-15 min.)
Led by Scrum Master, asks every team member:
  What did you do yesterday?
  Where are you blocked?
  What are you going to do today?
Decision-Making and Problem Solving to ensure Sprint finishes its objectives

## Slide 30: Sprint Burndown Chart vs. Project Burndown Chart
Chart: Sprint 2 Burndown Chart
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
User Stories Remiaing | 32 | 32 | 32 | 29 | 29 | 26 | 26 | 26 | 23 | 23 | 20 | 20 | 15 | 15 | 0
Chart: Project Burndown Chart
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3
User Stories Remiaing | 307 | 272 | 240

## Slide 31: Sprint 2 Review
Team makes a demo
Customer
Finished Work:
Arithmetic functions, button Shape,
Feedback:
Proceed with Release 1
Customer Identified minor bug to be resolved that won’t impact release 1.
Customer wants to add more than two numbers in one calculation

## Slide 32: Sprint 2 Retrospective
Scrum Master facilitates a review of the sprint
Team identifies what went good and what can be improved
Feedback:
Calculated average velocity (35+32/2) = 33.5
Decided to develop user manual (should be added as a user story)

## Slide 33: Product Backlog Refinement After Sprint 2
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
1 | Design | 1 | CLOSED | 15
2 | Coding | 1 | CLOSED | 20
3 | Add | 2 | CLOSED | 3
4 | Subtract | 2 | CLOSED | 3
5 | Multiply | 2 | CLOSED | 3
6 | Divide | 2 | CLOSED | 3
7 | Change Button Shape | 2 | CLOSED | 5
8 | Add 2 Memory Buttons | 2 | CLOSED | 15
9 | Sin |  | Open | 5
10 | Cos |  | Open | 5
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
11 | Tan |  | Open | 5
12 | Sec |  | Open | 5
13 | Csc |  | Open | 5
14 | Cot |  | Open | 5
15 | Solve Minor Bug |  | Open | 3
16 | Polynomial |  | Open | 20
17 | Rational |  | Open | 20
18 | Exponential |  | Open | 50
19 | Logarithmic |  | Open | 40
20 | Add more than 2 numbers |  | Open | 8
Id | Backlog Item | Assigned to Sprint | Status | Size (In Story Points)
21 | Radical |  | Open | 15
22 | Mean |  | Open | 13
23 | Median |  | Open | 8
24 | Mode |  | Open | 8
25 | Std. Deviation |  | Open | 20
26 | Variance |  | Open | 13
27 | Count |  | Open | 3
28 | User Manual |  | Open | 13
29 |  |  |  | 
40 |  |  |  | 
 |  |  | Total | 331

## Slide 34
Key Points
Chapter
06
Review Lectures 2 and 4 for definitions for this lecture exam
Scrum has very minimal documents (product Backlog, Sprint Backlog) and uses many visual tools (Kanban Board, Burndown Charts, Velocity Charts)
Scrum is characterized by fast problem solving and decision making in sprint planning, daily scrum, sprint review and retrospective
As all Agile frameworks, Scrum is flexible and adapts to changing needs
Scrum involves the customer and focus on delivering high priority, high value features first

## Slide 35
Preparation for discussion panel:
Check this link for several case studies on applying Scrum Methodologies.
“Examples of Scrum Case Studies”
Watch the video for a case study on applying Scrum “Scrum in 20 mins... (with examples)”
Watch the video for Scrum Workflow “Scrum Master Tutorial | Google Project Management Certificate”
For Discussion Panel
Chapter
06
www.midocean.ae

## Slide 36
Preparation for discussion panel:
Watch the video for Scrum Example “8 Practical Examples & Case Study | Scrum Master Course | Speedily Tech”
Read the following Scrum Case Study “How to Develop an Agile Project Proposal with Use Case Analysis: A Local Grocery Store Example”
For Discussion Panel
Chapter
06
www.midocean.ae

## Slide 37
Before next lecture:
Hybrid Life Cycles:
Read the Article
“Hybrid Life Cycles”
For Next Lecture
Chapter
06
www.midocean.ae

## Slide 38
Thank You