## Slide 1
PROJECT MONITORING
Lecture 03
PMG333
Dr. Bassel alhassan
Prepared by
COST& TIME MONITORING 1

## Slide 2
1 - 2
Lecture
03
Lecture Contents

## Slide 3
1 - 3
Lecture
03

## Slide 4
1 - 4
Lecture
03
ISO 21508:2018

## Slide 5
1 - 5
Lecture
03
Scope & Objective of ISO 21508:2018

## Slide 6
1 - 6
Lecture
03
EVM Implementation Steps

## Slide 7
1 - 7
Lecture
03
EVM Implementation Steps

## Slide 8
1 - 8
Lecture
03
Step 1: Decompose the Project Scope

## Slide 9
1 - 9
Lecture
03
General Concepts of WBS

## Slide 10
1 - 10
Lecture
03
Characteristics of an Effective WBS

## Slide 11
1 - 11
Lecture
03
Work Packages & WBS Dictionary

## Slide 12
1 - 12
Lecture
03
Practical Example 1

## Slide 13
1 - 13
Lecture
03
Practical Example 2: Smartphone App Development

## Slide 14
1 - 14
Lecture
03
Takeaways

## Slide 15
1 - 15
Lecture
03
Step2: Assign Responsibility

## Slide 16
1 - 16
Lecture
03
Guidelines for Assigning Responsibility

## Slide 17
1 - 17
Lecture
03
Practical Example: Software Development

## Slide 18
1 - 18
Lecture
03
Step 3: Schedule Work

## Slide 19
1 - 19
Lecture
03
Guidelines for Developing Project Schedules

## Slide 20
1 - 20
Lecture
03
Practical Example: Retaining Wall Construction

## Slide 21
1 - 21
Lecture
03
Step 4: Develop Time- Phased Budget

## Slide 22
1 - 22
Lecture
03
Practical Example: Time- Phased Budget for Retaining Wall

## Slide 23
1 - 23
Lecture
03
Step 5: Assign Performance Metrics

## Slide 24
1 - 24
Lecture
03
Guidelines for Performance Metrics

## Slide 25
1 - 25
Lecture
03
Practical Example: Assigning Metrics to Retaining Wall

## Slide 26
1 - 26
Lecture
03
Step 6: Establish PMB (Performance Management Baselines )

## Slide 27
1 - 27
Lecture
03
Step 6: Establish PMB (Performance Management Baselines )

## Slide 28
1 - 28
Lecture
03
Step 7: Authorize & Execute Work (ISO 21508:2018)

## Slide 29
1 - 29
Lecture
03
Step 8: Data Collection (ISO 21508:2018)

## Slide 30
1 - 30
Lecture
03
Step 9: Performance Analysis (EVM)

## Slide 31
فا
1 - 31
Lecture
03
The requirement is to deliver ten tables in ten days at a cost of one thousand per table
As a result, one table is delivered daily at a unit cost of one thousand
Review of Previous Session

## Slide 32
1 - 32
Lecture
03
By day four, the planned completion is four tables at a cost of 4,000
However, upon reviewing the actual progress on day four, three tables had been completed at a cost of 5,000
Review of Previous Session

## Slide 33
1 - 33
Lecture
03
Actual Cost of Work Performed (ACWP)= 5000
Budget Cost of Work Schedule (BCWS)= 4000
Budget Cost of Work Performed (BCWP)=3000
Review of Previous Session

## Slide 34
1 - 34
Lecture
03
Schedule Variance (SV)
= BCWP-BCWS
= 3000-4000=-1000<0
behind schedule
Lecture
Cost Variance (CV)
= BCWP-ACWP
= 3000- 5000= -2000<0
over budget
Review of Previous Session

## Slide 35
1 - 35
Lecture
03
Schedule performance Index (SPI)
= BCWP / BCWS
= 3000/4000=0.75<1
behind schedule
Cost performance Index (CPI)
= BCWP / ACWP
= 3000/5000=0.6<1
over budget
Review of Previous Session

## Slide 36
1 - 36
Lecture
03
Estimated Final Time (EFT)
EFT = TAC / SPI
EFT= 10/0.75= 13.33= 14
Review of Previous Session

## Slide 37
1 - 37
Lecture
03
EAC = BAC / CPI
        EAC = 10000 / 0.6=16667(Estimated at complete )
Estimated Cost At Completion (EAC)
  EAC = ACWP+ Original Remaining Budget
Review of Previous Session

## Slide 38
1 - 38
Lecture
03
ETC = EAC – ACWP(estimated to complete )
ETC= 16667-5000=11667
Estimated To Complete (ETC)
VAC = BAC – EAC
VAC= 10000-16667=-6667
Variance At Completion (VAC)
Variance At Completion= Budget Cost At Completion - Estimated Cost At Completion
Review of Previous Session

## Slide 39
1 - 39
Lecture
03
EVM Graph
In the adjacent graph, we observe that the curve representing the Earned Value (in red) lies below the curve representing the Planned Value. Consequently, the Schedule Variance (SV) value will be negative, indicating that the project is behind schedule."
"Similarly, we observe that the curve representing the Earned Value (in red) lies below the curve representing the Actual Cost. Consequently, the Cost Variance (CV) value will be negative, which means the project is over budget based on the current performance

## Slide 40
1 - 40
Lecture
03
In the adjacent chart, we observe that until week six, the curve representing the Earned Value was higher than the curve representing the Planned Value. Therefore, the schedule variance was positive, and the project was ahead of schedule. However, starting from the sixth week, the Earned Value curve fell below the Planned Value. Consequently, schedule performance declined, the schedule variance became negative, and a delay relative to the planned value will occur."
"Throughout the entire duration of the project, the curve representing the Earned Value remained higher than the curve representing the Actual Cost. Therefore, the cost performance is excellent, and the project will be completed under the contractual budget
EVM Graph

## Slide 41
Thank You