## Slide 1
Prepared by Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Agile Project
Management
Lecture 2
PMG 622
Master of Project Management

## Slide 2
Understanding Agile Approaches: General Practices and Terminology
Lecture 2
PMG 622
Agile Project Management
Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Prepared by

## Slide 3
Learning Objectives
Understand agile practices and processes
Learn agile terminology
Lecture
02

## Slide 4
Key Points from Previous Lecture
Lecture
02
Agile project management started slowly since 1970s but gained momentum from 2001 onwards after publishing “The Agile Manifesto”
The Agile Manifesto has 4 values and 12 principles that focus on flexibility, faster delivery, and customer collaboration
There are many frameworks and methodologies following Agile Values and Principles (ex. Scrum, Kanban, XP)
Uncertainty in projects comes from lack of requirements clarity and/or solution clarity
We select the suitable approach to manage the project based on degree of change and frequency of delivery

## Slide 5
Agile Practices and
Processes
Lecture
02

## Slide 6: Agile Practices and Processes
VISION
PRODUCT BACKLOG
ITERATION/SPRINT BACKLOG
INCREMENT/
RELEASE
PRODUCT
DAILY
MEETING
ITERATION/SPRINT 1-4 WEEKS
ITERATION/
SPRINT
REVIEW
ITERATION/SPRINT PLANNING
x 3-4
Initiation/Planning
Execution
Closing
PRODUCT Roadmap

## Slide 7: What happens in a typical Agile Project?
Initiating
Planning
Executing
Closing
01
02
03
04
Product Vision, Project Charter
Project Kick-Off
Product Roadmap, Release Planning
Product Backlog
Story Mapping, User Story Definition, Acceptance Criteria Definition
Story Mapping, User Story Definition, Acceptance Criteria Definition
For every Iteration: Iteration Planning, Iteration Backlog, Daily Meeting, Iteration Retrospective, Iteration Grooming
Effort Estimation, Risk Management, Burn charts, velocity charts
For each Iteration: Deployment
Product Releases
Project Closing

## Slide 8
All Agile frameworks share main practices/processes with some differences in process and terminology used
Lecture
02
Scrum
XP
ScrumBan
DSDM
AUP
Kanban
Crystal
FDD
Lean
Agile

## Slide 9: The Agile Subway Roadmap
Retrieved from https://www.agilealliance.org/agile101/subway-map-to-agile-practices/

## Slide 10
Agile Terminology
Lecture
02

## Slide 11: Main Roles in an Agile Team
Product Owner
Agile Coach/ Scrum Master/ Project Manager
Team
Responsible for the Product Backlog, Prioritization, and for maximizing the value delivered to customers, usually comes from the business side
Responsible for helping the team follow the Agile (Scrum, Kanban, Lean, XP,…) framework, removes roadblocks, facilitates communication, and helps the team to continuously improve.
Responsible for developing the product. The Team is a cross-functional team that includes specialists

## Slide 12: Agile Teams are usually between 5-9 people
Easier Communication
Faster Decision-Making
Higher Accountability
An Agile Team should be small enough to be fed by two large pizzas 

## Slide 13
Colocation
“Team Room”
Ideally the whole team, including the product owner or domain expert, has the use of a dedicated space for the duration of the project, set apart from other groups’ activities.
This space is furnished with the various amenities that the team may need: workstations, whiteboards and flipcharts, wall space to display task boards, project plans or other charts, and so on.

## Slide 14
“Scrum” Framework
Name inspired by the Rugby Scrum where the team works closely together to move the ball forward (achieve a common goal or move the project forward)

## Slide 15: Kanban Board
BACKLOG
1
ANALYSIS
4
DEVELOPMENT
5
TESTING & QA
3
DEPLOYMENT
2
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Description Text
Doing
Done
Doing
Done
“A visual board that shows the current state of work items.”

## Slide 16: Product Vision
Describes the purpose of a Product, the intention with which the Product is being created, what problems it tries to resolve, and what it aims to achieve for customers
The first thing to be done in the project (at initiating) and has the same purpose as Business Case in traditional project management.

## Slide 17: Features and Value
Improved Quality
Increased Revenue
Decreased Risk
Increased Satisfaction
Feature: A new or improved functionality that is delivered to customers
Value: Anything that delivers a benefit to the customer

## Slide 18: Product Roadmap
“A visual depiction of the product releases and the main components that will be included in each release.”
Serves as a communication tool that provides project stakeholders with a quick view of the primary release points and intended functionality that will be delivered.

## Slide 19: Product Roadmap Example

## Slide 20: Product Backlog
“A prioritized list of all the work that needs to be done to complete the project as new features, changes to existing features, fixes, process changes, or other activities.”
The single source for things that a team works on. i.e. nothing gets done that isn’t on the product backlog

## Slide 21: Product Backlog
“Product Backlog can be modified (add new, delete, modify) in a process called Backlog Grooming/Refinement performed after each Iteration’s Retrospective.
Can be comparable WBS Work Packages in Traditional Project Management

## Slide 22: Product Backlog Example
 | Id | Backlog Item | Assigned to Sprint | Priority | Status | Working Hours | 
 |  |  |  |  |  | Estimate | Actual
 | 1 | Feature 1 | 1 | Must Have | Open | 8 | 2
 | 2 | Feature 2 | 1 | Must Have | Open | 4 | 3
 | 3 | Feature 3 | 1 | Must Have | Open | 4 | 0
 | 4 | Feature 4 | 2 | Should Have | Open | 2 | 0
 | 5 | Feature 5 | 2 | Should Have | Open | 2 | 0
 | 6 | Feature 6 | 2 | Should Have | Open | 4 | 0
 | 7 | Feature 7 | - | Nice to Have | Closed | 2 | 0
 | 8 | Feature 8 | - | Nice to Have | Closed |  | 
 | 9 | Feature 9 | - | Nice to Have | Closed |  | 
 |  |  |  |  | TOTAL | 27 | 5

## Slide 23: User Story
“A short description of a feature or requirement from the user perspective.
A user story involves roughly 1 to 3 days’ worth of work or “4 to 40 hours’ worth of work
Help align team priorities with the needs of the business.
Written on a card in the following format:
“As a <Role>, I want <Functionality>, so that <Business beneﬁt >."

## Slide 24: User Story Examples

## Slide 25: Definition of “Done” / Acceptance Criteria
A set of criteria that must be met in order for a work item to be considered truly complete.

## Slide 26: Story Mapping
Story mapping consists of ordering user stories along two independent dimensions.
Help understand “User Journey”
Along the horizontal axis user activities are put roughly in the order in which the user would perform the task.
Down the vertical axis, user stories are ordered by priority and/or increasing sophistication of the implementation.

## Slide 27: Iteration/Sprint
www.midocean.ae
A short period of time (usually one to two weeks) during which the team works on a specific set of tasks from the backlog.
Iteration/Sprint Backlog: A list of all the work that the team plans to complete during a sprint. Is a subset from the Product backlog items usually written in user stories format.
 | Id | Backlog Item | Assigned To | Due | Status | Working Hours | 
 |  |  |  |  |  | Estimate | Actual
 | 1 | Task Description 1 | None | Day 10 | Open | 8 | 2
 | 2 | Task Description 2 | TB | Day 8 | Open | 4 | 3
 | 3 | Task Description 3 | NB | Day 12 | Open | 4 | 0
 | 4 | Task Description 4 | - | - | Open | 2 | 0
 | 5 | Task Description 5 | ST | - | Open | 2 | 0
 | 6 | Task Description 6 | - | - | Open | 4 | 0
 | 7 | Task Description 7 | - | - | Closed | 2 | 0
 | 8 | Task Description 8 | - | - | Closed |  | 
 | 9 | Task Description 9 | - | - | Closed |  | 
 |  |  |  |  | TOTAL | 27 | 5

## Slide 28: Daily Meeting / Daily Scrum / Standup Meeting
A short (5 to 15 minutes), daily meeting where the team discusses their progress, plans, and any roadblocks they are facing.
Sometimes held while the team standing to make sure it stays short.
Uses Kanban Boards and follows a structure

## Slide 29: Burn Down Chart
A measure of progress depicted as a visual chart that shows how much work remains to be done on a project or iteration.
Burndown Chart
Chart: 
| 1 | 5 | 10 | 15
Datenreihe 1 | 1850 | 1720 | 1644 | 1533 | 1523 | 1500 | 1234 | 1200 | 1156 | 800 | 754 | 652 | 550 | 544 | 520 | 450 | 300 | 200 | 0
Projected Finish

## Slide 30: Iteration/Sprint Retrospective
A meeting, held at the end of each iteration/sprint, where the team reflects on their work and identifies areas for improvement.
Product Backlog Refinement/Grooming may be done as a result of the Retrospective

## Slide 31: Velocity
A measure of the amount of work a team can complete in a period of time.
Measured in story points, a unit of measurement that represents the effort required to complete a user story.

## Slide 32: Increment/Release
An Agile increment or release is a working version of a product that is delivered to customers at the end of a sprint or iteration.
Typically, a small, but complete and usable, piece of the product that includes new features and functionality.
Benefits:
Customer is satisfied and can use the product
Learn from mistakes and adapt to change quickly
Test product in market and reduce risk of not meeting requirements

## Slide 33
Key Points
Lecture
02
Agile Frameworks and Methodologies have similar processes that might differ in naming and terminology
The role of the Project Manager in Agile is a coach, facilitator, and enabler for success.
The Customer (Product Owner) is represented in the team
In Initiating and Planning an Agile project, we do Product Vision, Product Roadmap, and Product Backlog
In Executing an Agile project, we do Iteration Planning, User Stories, Iteration Backlog, and Iteration Retrospective, work is monitored through Daily Meetings, Burn Down, and Velocity Charts

## Slide 34
Preparation for discussion panel:
“Watch the Video:
“Introduction to Scrum – 7 minutes”
Question for Discussion: As a project manager moving from Traditional to Agile project management:
  Which practices you can adapt to easily and which practices you will find difficultly in adapting to?
For Discussion Panel
Lecture
02

## Slide 35
Before next lecture:
Familiarize yourself with Agile Terminology :
https://www.agilealliance.org/agile101/subway-map-to-agile-practices/
Click on the circle beside the term to get its definition
Try to test your knowledge before clicking on them
For Next Lecture
Lecture
02

## Slide 36
Thank You