## Slide 1
Prepared by Dr. Tarek Mohamed
Project Procurement and
Supply Chain
Lecture 9
PMG 433

## Slide 2
Contract Management in Projects
Lecture 9
PMG 433
Dr. Tarek Mohamed
Prepared by

## Slide 3
Course Agenda
Explain the role of contract management in project success.
Understand the project contract life cycle.
Differentiate between contract administration and procurement.
Identify contract risks.
Select appropriate contract types.
Manage supplier performance.
Handle contract changes and claims.
Close contracts successfully.
Apply PMBOK practices to real projects.
Chapter

## Slide 4: Contract management
Contract Management is
The systematic process of planning, creating, executing, monitoring, controlling,
modifying, and closing contracts to ensure that both parties fulfill their
contractual obligations.
Effective contract management requires balancing legal compliance, commercial objectives, and supplier relationships.
It ensures
Scope is delivered
Cost is controlled
Time commitments are met
Risks are minimized
Legal obligations are fulfilled

## Slide 5: Contract management
PMBOK Perspective
Within PMBOK, contract management belongs to
Project Procurement Management
Processes include
Plan Procurement Management
Conduct Procurements
Control Procurements
Contract Management mainly occurs during Control Procurements

## Slide 6: Contract management
Why is Contract Management Important?
Poor contract management causes
Cost overruns
Project delays
Claims
Litigation
Supplier disputes
Poor quality
Financial losses

## Slide 7: Contract management
Real Example
Construction Project
Contract Value
$100 Million
Because of poor contract administration
Variation orders not documented
Delayed approvals
Supplier disputes
Final Cost
$127 Million
Lessons
Contract management protects project profitability.

## Slide 8: Contract management
Procurement Management in PMBOK
Project Procurement Management includes
Planning
↓
Selecting suppliers
↓
Awarding contracts
↓
Managing contracts
↓
Closing contracts

## Slide 9: Procurement vs Contract Management
Procurement | Contract Management
Selecting suppliers | Managing suppliers
Tendering | Contract execution
Bid evaluation | Performance monitoring
Contract award | Claims management
Supplier selection | Contract closeout

## Slide 10: Typical Contract Life Cycle
Need Identification
↓
Planning
↓
Tendering
↓
Evaluation
↓
Negotiation
↓
Contract Award
↓
Execution
↓
Monitoring
↓
Changes
↓
Closeout

## Slide 11: Contract Types (PMBOK)
A. Fixed Price Contracts
Seller assumes most risk.
Examples
Lump Sum Contract
Firm Fixed Price (FFP)
Fixed Price Incentive Fee (FPIF)
Fixed Price with Economic Price Adjustment (FPEPA)
Advantages
Cost certainty
Easier budgeting
Disadvantages
Less flexibility
Supplier may increase price to cover risks
Example
Building office furniture
Fixed Price
$200,000

## Slide 12: Real-World examples of Fixed Price Contracts
1. Boeing – Aircraft Component Manufacturing
Project
Manufacturing aircraft landing gear components.
Contract Type
Firm Fixed Price (FFP)
Example
Boeing contracts a supplier to manufacture 100 landing gear assemblies for the Boeing 737.
Contract Price: $25 million
Delivery: 12 months
Technical specifications are fully defined.
If steel prices increase or production costs rise, the supplier absorbs the additional costs.

## Slide 13: Real-World examples of Fixed Price Contracts
Why Fixed Price?
Specifications are well defined.
Quantities are known.
Manufacturing process is standardized.
Buyer wants cost certainty.
Risk Allocation
Buyer Risk → Low
Seller Risk → High

## Slide 14: Real-World examples of Fixed Price Contracts
2. Toyota – Automotive Parts Procurement
Project
Supplying brake systems for a new vehicle model.
Contract
Firm Fixed Price
Toyota signs a contract with a brake supplier to deliver
50,000 brake systems
Price: $180 per unit
Even if the supplier's manufacturing costs increase, Toyota pays the agreed
contract price.
Lesson
Stable production environments favor fixed-price contracts.

## Slide 15: Contract Types (PMBOK)
B. Cost Reimbursable Contracts
Buyer pays actual costs plus fee.
Examples
Cost Plus Fixed Fee
Cost Plus Incentive Fee
Cost Plus Award Fee
Advantages
Flexible
Suitable for R&D
Disadvantages
Buyer bears higher financial risk

## Slide 16: Real-World examples of Cost Reimbursable Contracts
Pfizer – Pharmaceutical Research
Project
Development of a new vaccine or medicine.
Research organizations and biotechnology partners often work under cost-reimbursable research agreements because:
Clinical trials may expand.
Research duration is uncertain.
Additional laboratory work may be required.
Actual research costs are reimbursed while performance incentives may be
added for meeting milestones.

## Slide 17: Real-World examples of Cost Reimbursable Contracts
Boeing – New Aircraft Development
During the research and development phase of new military aircraft programs,
Boeing may work under cost-reimbursable contracts funded by government agencies.
Why?
Prototype design evolves continuously.
Engineering solutions are unknown.
Testing frequently results in redesign.
Once production begins, contracts often shift to Fixed Price.

## Slide 18: Contract Types (PMBOK)
C. Time and Material Contracts
Combination of
Fixed labor rates
Variable quantities
Suitable for
Consulting
Maintenance
IT Support
Time and Material contracts are suitable when project scope is expected to evolve and are not clearly defined.

## Slide 19: Real-World examples of Time and Material Contracts
IBM – Cloud Migration Projects
Project
Migrating a company's data center to IBM Cloud.
Contract
Time and Material
IBM charges for:
Cloud engineers
Cybersecurity specialists
Database administrators
Travel expenses (if applicable)
Because migration complexity becomes clear only after work begins, billing is
based on actual effort.

## Slide 20: Real-World examples of Time and Material Contracts
Microsoft – IT Consulting Services
Project
Implementation of Microsoft Dynamics 365 ERP.
Contract Type
Time and Material (T&M)
Example
A manufacturing company hires Accenture to implement Microsoft Dynamics 365.
ERP Consultant: $180/hour
Technical Architect: $250/hour
Actual software configuration hours billed monthly.
Since user requirements evolve during implementation, the total number of
consulting hours cannot be accurately estimated in advance.

## Slide 21: Contract Risk Allocation
Contract Type | Buyer Risk | Seller Risk
Fixed Price | Low | High
Cost Reimbursable | High | Low
Time & Material | Medium | Medium

## Slide 22: Contract Administration
Contract administration ensures
Supplier complies with contract
Deliverables meet specifications
Milestones are achieved
Payments are justified
Risks are managed

## Slide 23: Major Activities
Monitor
Scope
Schedule
Cost
Quality
Safety
Compliance
Approve
Deliverables
Invoices
Variations
Document
Meetings
Correspondence
Performance reports

## Slide 24: Key Documents
Contract Agreement
Statement of Work (SOW) (describes the work that the contractor must perform)
Technical Specifications
Schedule
Performance Reports
Inspection Reports
Payment Certificates
Change Orders

## Slide 25: Monitoring Supplier Performance
Key Performance Indicators (KPIs)
Cost Variance
Schedule Variance
Delivery Performance
Quality Performance
Defect Rate
Response Time
Safety Performance
Customer Satisfaction
Example
Supplier promised
95% On-Time Delivery
Actual
81%

## Slide 26: Performance Reviews
Methods include
Site inspections
Audits
Progress meetings
Performance scorecards
Earned Value Management (EVM)
Dashboards

## Slide 27: Contract Changes
Changes occur because of
Design modifications
Scope increase
New regulations
Client requests
Unforeseen conditions
PMBOK Principle
Every contract change must follow the formal change control process, supported by
formal documentation .

## Slide 28: Change Order Process
Request
↓
Evaluation
↓
Impact Analysis
↓
Approval
↓
Contract Amendment
↓
Implementation

## Slide 29: Claims Management
Claim
A formal request seeking compensation for additional cost, time, or other
contractual relief due to events affecting contract performance.
Common Claims
Delay claims
Acceleration claims
Scope changes
Design errors
Force majeure
Payment disputes

## Slide 30: Claims Process
Identify
↓
Notify
↓
Document
↓
Evaluate
↓
Negotiate
↓
Resolve

## Slide 31: Contract Risks
Examples
Supplier Bankruptcy
Late Delivery
Inflation
Currency Changes
Political Risks
Natural Disasters
Technology Failure
Poor Quality
Contract risks should be identified and managed throughout the project life cycle.

## Slide 32: Risk Responses
Avoid
Mitigate
Transfer
Accept
Example
Performance Bond
Transfers financial risk.

## Slide 33: Contract Disputes
Reasons
Ambiguous specifications
Late payments
Scope changes
Poor communication
Schedule delays
Poor documentation

## Slide 34: Dispute Resolution Methods
Negotiation
↓
Mediation
↓
Arbitration
↓
Litigation

## Slide 35: Contract Closeout
Activities
Confirm work completion
Final inspection
Final payment
Release retention
Archive documents
Lessons learned
Supplier evaluation
Formal acceptance
Contract closure certificate

## Slide 36: PMBOK Contract Closure Checklist
✔ Deliverables accepted
✔ Final invoice approved
✔ Claims resolved
✔ Warranties documented
✔ Records archived
✔ Supplier evaluation completed
✔ Contract officially closed

## Slide 37: Real Company Examples
Construction
Large EPC contractors use milestone-based payments tied to engineer-certified progress, with change orders managed through formal approval workflows.
Information Technology
Software implementation projects often use Time & Material contracts during requirements discovery and Fixed Price contracts for well-defined deployment phases.

## Slide 38: Real Company Examples
Oil & Gas
Offshore engineering projects rely on rigorous claims management because weather delays, design revisions, and regulatory changes can significantly affect cost and schedule.
Manufacturing
Automotive manufacturers monitor supplier performance using KPIs such as on-time delivery, defect rates (PPM), responsiveness, and corrective action effectiveness.

## Slide 39: Common Causes of Contract Failure
Poorly defined scope
Weak specifications
Inadequate risk allocation
Poor communication
Lack of documentation
Ineffective change management
Delayed decisions
Failure to monitor supplier performance
Unrealistic schedules Inadequate stakeholder involvement

## Slide 40: Best Practices (PMBOK-Aligned)
Develop clear Statements of Work (SOWs).
Select the contract type that best aligns with project risk.
Define measurable KPIs before contract award.
Monitor performance continuously.
Use formal change control for all contract modifications.
Keep complete and accurate contract records.
Address issues and claims promptly.
Conduct regular supplier performance reviews.
Capture lessons learned at contract closeout.

## Slide 41
Summary of Learning Objectives
Explain the role of contract management in project success.
Understand the project contract life cycle.
Differentiate between contract administration and procurement.
Identify contract risks.
Select appropriate contract types.
Manage supplier performance.
Handle contract changes and claims.
Close contracts successfully.
Apply PMBOK practices to real projects.
Chapter

## Slide 42
Morris, P. W., & Pinto, J. K. (Eds.). (2007). The Wiley guide to project technology, supply chain, and procurement management (Vol. 4). John Wiley & Sons.
Schwalbe, K. (2015). Information technology project management. Cengage Learning.
Baily, P., Farmer, D., Crocker, B., Jessop, D., & Jones, D. (2008). Procurement principles and management. Pearson Education.
Supply Chain Council
PMBOK® Guide (Project Management Body of Knowledge),
Essential Reference

## Slide 43
Thank You