## Slide 1: PMG 622 Agile Project Management LECTURE 02: LIFE CYCLE SELECTION
Everyone’s Smart University
دكتور مهندس استشاري ادارة المشروعات
Eng. Dr. Akram Mustafa Suliman Ali,
PhD. AU, BEng. & MSc. AAST, CEng CMarEng MIMarEST, PE, PMP®,
ASQ CSSBB, ISO Lead Auditor, NDT Level II,

## Slide 2: Quick Review

## Slide 3: Agile Manifesto and Mindset
ميثاق
بيان الاسلوب الرشيق
عقلية الاسلوب الرشيق

## Slide 4: Agile Manifesto / “4 Values”
We are uncovering better ways of developing software by doing it and helping others do it.
Through this work we have come to value:
That is, while there is value in the items on the right, we value the items on the left more.
Working products
Customer collaboration
Over
Over
Process and tools
Comprehensive documentation
Responding to change
Individuals and interactions
Contract negotiation
Following and plan
Over
Over

## Slide 5: BEING AGILE VS DOING AGILE

## Slide 6: PMIAA
Program Management Improvement and Accountability Act
Forum Topic: Tell us anything about PMIAA

## Slide 7: CHARACTERISTICS OF PROJECT LIFE CYCLES

## Slide 8: Types of PM LIFECYCLES
  Predictive life cycle. A more traditional approach, with the bulk of planning occurring upfront, then executing in a single pass; a sequential process.
  Iterative life cycle. An approach that allows feedback for unfinished work to improve and modify that work.
  Incremental life cycle. An approach that provides finished deliverables that the customer may be able to use immediately.
  Agile life cycle. An approach that is both iterative and incremental to refine work items and deliver frequently.

## Slide 9: NON-AGILE (NON-ADAPTIVE) APPROACHES
Predictive
Linear
Waterfall
Plan-driven
Serial
Notes: In the end, we settled on the term predictive since it is used in A Guide to the Project
Management Body of Knowledge (PMBOK® Guide) [3] and the Software
Extension to the PMBOK® Guide Fifth Edition [4].
If agile is at one end, we call the other end
predictive.

## Slide 10: Characteristics of Four Categories of Life Cycles

## Slide 11: Figure X3-1. The Continuum of Project Life Cycles (from PMBOK 6th ed.)
If agile is at one end, we call the other end predictive.

## Slide 12: The Continuum of Life Cycles

## Slide 13: Predictive life cycles
Take advantage of things that are known and proven.
This reduced uncertainty and complexity allows teams to segment work into a sequence of predictable groupings.

## Slide 14: Iterative life cycles
Allow feedback on partially completed or unfinished work to improve and modify that work

## Slide 15: Incremental life cycles
Provide finished deliverables that the customer may be able to use immediately

## Slide 16: Agile life cycles
Leverage both the aspects of iterative and incremental characteristics.
When teams use agile approaches, they iterate over the product to create finished deliverables.
The team gains early feedback and provides customer visibility, confidence, and control of the product.
Because the team can release earlier, the project may provide an earlier return on investment because the team delivers the highest value work first.

## Slide 17: Model for Suitability of Agile Approaches

## Slide 18: CHARACTERISTICS OF PREDICTIVE LIFE CYCLES
Predictive life cycles expect to take advantage of high certainty around firm requirements, a stable team, and low risk
Project activities often execute in a serial manner
These projects succeed when potential changes are restricted (plans, team members, requirements)
Articulate the constraints
Serialized sequence of work
Do not typically deliver business value until the end of the
project

## Slide 19: CHARACTERISTICS OF ITERATIVE LIFE CYCLES
Iterative life cycles improve the product or result through successive prototypes or proofs of concept
Iterations help identify and reduce uncertainty in the project
Projects benefit from iterative life cycles when:
  complexity is high
  when the project incurs frequent changes
  when the scope is subject to differing stakeholders’ views of the desired final product
Notes: “We will know the requirements when we deliver a prototype that the business approves.” = MOCK UP

## Slide 20: CHARACTERISTICS OF Incremental LIFE CYCLES
Optimize work for delivering value to sponsors or customers more often than a single, final product
Delivery of smaller deliverables
Speed of delivery
Customers receive a subset of the overall solution frequently
The degree of change and variation is less important than ensuring customers get value sooner than at the end of the project.
Notes: For example, builders may want to show a finished room or floor of a building
before they continue with the remainder of the building. In that case, they may
complete a floor with fixtures, paint, and everything else intended for the
finished floor before proceeding to the next floor. The customer is able to see
and approve of the style, color, and other details, allowing adjustments to be
made before further investments of time and money are made. This reduces
potential rework and/or customer dissatisfaction.

## Slide 21: CHARACTERISTICS OF agile LIFE CYCLES
Agile life cycles are those that fulfill the principles of the Agile Manifesto
Customer satisfaction increases with early and continuous delivery of valuable products
An incremental deliverable that is functional and provides value is the primary measure of progress
Adapt to high degrees of change and deliver project value more often
Incremental delivery uncovers hidden or misunderstood requirements
Iteration-Based Agile
Flow-Based Agile
The iterative and incremental approaches provide feedback to better plan the next part of the project

## Slide 22: CHARACTERISTICS OF iteration-based agile LIFE CYCLES
The team works in iterations (time-boxes of equal duration) to deliver completed features
The team works on the most important feature, collaborating as a team to finish it
Then the team works on the next most important feature and finishes it
The team may decide to work on a few features at a time, but the team does not address all of the work for the iteration at once
Notes: (i.e., does not address all of the requirements, followed by all of the analyses, etc.).

## Slide 23: CHARACTERISTICS OF flow-based agile LIFE CYCLES
In flow-based agile, the team pulls features from the backlog based on its capacity to start work rather than on an iteration-based schedule
The team defines its workflow with columns on a task board and manages the work in progress for each column
Each feature may take a different amount of time to finish
Teams keep work-in-progress sizes small to better identify issues early and reduce rework should changes be required
Without iterations to define planning and review points, the team and business stakeholders determine the most appropriate schedule for planning, product reviews, and retrospectives
Notes: WIP

## Slide 24: pull/ push / jit

## Slide 25: PREDICTIVE LIFE CYCLES

## Slide 26: Iterative Life Cycle

## Slide 27: A Life Cycle of Varying-Sized Increments

## Slide 28: Iteration-Based Agile

## Slide 29: Flow-Based Agile

## Slide 30: Agile suitability filters

## Slide 31: introduction
Various assessment models exist to help determine the likely fit or gaps for using agile approaches.
These models assess project and organizational factors associated with adoption and suitability and then provide scores indicating alignment or potential risk areas.
Appendix X3 provides a synthesis of popular assessment models for use as an agile suitability filter.

## Slide 32: Model for Suitability of Agile Approaches

## Slide 33: CHARACTERISTICS OF HYBRID LIFE CYCLES
It is not necessary to use a single approach for an entire project.
A combination of predictive, iterative, incremental, and/or agile approaches is a hybrid approach.

## Slide 34: Agile development followed by a predictive rollout
This approach can be used when there is uncertainty, complexity, and risk in the development portion of the project that would benefit from an agile approach, followed by a defined, repeatable rollout phase that is appropriate to undertake in a predictive way, perhaps by a different team.
An example of this approach is the development of a new high-tech product followed by rollout and training to thousands of users.

## Slide 35: COMBINED AGILE AND PREDICTIVE APPROACHES
Another approach is to use a combination of agile and predictive approaches throughout the life cycle
It would be misleading to call the approach agile since it clearly does not fully embody the agile mindset, values, and principles
It would also be inaccurate to call it predictive
It is a hybrid approach

## Slide 36: PREDOMINANTLY PREDICTIVE APPROACH WITH SOME AGILE COMPONENTS
A small agile element within a chiefly predictive project
The portion of the project with uncertainty, complexity, or opportunity for scope creep is being tackled in an agile way
Notes: An example of this approach
would be an engineering firm that is building a facility with a new component.
While the majority of the project may be routine and predictable, like many
other facility projects the organization has undertaken before, this project
incorporates a new roofing material. The contractor may plan for some smallscale
installation trials on the ground first to determine the best installation
method and to uncover issues early while there is plenty of time to solve them
and incrementally improve processes through experimentation and adaptation.

## Slide 37: A LARGELY AGILE APPROACH WITH A PREDICTIVE COMPONENT
A largely agile approach with a predictive component
Used when a particular element is non-negotiable or not executable using an agile approach
Notes: Examples include integrating an external
component developed by a different vendor that cannot or will not partner in a
collaborative or incremental way. A single integration is required after the
component is delivered.

## Slide 38: HYBRID LIFE CYCLES AS FIT-FOR-PURPOSE
Project teams may design a hybrid life cycle based on project risks
The goal of project management is to produce business value in the best possible way given the current environment
The question to ask is: “How can we be most successful?”
Is feedback needed as the team produces value? If so, increments will help
Is it necessary to manage risk as ideas are explored? If so, iterations or agile will help
When the organization cannot deliver intermediate value, agile approaches may not be useful
Agile is about customer-based delivery on a frequent basis. That delivery creates feedback for the team. The team uses that feedback to plan and replan the next chunk of work.
Notes: For
example, a campus construction project may have multiple buildings to improve
and build. An incremental approach would focus resources on completing some
buildings earlier than others, accelerating the return on investment. Each
individual delivery may be sufficiently well known to benefit from a predictive
life cycle for that building alone.

## Slide 39: HYBRID LIFE CYCLES AS TRANSITION STRATEGY
A gradual transition involves adding more iterative techniques to improve learning and alignment among teams and stakeholders
Later, consider adding more incremental techniques to accelerate value and return on investment to sponsors
Try these new techniques on a less risky project with a medium-to low-degree of uncertainty
Then, when the organization is successful with a hybrid approach, try more complex projects that require more of those techniques to be added
Notes: Many teams are not able to make the switch to agile ways of working
overnight. Agile techniques look and feel very different to those who are
accustomed to and have been successful in a predictive environment. The larger
the organization and the more moving parts, the longer it will take to transition.
For that reason, it makes sense to plan a gradual transition.

## Slide 40: MIXING AGILE APPROACHES

## Slide 41: introduction
Agile frameworks are not customized for the team.
The team may need to tailor practices to deliver value on a regular basis.
Often, teams practice their own special blend of agile, even if they use a particular framework as a starting point
Notes: BLENDING APPROACHES
As an example of tailoring agile frameworks, one of the most common
blends in widespread use involves a coordinated use of the Scrum framework,
the Kanban Method, and elements of the eXtreme Programming (XP) method.
Scrum provides guidance on the use of a product backlog, a product owner,
scrum master, and a cross-functional development team, including sprint
planning, daily scrum, sprint review, and sprint retrospective sessions. A
kanban board helps the team to further improve its effectiveness by
visualizing the flow of work, making impediments easily visible, and
allowing flow to be managed by adjusting work in process limits. In addition,
XP-inspired engineering practices such as use of story cards, continuous
integration, refactoring, automated testing, and test-driven development
further increase the effectiveness of the agile team. In summary, the blend of
practices from these various sources produces a synergistic result of higher
performance than each individual component in isolation.

## Slide 42: PROJECT FACTORS THAT INFLUENCE TAILORING [1/2 ]
Project Factor | Tailoring Options
Demand pattern: steady or sporadic | Many teams find that using a cadence (in the form of a regular timebox) helps them demo, retrospect, and take in new work. In addition, some teams need more flexibility in their acceptance of more work. Teams can use flowbased agile with a cadence to get the best of both Worlds
Rate of process improvement required by the level of team experience | Retrospect more often and select improvements
The flow of work is often interrupted by various delays or impediments | Consider making work visible using Kanban boards and experimenting with limits for the various areas of the work process in order to improve flow

## Slide 43: PROJECT FACTORS THAT INFLUENCE TAILORING [2/ 2]
Project Factor | Tailoring Options
The quality of the product increments is poor | Consider using the various test-driven development practices. This mistake-proofing discipline makes it difficult for defects to remain Undetected
More than one team is needed to build a product | To scale from one to several agile teams, with minimal disruption, first learn about agile program management or formal scaling frameworks. Then, craft an approach that fits the project context
The project team members are inexperienced in the use of agile approaches | Consider starting by training team members in the fundamentals of the agile mindset and principles. If the team decides to use a specific approach such as Scrum or Kanban, provide a workshop on that approach so the team members can learn how to use it