## Slide 1
PMG510
Project Risk Management
Prepared by Dr. Salahaldin Abuabdou
Risk assessment Considerations
Lecture 5

## Slide 2
Lecture 4 Summery
Risk management process:
Risk management context
Components of the RM context
Scope of the context
Designing a risk register
Risk Management Planning

## Slide 3
Importance of risk assessment:
Lecture 5 Risk assessment considerations
Risk Assessment: is defined as the overall process of risk identification, risk analysis and risk evaluation.
The purpose of risk assessment is to identify the significant risks that could impact the selected feature
An important feature of undertaking a risk assessment: is to decide whether the identified risk is going to be evaluated at the inherent level or at the current (or residual) level.

## Slide 4
Importance of risk assessment:
Lecture 5 Risk assessment considerations
The benefit of undertaking assessment of inherent risk: is that the difference between the current level and the inherent level can be identified.
This will give an indication of the importance of the existing control measures and the information is used by internal auditors to help identify critical controls and set audit priorities.
For example, if an assessment of an x-ray machine is being undertaken, the safety person will assume that the enclosure or cabinet is in good order and the risk should be assessed on that basis. The internal auditor will more easily recognize that the enclosure or cabinet is a vitally important control factor that has to be subject to a routine inspection.

## Slide 5
Techniques of risk assessment:
Lecture 5 Risk assessment considerations
The main risk assessment techniques are as following:
1- Questionnaires and checklists: Use of structured questionnaires and checklists to collect information that will assist with the recognition of the significant risks.
2- Workshops and brainstorming: Collection and sharing of ideas at workshops to discuss the events that could impact the objectives, core processes or key dependencies

## Slide 6
Techniques of risk assessment:
Lecture 5 Risk assessment considerations
The main risk assessment techniques are as following:
3- Inspections and audits: Physical inspections of premises and activities an audits of compliance with established systems and procedures.
4- Flow charts and dependency analysis: Analysis of the processes and operations within the organization to identify critical components that are key to success.

## Slide 7
Advantages and disadvantages of RA techniques:
Lecture 5 Risk assessment considerations

## Slide 8
Nature of the risk matrix:
Lecture 5 Risk assessment considerations

## Slide 9
Nature of the risk matrix:
Lecture 5 Risk assessment considerations

## Slide 10
Nature of the risk matrix:
Lecture 5 Risk assessment considerations
Identification of potentially significant risks will be undertaken during a risk recognition exercise. It is necessary to decide the:
Magnitude of the event should the risk materialize;
Size of the impact that the event would have on the organization;
Likelihood of the risk materializing at or above the benchmark;
Scope for further improvement in control.

## Slide 11
Attitude to risk:
Lecture 5 Risk assessment considerations
Risk attitude represents the long-term approach of the organization to risk
It is becoming more common for a risk attitude matrix to contain four sections.
These sections can be represented by the 4Cs of comfort, cautious, concerned and critical.

## Slide 12
Attitude to risk:
Lecture 5 Risk assessment considerations

## Slide 13
Attitude to risk:
Lecture 5 Risk assessment considerations
Example risks involved in buying a car:
As an example that brings together the ideas of risk appetite and hazard, control and opportunity risks, consider the decision to buy a car.
When deciding which car to buy, there is a need to evaluate hazard tolerance and acceptance of uncertainty, as well as the sum of money that will be invested in the opportunity of owning a new vehicle.
Together, these components represent the risk appetite to buy and run a car. In order to achieve an upside of taking the risk of buying a car, the benefits obtained must exceed the costs involved

## Slide 14
Attitude to risk:
Lecture 5 Risk assessment considerations
Example risks involved in buying a car:
If undertaking a risk-based evaluation of buying a car is to help with the decision-making process, the intended benefits of car ownership should be established. This is equivalent to identifying the objectives associated with car ownership.
The actual financial capacity and ability to run a car also needs to be considered. When buying a new vehicle, the buyer needs to make sure that the vehicle selected will not lead to more risk and cost than anticipated. The risks that are associated with owning a vehicle include breakdown, repairs, accidents, servicing costs and insurance, as well as the purchase price and the anticipated annual depreciation.

## Slide 15
Attitude to risk:
Lecture 5 Risk classification systems
Example risks involved in buying a car:
Assume that the decision has been taken to buy a two-year-old prestigious car. The car will cost much less money than a new vehicle and the depreciation costs will be much less (opportunity risks). However, the repair and maintenance costs may be higher than for a new vehicle (control risks). The exposure to accidents, theft and repair costs will be similar for most vehicles (hazard risks).
Remember that the opportunity risks enhance the possible achievement of the benefits of owning a car. The control risks increase uncertainty or doubt about achieving these benefits and the hazard risks inhibit the achievement of the car ownership benefits

## Slide 16
1- short-, medium- and long-term risks:
Lecture 5 Risk classification systems
The classification of risks into short, medium and long term helps to identify risks as being related (primarily) to operations, tactics and strategy, respectively.
This distinction is not clear-cut, but it can assist with further classification of risks.
there will be some short-term risks to strategic core processes and there may be some medium-term and long-term risks that could impact operational core processes.

## Slide 17
1- short-, medium- and long-term risks:
Lecture 5 Risk classification systems
A short-term risk has the ability to impact the objectives, key dependencies and core processes, with the impact being immediate.
Medium-term risks usually impact the ability of the organization to maintain effective and efficient core processes that are concerned with the management of tactics, projects and other change programmes.
Long-term risks usually impact the ability of the organization to maintain the core processes that are concerned with the development and delivery of effective and efficient strategy.

## Slide 18
1- short-, medium- and long-term risks:
Lecture 5 Risk classification systems
The next Figure illustrates short-term, medium-term and long-term risks in terms of the source of these risks.
The risks arise from the operations, tactics and strategy adopted by the organization.
For the sake of completeness, the category of compliance risks is also included, since this is an additional category to operations, tactics and strategy.

## Slide 19
1- short-, medium- and long-term risks:
Lecture 5 Risk classification systems
The need to respond to risks according to whether they arise from strategy, tactics, operations or compliance (STOC) is summarized by embrace, manage, mitigate and minimize (EM3) respectively.
The purpose of the bow-tie illustration of risk management is to demonstrate that sources of risk can lead to events that have consequences

## Slide 20
1- short-, medium- and long-term risks:
Lecture 5 Risk classification systems

## Slide 21
1- short-, medium- and long-term risks:
Lecture 5 Risk classification systems
The pervious Figure provides an example of the bow-tie being used to represent the three components of risk: source, event and impact.
In this high-level representation, risk sources are identified as strategic, tactical, operational or compliance.
Impacts are represented using the FIRM risk scorecard, as described in the following Table.
At the center of the bow-tie is the event, as described by the component of the organization that will be impacted by the event.

## Slide 22
2- FIRM risk scorecard:
Lecture 5 Risk classification systems
The classification system also reflects the idea that every organization should be concerned about its finances, infrastructure, reputation and marketplace success. In order to give a broader scope to commercial success, the headings of the FIRM risk scorecard are as follows:
F Financial;
I Infrastructure;
R Reputational;
M Marketplace.

## Slide 23
short-, medium- and long-term risks:
Lecture 5 Risk classification systems

## Slide 24
short-, medium- and long-term risks:
Lecture 5 Risk classification systems

## Slide 25
3- PESTLE classification system:
Lecture 5 Risk classification systems

## Slide 26
4- Compliance, hazard, control and opportunity
Lecture 5 Risk classification systems
Categorizing risks according to a single risk classification system is not always helpful
Risks need to be classified according to the source or impact as well as according to the timescale of the impact.
Therefore, a combination of the FIRM risk scorecard and the classification of risks as hazard, control and opportunity risks, or classifying them according to whether they are short term, medium term or long term, all can be used to provide a complete picture.

## Slide 27
Project Risk Identification:
Lecture 5 Project Risk Management Guide

## Slide 28
Project Risk Identification:
Lecture 5 Project Risk Management Guide
2-1 Risk Identification during Project Development:
Risk identification is ongoing through project development:
1. Planning
2. Scoping
3. Design/Plans, Specifications, and Estimate (Engineer’s Estimate)
4. Construction

## Slide 29
Project Risk Identification:
Lecture 5 Project Risk Management Guide
2-2 Risk Identification: Inputs, Tools and Techniques, Outputs:
2-2.1 Risk Identification Inputs
The most important first input is a defined project. In order to fully understand and assess. project risks we must ensure a mutual understanding of the project under evaluation.
Fundamental information about a project includes a clear statement of need. To focus on risks and uncertainties our project will face, we must know the project in context, scope, schedule, and estimate.
Information is commensurate with the level of project development at the time of risk analysis. Progressive elaboration should not be confused with scope creep.

## Slide 30
Project Risk Identification:
Lecture 5 Project Risk Management Guide
2-2 Risk Identification: Inputs, Tools and Techniques, Outputs:
2-2.2 Risk Identification Tools and Techniques
Brainstorming: An effective method, brainstorming can range from a small informal project team effort for simpler projects to a full-blown CEVP® workshop. Effective brainstorming requires a skilled facilitator, working together with the project team and specialists who can bring additional expertise.
Checklists and/or questionnaires to “specialty groups”: Checklists/questionnaires are quick and easy to use, but limited in nature; they only deal with the items on the list. Each project is unique, so a standard list will often not capture the project-specific risks of most concern. Though it can be limited, a checklist/questionnaire can spark thinking prior to a more formal brainstorming process.

## Slide 31
Project Risk Identification:
Lecture 5 Project Risk Management Guide
2-2 Risk Identification: Inputs, Tools and Techniques, Outputs:
2-2.2 Risk Identification Tools and Techniques
Examination of past similar projects: Lessons learned from past projects help us to avoid repeating mistakes. Using past examples requires prudent and objective judgment, since a previous project may be similar but is nonetheless different because each new project has unique requirements and features, including uncertainties and risks.
A combination of the above methods and/or others: It is quite likely that for most projects, a
combination of the above methods will be used to identify risks.

## Slide 32
Thanks