## Slide 1
Prepared by Dr. Tarek Mohamed
Project Procurement and
Supply Chain
Lecture 6
PMG 433

## Slide 2
Procurement: Process overview and emerging
project management techniques
Lecture 6
PMG 433
Dr. Tarek Mohamed
Prepared by

## Slide 3
Course Agenda
To explain more about the scope of procurement.
To overview the project procurement management processes.
To explain the procurement planning steps.
To differentiate between the RFP and RFQ and RFI
AI and Emerging Project Management Techniques
Chapter

## Slide 4: PROCUREMENT
Effective procurement is critical for effective project management.
Procurement means acquiring goods and/or services from an outside source.
Procurement – The process of acquiring and evaluating goods and services beginning with determining needs through product utilization, conclusion of contracted service, or until the end of the useful life of a capital equipment item.
Depending upon the specific type of project being managed, over 50 percent of the total project cost can be attributed to parts, supplies, and services procured, and for many high-technology projects, this procurement fraction can approach 90 percent.
Further, because of long lead times, procured items nearly always define the critical path through the project schedule network.

## Slide 5: Project Procurement Management Processes
Project procurement management
Includes the following processes for acquiring goods and services from outside
the project organization
  Procurement planning: determining what to procure and when.
  Solicitation planning: documenting product requirements and identifying potential sources.
  Solicitation: obtaining quotations, bids, offers, or proposals as appropriate.
  Source selection: choosing from among potential vendors.
  Contract administration: managing the relationship with the vendor.
  Contract close-out: completion and settlement of the contract.

## Slide 6: Project Procurement Management Processes & Key Outputs
The figure below summarises the major processes involved in procurement management, and identifies important milestones associated with each stage.
For example, after procurement planning the key milestone is the “make or buy decision”. This will determine if further procurement management processes are required.

## Slide 7: Procurement Planning
Procurement planning involves identifying which project needs
can be best met by using products or services outside the organization.
It includes deciding:
  Whether to procure.
  How to procure.
  What to procure.
  How much to procure.
  When to procure.
It is essential to be creative when planning procurement.
Even though a company may be viewed as a competitor, it will often be
advantageous to collaborate on some projects.

## Slide 8: Inputs to Procurement Planning
The inputs needed for procurement planning include:
The project scope statement.
Product description.
Market conditions.
Constraints and assumptions.
It is important to define the scope of the project, the products,
market conditions, and constraints and assumptions.
However, it is also essential to know exactly why you want
to procure goods or services.

## Slide 9: Tools and Techniques
Procurement management will often incorporate the following:
  Make-or-buy analysis: determining whether a particular product or service should be made or performed inside the organization or purchased from someone else. Often involves financial analysis.
  Experts, both internal and external, are valuable assets in procurement decisions.
    Internal experts are particularly useful in providing knowledge of organisational and personnel issues.
    External experts can provide expert judgement, especially with regard to vendors and technology issues.

## Slide 10: Project Procurement Plan
A Project Procurement Plan is a formal document that describes how the project team will acquire the goods, services, equipment, and works needed to complete the project successfully.
It defines the procurement strategy, schedule, budget, contract types, supplier selection methods, roles and responsibilities, and risk management approach.
The Project Procurement Plan is typically developed during the Project Planning phase and serves as a guide for managing all procurement activities throughout the project lifecycle.

## Slide 11: Objectives of a Project Procurement Plan
The Project Procurement Plan aims to:
Ensure the timely acquisition of project resources.
Support project scope, schedule, and budget.
Select qualified suppliers through a fair and transparent process.
Minimize procurement risks.
Ensure compliance with organizational policies and legal requirements.
Improve communication among project stakeholders.
Achieve value for money while maintaining quality.

## Slide 12: Procurement Plan

## Slide 13: Procurement Planning (cont.)
Procurement plan linked to project implementation schedule:
Consulting services
Goods and / or works
Major contracts
Phasing of contracts
Critical path

## Slide 14: Procurement Planning Packaging
Decide contract packages
WHAT (like items, large, small, values slice and packages)
HOW (ICB, NCB, other, co-financing)
WHEN (each step, each package)
WHO (to do, to review)

## Slide 15: Procurement Planning: Timing
TIMING (Preparation, approvals, delays)
CONSTRAINTS
(Technical, PIU staffing, legal, training, other)
DETERMINE LEAD TIME
  Administrative
  Manufacture
  Delivery
  Construction period

## Slide 16: Procurement Planning: Schedule
Critical dates for each package
Tabulate / prepare bar chart
Periodically update
Use of monitoring system

## Slide 17: Procurement Process Definition
The Procurement Process consists of the full cycle of activities (steps) to undertake to fulfill a specified need, starting from identification of the said need

## Slide 18: Procurement Steps
Identification of needs
  List of goods (e.g. equipment, materials, plant, IT systems)
  Types of works (large, small, very small)
  Associated services: transport, distribution, training, maintenance

## Slide 19: Procurement Steps (cont.)
Project implementation plan
  Design and specification
  Packaging: organizational implementation
  Schedule: time frame of implementation
Bidding methods and documents
  Competitive methods
  Shopping methods
  Direct contracting

## Slide 20: Procurement Steps (cont.)
Advertising
Bidding process
  Issuance of bidding documents or request for quotations
  Bid or quotations submission and opening
  Bid or quotation evaluation

## Slide 21: Procurement Steps (cont.)
Contract and purchase order award
  Notification
  Signature
  Effectiveness
Contract management
  Contract execution
  Delivery, commissioning, acceptance
  Warranty
  Maintenance period
Need fulfilled

## Slide 22: Competence Requirements in Procurement Process
DETERMINING NEEDS
1. Forecasting Requirements
2. Acquisition (procurement), Planning and Packaging
3. Initiating Procurement (requisition, budget approval)
ANALYSIS OF REQUIREMENTS
4. Preparation of Technical Specifications (goods / equipment)
5. Detailed Design and Drawings (Civil Works)
6. Terms of Reference (TOR) - (Services)

## Slide 23: Competence Requirements in Procurement Process (cont.)
EXTENT OF COMPETITION
7. Sources of Supply (market research)
8. Lease vs. Purchase
9. Evaluation Factors (technical and commercial)
10. Method of Procurement (with or without pre-qualification)

## Slide 24: Competence Requirements in Procurement Process - Bidding
TERMS AND CONDITIONS
11. Contract Types
Need for Securities (Bid and Performance)
Selection of INCOTERM
Preparation of Tender Documents
Prescribing insurance requirements
14. Publicizing Proposed Procurements
15. Pre-bid / Pre-proposal Conferences
16. Amending Bidding Documents
17. Cancelling Tenders

## Slide 25: Competence Requirements in Procurement Process - Bidding
BID EVALUATION
Receiving Bids / Rejecting Late Bids
Bid Opening
Preliminary Examination / Determination of Responsiveness
Technical Evaluation
Cost Analysis
Evaluation: Other Terms and Conditions
Clarification of Issues before Contract Signing

## Slide 26: Competence Requirements in Procurement Process - Bidding
SELECTION FOR AWARD
Subcontracting Requirements
Post-Qualification
EXECUTING AWARD
Preparing Awards
Debriefing
Protests by Bidders
Dealing with Fraud & Corruption

## Slide 27: Competence Requirements in Procurement Process – Contract Execution
ORGANIZATION
Contract Administration Planning
Consent to sub-contracts
MONITORING AND RESOLUTION OF PERFORMANCE PROBLEMS
Monitoring, Inspection and Acceptance
Delays
Stop Works (Suspension of Works)
Remedies
Reporting Performance Problems / Contemporary record

## Slide 28: Competence Requirements in Procurement Process – Contract Execution
PROCEDURES - PAYMENT
Variation Orders
Progress Payment / Retention
Price Adjustment
PROCEDURES - ACCOUNTING
41. Cost Accounting Systems
PROCEDURES - MODIFICATION / OPTIONS
42. Contract Amendments

## Slide 29: Competence Requirements in Procurement Process – Contract Execution
PROCEDURES - TERMINATION
Termination for Default / Convenience
Warranty / Maintenance / Defects Notification Period
Contract close-out
PROCEDURES - CLAIMS / DISPUTES
49. Claims
50. Dispute Settlement Procedures

## Slide 30: RFP/RFQ Process Difference of RFP and RFQ and RFI

## Slide 31: Difference of RFP and RFQ and RFI
Request for Proposal (RFP)
Request for Quote (RFQ)
Request for information (RFI)

## Slide 32: Difference of RFP and RFQ and RFI
DEFINITION of RFP:
Request for Proposal (RFP) - A solicitation to prospective suppliers where the supplies and/or services described are highly complex, undeveloped products and/or services, requiring a response detailing technical and management expertise and a proposed design/development approach.

## Slide 33: Difference of RFP and RFQ and RFI
DEFINITION of RFQ:
Request for Quotation (RFQ) - A solicitation to prospective suppliers wherein the requirements described are existing, “off-the-shelf” equipment, build-to-print parts with known specifications, common services, or otherwise sufficiently defined so that the award can be made on the basis of price and past performance from the responsive bidders.

## Slide 34: Difference of RFP and RFQ and RFI
DEFINITION of RFI:
Request for information (RFI) - is a standard business process whose purpose is to collect written information about the capabilities of various suppliers. Normally it follows a format that can be used for comparative purposes.
An (RFI) is primarily used to gather information to help decide on what steps to take next..
(RFIs) are therefore seldom the final stage and are instead often used in combination with the following: request for proposal (RFP), and request for quotation (RFQ).

## Slide 35: Types of solicitations
A solicitation is a document, sent to prospective contractors by a Government agency, requesting the submission of offers or information.
This is a generic term that includes the following types of solicitations:
Invitations for Bids (IFBs)
Requests for Proposals (RFPs)
Requests for Quotations (RFQs)

## Slide 36: Invitation for Bids (IFB)
The Invitation for Bid (IFB) is the solicitation document used in sealed bidding procurements.
IFBs must describe the government’s requirements clearly, accurately, and completely.
It includes all documents needed by prospective bidders for the purpose of bidding plus all terms and conditions of the prospective contract (except price) so that all bidders will submit bids on the same basis and award can be made solely on the basis of price and price-related factors.

## Slide 37: Buyer’s Role in the RFQ/RFP Process
Upon receipt of a requirement the Buyer reviews and determines if the originating organization(s) has furnished complete specifications, blueprints, statements of work (SOW), description of item(s) to be purchased, etc., so that requirements can be adequately defined in the RFQ/RFP and any resulting Purchase Order (PO).
The Buyer will contact originating organization(s) or Integrated Product Teams (IPTs) if additional data is required.

## Slide 38: RFQ Structure
The Buyer is responsible for the entire content of the RFQ. The RFQ should be structured in such a manner to assure that all requirements are clearly delineated on the RFQ, and that the supplier clearly understands the requirements.
In some cases, the Buyer may need to provide additional clarification of the requirements to assure complete understanding by the supplier. In such cases, the Buyer is responsible for providing consistent information to all solicited suppliers.

## Slide 39: Supplier Steps To Providing A Responsive Proposal
  Do’s
    Read the RFP Instructions
    Contact the Buyer regarding RFP questions
    Meet the RFP deadline and provide a Proposal which meets the RFP instructions
    Protect PWR proprietary data
    Protect Export controlled data
  Don’ts
    Contact technical personnel for questions during the proposal process unless Buyer instructed
    Wait to the last minute to ask for an extension
    Continually ask for extensions

## Slide 40: Request for proposal
Key objectives
Obtain correct information to enable sound business decisions.
Ensure that all suppliers have an equal understanding of the requirements.
Enable a broader and creative range of solutions to be considered.
Responsive Bids allow PWR purchasing to evaluate proposals to obtain a favorable deal.

## Slide 41: Evaluation Criteria
Responsive Bid
Price
Delivery
Technical Solution
Past Performance (SPI)
Financial Stability
Agreed Upon Terms & Conditions

## Slide 42: Steps In The RFP Evaluation Process
Step One: Review All Proposals
Step Two: Determine Status. Determine if proposal is “responsive” or “non-responsive”
Step Three: Score Proposals based on criteria established in the RFP
Step Four: Discuss Proposals. The evaluation committee reaches a “unified understanding” of the criteria and corresponding responses. Individual scores may be adjusted at this point based on discussion. Tally results.
Step Five: Interview. This step is optional. This is an opportunity for both sides to explain their viewpoints

## Slide 43: Steps In The RFP Evaluation Process
Step Six: Discussion/Negotiation. This step can be optional but may be required.
Step Seven: Best and Final Offer. This is optional. Once a BAFO is received the committee will evaluate it in the same manner as the original proposal.
Step Eight: Recommendation. Written recommendation includes scores, justification and rationale for the decision.
Step Nine: Management Review of committee scoring and justification. If accepted, the winning proposal will be used to roll up in PWR proposal or award PO to supplier if using company funds or after PWR is awarded a contract.

## Slide 44: AI and Emerging Project Management Techniques
Emerging Technique | AI Contribution | Project Benefit
Predictive Analytics | Forecasts demand, costs, and procurement risks | Better planning and decision-making
Machine Learning | Learns from procurement data to improve recommendations | More accurate supplier selection and forecasting
Robotic Process Automation (RPA) | Automates routine procurement activities | Faster processing and lower administrative costs
Big Data Analytics | Analyzes large volumes of procurement and market data | Better strategic purchasing decisions
Blockchain Integration | Enhances transparency and traceability when combined with AI | Improved trust and fraud prevention
Cloud Procurement Systems | Provides centralized procurement data for AI analysis | Real-time collaboration and visibility
Agile Project Management | Uses AI insights to respond quickly to changing project needs | Greater flexibility and adaptability
Sustainable Procurement | AI evaluates suppliers' environmental and social performance | Supports ESG and sustainability objectives

## Slide 45
Summary of Learning Objectives
To explain more about the scope of procurement.
To overview the project procurement management processes.
To explain the procurement planning steps.
To differentiate between the RFP and RFQ and RFI
AI and Emerging Project Management Techniques

## Slide 46
Morris, P. W., & Pinto, J. K. (Eds.). (2007). The Wiley guide to project technology, supply chain, and procurement management (Vol. 4). John Wiley & Sons.
Schwalbe, K. (2015). Information technology project management. Cengage Learning.
Baily, P., Farmer, D., Crocker, B., Jessop, D., & Jones, D. (2008). Procurement principles and management. Pearson Education.
Supply Chain Council
Essential Reference

## Slide 47
Thank You