## Slide 1
Project Time Management
Lecture 8
PMG 212
www.midocean.ae
Prepared by Dr. Nael Yousry
Presented by Dr. Amira Elfekky

## Slide 2
Prepared by Dr. Nael Yousry
Project Time Management
Lecture 8
PMG 212
Presented by Dr. Amira Elfekky

## Slide 3
Agenda
Critical Path method
Scheduling Terminology
Estimate the duration
Scheduling Consists of
Develop the Schedule
The common Scheduling Failures
www.midocean.ae
08
Chapter

## Slide 4
Agenda
Critical Path method
Scheduling Terminology
Estimate the duration
Scheduling Consists of
Develop the Schedule
The common Scheduling Failures
www.midocean.ae
08
Chapter

## Slide 5
Critical Path
www.midocean.ae
One or more continuous chains of zero or negative float activities running from the start event to the finish event in the schedule.
The Critical Path is normally the Longest Path (longest series of continuous activities) in the schedule.
Any activity on the critical path is called a Critical Activity.
08
Chapter

## Slide 6
Critical Path method
The critical path method (CPM) is a technique that’s used by project managers to create a project schedule and estimate the total duration of a project.
Activity | Duration
A | 1
B | 7
C | 6
D | 4
E | 8
F | 6
G | 4
H | 3
I | 5
J | 5
K | 3
Sum | 52
www.midocean.ae
08
Chapter

## Slide 7
Critical Path method
The CPM method, also known as critical path analysis (CPA), consists in using a network diagram to visually represent the sequences of tasks needed to complete a project.
Once these task sequences or paths are defined, their duration is calculated to identify the critical path, which determines the total duration of the project.
www.midocean.ae
08
Chapter

## Slide 8
Critical Path method
www.midocean.ae
08
Chapter

## Slide 9
Agenda
Critical Path method
Scheduling Terminology
Estimate the duration
Scheduling Consists of
Develop the Schedule
The common Scheduling Failures
www.midocean.ae
08
Chapter

## Slide 10
Scheduling Terminology
Lead & Lag
Lead and Lag are the duration unit of tasks.
Lead is portrayed by negative (-) sign
whereas Lag is by positive (+) sign.
www.midocean.ae
08
Chapter

## Slide 11
Scheduling Terminology
Float
Total Float
Amount of time an activity can exceed its early finish date without affecting the project end date or other imposed dates.
Free Float
Amount of time by which an activity can exceed its early finish date without affecting the early start date of any successor(s).
Negative Float
Amount of time that the start or finish of any activity exceeds the time allowed.
www.midocean.ae
08
Chapter

## Slide 12
Scheduling Terminology
The disadvantages of showing float on the schedule
End user may delay start of activity thinking there is slack time
May cause false sense of security
Once used as an activity -- it’s gone forever
Assumes CPM is complete with correct logic
www.midocean.ae
08
Chapter

## Slide 13
Scheduling Terminology
Duration - Original / Remaining
Duration: is the amount of time required to complete an activity.
www.midocean.ae
08
Chapter

## Slide 14
Scheduling Terminology
Original Duration - the planned estimate of the number of work periods required to accomplish an activity.
Remaining Duration - the number of work periods currently forecast to complete the activity.
Work periods can be hours, days, weeks or months.
www.midocean.ae
08
Chapter

## Slide 15
Agenda
Critical Path method
Scheduling Terminology
Estimate the duration
Scheduling Consists of
Develop the Schedule
The common Scheduling Failures
www.midocean.ae
08
Chapter

## Slide 16
Estimate the duration
Historical information
Market information
Rates of installation
What is a “Normal” rate of installation? How do we come up with this? Varies by area?
www.midocean.ae
08
Chapter

## Slide 17
Calendar(s)
The work periods and holidays defined for the Project.
There can be multiple Calendars on a Project:
Engineering - 5 day work week
Manufacturing - 7 day work week
Construction - 6 day work week
Different local Holidays ?
www.midocean.ae
08
Chapter

## Slide 18
Project Assumptions
Project assumptions are identified at the beginning of the project. Throughout the project life cycle, they will be refined and reanalyzed.
An assumption is what you believe to be true. These are anticipated events or circumstances that are expected during your project’s life cycle. You make assumptions based on your experience or the information available on hand.
www.midocean.ae
08
Chapter

## Slide 19
Project Constraints
Project Constraints are identified at the beginning of the project. Throughout the project life cycle, they will be refined and reanalyzed.
These constraints are defined at the beginning of your project, and you must work within their boundaries.
A constraint can be of two types:
usiness Constraints
Technical Constraints
www.midocean.ae
08
Chapter

## Slide 20
Agenda
Critical Path method
Scheduling Terminology
Estimate the duration
Scheduling Consists of
Develop the Schedule
The common Scheduling Failures
www.midocean.ae
08
Chapter

## Slide 21
Scheduling Consists of
Determining the activity duration's.
Ties individual plans together.
Timing of activities.
Minimizing resource conflicts.
Identifying critical activities.
www.midocean.ae
08
Chapter

## Slide 22
Scheduling Consists of
Establishing the baseline.
Providing a tool for project evaluation.
Provides outputs for analysis.
Monitoring and analyzing progress.
Assists in developing work-arounds
www.midocean.ae
08
Chapter

## Slide 23
Information Gathering
  Information outlining the project is available in many forms and from many sources
  From the project scope description look for similar projects
  The Client - gather as much information about this Project and other similar Projects in which they have been involved.
www.midocean.ae
08
Chapter

## Slide 24
Information Gathering
Asking about these simple questions
What are you going to do?
How long is it going to take?
What do you need to start the activity?
What do you need to finish the activity?
www.midocean.ae
08
Chapter

## Slide 25
Agenda
Critical Path method
Scheduling Terminology
Estimate the duration
Scheduling Consists of
Develop the Schedule
The common Scheduling Failures
www.midocean.ae
08
Chapter

## Slide 26
Agenda
Lecture 8
Critical Path method
Scheduling Terminology
Estimate the duration
Scheduling Consists of
Develop the Schedule
The common Scheduling Failures

## Slide 27
Develop the Schedule
  Integrate individual plans
  Identify activities
  Determine activity duration
  Determine activity sequence
  Establish dependencies and constraints
  Identify critical activities
  Optimize the application of resources
www.midocean.ae
08
Chapter

## Slide 28
Types of logic among the activities
Mandatory/Hard logic
Preferential/Preferred/Discretionary/soft logic
www.midocean.ae
08
Chapter

## Slide 29
Developing an EPC Schedule
Engage in an iterative process.
  Starting with Level I and II, build the schedule.
  Check viability (milestone comparisons, curves, etc.).
  Build Level III with activity logic, resources, etc.
  Confirm Level I and II, and then finalize Level III baseline.
Planners facilitate discussions between Engineering, Procurement, Construction, and Startup team members, and interface between workgroups to optimize the overall schedule.
www.midocean.ae
08
Chapter

## Slide 30
Communicate the Schedule
The project’s principal sequences and overall strategy is clear to the team.
The project must have basic boundaries and commitments identified.
The project needs a workable plan to accomplish its objectives and everyone understands their role.
www.midocean.ae
08
Chapter

## Slide 31
Implement the Schedule
Once everyone (including the Client) agrees on the Schedule, it becomes the BASELINE Schedule.
This the reference point from which the Project will be measured from and from which all VARIANCES/ CLAIMS will be analyzed.
A copy of this Schedule will be updated with actual progress and then it becomes the Current Schedule which will change as the Project evolves.
www.midocean.ae
08
Chapter

## Slide 32
Agenda
Critical Path method
Scheduling Terminology
Estimate the duration
Scheduling Consists of
Develop the Schedule
The common Scheduling Failures
www.midocean.ae
08
Chapter

## Slide 33
The common Scheduling Failures
Lack of buy-in by all project team members
Lack of planning
Poorly defined activities
Inappropriate scheduling detail
Inadequate logic ties
www.midocean.ae
08
Chapter

## Slide 34
The common Scheduling Failures
Poor duration estimating
Lack of information
Failure to disseminate the proper information to all parties
Excessive details that overwhelm the sanity
Updates without analysis
www.midocean.ae
08
Chapter

## Slide 35
Thank You
www.midocean.ae
08
Chapter