## Slide 1
Prepared by Dr. Manal El-Sayed
Lecture 4
PMG 201
Project Feasibility Study

## Slide 2
THE WORLD OF PROJECT MANAGEMENT
Lecture 4
PMG201
THE WORLD OF PROJECT MANAGEMENT
Dr. Manal El-Sayed
Prepared by
www.midocean.ae

## Slide 3
What Is a Project?
Project Management vs. General Management
What Is Managed? The Three Goals of a Project
The Life Cycles of Projects
Selecting Projects to Meet Organizational Objectives
Confronting Uncertainty—the Management of Risk
The Project Portfolio Process
LEARNING OUTCOMES
Chapter
04
www.midocean.ae

## Slide 4
What Is a Project?
Chapter
04
Project, Defined
At first A project is an endeavor to accomplish a specific objective through a unique set of interrelated tasks and the effective utilization of resources.
www.midocean.ae

## Slide 5
A secondary effect of using multidisciplinary teams to deal with complex problems is conflict. Projects are characterized by conflict. As we will see in later chapters, the project schedule, budget, and specifications conflict with each other.
The needs and desires of the client conflict with those of the project team, the senior management of the organization conducting the project and others who may have a less direct stake in the project. Some of the most intense conflicts are those between members of the project team.
Much more will be said about this in later chapters. For the moment, it is sufficient to recognize that projects and conflict are inseparable companions, an environment that is unsuitable and uncomfortable for conflict avoiders.
What Is a Project?
Chapter
04
www.midocean.ae

## Slide 6
Project, Defined
Chapter
04
Finally, it is appropriate to ask, “ Why projects? ” The reason is simple. We form projects in order to fi x the responsibility and authority for the achievement of an organizational goal on an individual or small group when the job does not clearly fall within the definition of routine work.
www.midocean.ae

## Slide 7
Has a well-defined objective
Composed of a series of interdependent tasks
Utilizes various resources
Has a specific time frame
Has a customer
Involves a degree of uncertainty
Attributes of a Project
Chapter
04
www.midocean.ae

## Slide 8
Scope
Cost
Schedule
Customer satisfaction
Constraints
Chapter
04
www.midocean.ae

## Slide 9
Unforeseen circumstances may jeopardize achievement of the project objective.
The challenge facing the project manager is to prevent, anticipate, and/or overcome such circumstances.
Unforeseen Circumstances
Chapter
04
www.midocean.ae

## Slide 10
The project management process means planning the work and then working the plan.
The Project Management Process
Chapter
04
www.midocean.ae

## Slide 11
Clearly define the project objective.
Divide and subdivide the project.
Define the specific activities that need to be performed.
Graphically portray the activities in a network diagram
The Project Management Process (Cont.)
Chapter
04
www.midocean.ae

## Slide 12
Make a time estimate.
Make a cost estimate.
Calculate a project schedule and budget.
The Project Management Process (Cont.)
Chapter
04
www.midocean.ae

## Slide 13
Establish a baseline plan.
Monitor progress.
Measure actual progress and compare it to planned progress.
Take corrective action if the project is behind schedule, overrunning the budget, or not meeting technical specifications.
Controlling Projects
Chapter
04
www.midocean.ae

## Slide 14
Satisfied customers
Additional business
Expansion of career opportunities
Satisfaction of being on a winning team
Improved knowledge and skills
When projects are successful, everybody WINS
Benefits of Project Management
Chapter
04
www.midocean.ae

## Slide 15
Many recent developments in project management are being driven by quickly changing global markets, technology, and education.
Global competition is putting pressure on prices, response times, and product/service innovation. Computer and telecommunication technology, along with rapidly expanding higher education across the world allows the use of project management for types of projects and in regions where these sophisticated tools had never been considered before.
Trends in Project Management
Chapter
04
www.midocean.ae

## Slide 16
Achieving Strategic Goals
Achieving Routine Goals
Improving Project Effectiveness
Virtual Projects
Quasi - Projects
Trends in Project Management
Chapter
04
www.midocean.ae

## Slide 17
A project, then, is a temporary endeavor undertaken to create a unique product or service. It is specific, timely, usually multidisciplinary, and always conflict ridden. Projects are parts of overall programs and may be broken down into tasks, subtasks, and further if desired. Current trends in project management are noted.
Portfolio Program project task subtask
Trends in Project Management
Chapter
04
www.midocean.ae

## Slide 18
1. Project management differs greatly from general management. Every project is planned, budgeted, scheduled, and controlled as a unique task. Unlike non projects, projects are often multidisciplinary and usually have considerable need to cross departmental boundaries for technology, information, resources, and personnel. Crossing these boundaries tends to lead to intergroup conflict. The development of a detailed project plan based on the scope and due date of the project is critical to the project ’ s success.
2- Unlike their general management counterparts, project managers have responsibility for accomplishing a project, but little or no legitimate authority to command the required resources from the functional departments. The PM must be skilled at win - win negotiation to obtain these resources.
Major Differences
Chapter
04
www.midocean.ae

## Slide 19
The performance of a project is measured by three criteria. Is the project on time or early? Is the project on or under budget? Does the project deliver the agreed - upon outputs to the satisfaction of the customer? Figure 1-1 shows the three goals of a project. The performance of the project and the PM is measured by the degree to which these goals are achieved.
WHAT IS MANAGED? THE THREE GOALS OF A PROJECT
Chapter
04
www.midocean.ae

## Slide 20
One of these goals, scope, is set primarily by the client (although the client agrees to all three when contracting for the project). It is the client who must decide what capabilities are required of the project ’ s deliverables — and this is what makes the project unique. Some writers insist that “ quality ” is a separate and distinct goal of the project along with time, cost, and scope. We do not agree because we consider quality an inherent part of the project specifications. If we did not live in an uncertain world in which
Chapter
04
www.midocean.ae
WHAT IS MANAGED? THE THREE GOALS OF A PROJECT

## Slide 21
One of these goals, scope, is set primarily by the client (although the client agrees to all three when contracting for the project). It is the client who must decide what capabilities are required of the project ’ s deliverables — and this is what makes the project unique. Some writers insist that “ quality ” is a separate and distinct goal of the project along with time, cost, and scope. We do not agree because we consider quality an inherent part of the project specifications. If we did not live in an uncertain world in which
Chapter
04
www.midocean.ae
WHAT IS MANAGED? THE THREE GOALS OF A PROJECT

## Slide 22
There are two different paths (life cycles) along which projects progress from start to completion. One is S - shaped and the other is J - shaped. It is an important distinction because identifying the different life cycles helps the PM to focus attention on appropriate matters to ensure successful project completion.
S-Shaped :They start slowly, develop momentum, and then finish slowly.
J-Shaped :They start slowly, proceed slowly, and then finish rapidly.
The Project Life Cycle
Chapter
04
www.midocean.ae

## Slide 23
Projects are “born” when a need is identified by the customer.
Project life cycles vary in length, from a few weeks to several years.
Not all projects formally go through all four phases of the project life cycle.
The Project Life Cycle
Chapter
04
www.midocean.ae

## Slide 24
The first phase involves the identification of a need, problem, or opportunity.
The need and requirements are usually written by the customer into a document called a request for proposal (RFP).
Phases of the Project Life Cycle 1
Chapter
04
www.midocean.ae

## Slide 25
The second phase is the development of a proposed solution to the need or problem.
  This phase results in the submission of a proposal.
  The customer and the winning contractor negotiate and sign a contract (agreement).
Phases of the Project Life Cycle 2
Chapter
04
www.midocean.ae

## Slide 26
The third phase is performing the project.
  Different types of resources are utilized
  Results in the accomplishment of the project objective
Phases of the Project Life Cycle 3
Chapter
04
www.midocean.ae

## Slide 27
The final phase is terminating the project.
  Perform close-out activities
  Evaluate performance
  Invite customer feedback
Phases of the Project Life Cycle 4
Chapter
04
www.midocean.ae

## Slide 28
The accomplishment of important tasks and goals in organizations today is being achieved increasingly through the use of projects. A new kind of organization has emerged recently to deal with the accelerating growth in the number of multiple, simultaneously ongoing, and often interrelated projects in organizations
SELECTING PROJECTS TO MEET ORGANIZATIONAL OBJECTIVES
Chapter
04
www.midocean.ae

## Slide 29
There are many different methods for selecting projects, but they may be grouped into two fundamental types, nonnumeric and numeric.
Nonnumeric Selection Methods
Numeric Selection Methods
methods for selecting projects
Chapter
04
www.midocean.ae

## Slide 30
The Sacred Cow
The Operating/Competitive Necessity
Comparative Benefits
1. Nonnumeric Selection Methods
Chapter
04
www.midocean.ae

## Slide 31
Financial Assessment Methods
Financial Options and Opportunity Costs
Scoring Methods
2. Numeric Selection Methods
Chapter
04
www.midocean.ae

## Slide 32
As we note throughout this book, projects are all about uncertainty, and effective project management requires an ability to deal with uncertainty.
The time required to complete a project, the availability and costs of key resources, the timing of solutions to technological problems, a wide variety of macroeconomic variables, the whims of a client, the actions taken by competitors, even the likelihood that the output of a project will perform as expected
CONFRONTING UNCERTAINTY — THE MANAGEMENT OF RISK
Chapter
04
www.midocean.ae

## Slide 33
all these exemplify the uncertainties encountered when managing projects. While there are actions that may be taken to reduce the uncertainty, no actions of a PM can ever eliminate it.
Considering Uncertainty in Project Selection Decisions
Considering Disaster
Chapter
04
www.midocean.ae

## Slide 34
The Project Portfolio Process (PPP) attempts to link the organization ’ s projects directly to the goals and strategy of the organization. This occurs not only in the project ’ s initiation and planning phases, but also throughout the life cycle of the projects as they are managed and eventually brought to completion.
Thus, the PPP is also a means for monitoring and controlling the organization ’ s strategic projects,
THE PROJECT PORTFOLIO PROCESS
Chapter
04
www.midocean.ae

## Slide 35
Step 1: Establish a Project Council
Step 2: Identify Project Categories and Criteria
Step 3: Collect Project Data
Step 4: Assess Resource Availability
Step 5: Reduce the Project and Criteria Set
Step 6: Prioritize the Projects within Categories
Step 7: Select the Projects to Be Funded and Held in Reserve
Step 8: Implement the Process
THE PROJECT PORTFOLIO PROCESS
Chapter
04
www.midocean.ae

## Slide 36
THE PROJECT PORTFOLIO PROCESS
Chapter
04
www.midocean.ae
Projects are often subdivisions of major programs. Long - run success is determined by the organization ’ s portfolio of projects. Classified by the extent of innovation in product and process, there are four types of projects:
derivative, breakthrough, platform, and R & D projects. The actual mix of projects is a direct expression of the organization ’ s competitive strategy. A proper mix of project categories can help ensure its long - run competitive position. It is important for the Project Council or PMO to preplan project portfolio adjustments to respond to significant changes in the state of competition and other industrial crises.

## Slide 37
Thank You