## Slide 1
Prepared by Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Agile Project
Management
Lecture 3
PMG 622
Master of Project Management

## Slide 2
How is Agile similar to and different from Traditional PM Life Cycles?
Lecture 3
PMG 622
Agile Project Management
Eng. Ahmed Hussein, MBA, PfMP©, PMP©, CMP APMG
Prepared by

## Slide 3
Learning Objectives
Learn main characteristics of Traditional and Agile PM Life Cycles
Identify similarities between Traditional and Agile PM Life Cycles
Identify differences between Traditional and Agile PM Life Cycles
Lecture
03

## Slide 4
Key Points from Previous Lecture
Lecture
03
Agile Frameworks and Methodologies have similar processes that might differ in naming and terminology
The role of the Project Manager in Agile is a coach, facilitator, and enabler for success.
The Customer (Product Owner) is represented in the team
In Initiating and Planning an Agile project, we do Product Vision, Product Roadmap, and Product Backlog
In Executing an Agile project, we do Iteration Planning, User Stories, Iteration Backlog, and Iteration Retrospective, work is monitored through Daily Meetings, Burn Down, and Velocity Charts

## Slide 5
Main Characteristics of Traditional and Agile PM Life Cycles
Lecture
03

## Slide 6: The Four main Project Life Cycles
 | Predictive | Iterative | Incremental | Agile
Definition | A more traditional approach, with the bulk of planning occurring upfront, then executing in a single pass; a sequential process | An Approach that allows feedback for unfinished work to improve and modify that work | An approach that provides finished deliverables that the customer may be able to use immediately | An approach that is both iterative and incremental to refine work items and deliver frequently
Example | Building a house | Developing a new medication Product is released at the end only bit (product, technologies, methods might be adjusted along the way | Modifying100 processes in batches of 10 and implementing finished processes in each batch immediately | Developing a software application and adding features while testing different technologies
Definition Source: Project Management Institute, Agile Practice Guide, Project Management Institute Inc., 2017, Page 17.

## Slide 7: Comparing The four main Project Life Cycles
Source: Project Management Institute, Agile Practice Guide, Project Management Institute Inc., 2017, Page 18.
 | Predictive | Iterative | Incremental | Agile
Requirements | Fixed | Dynamic | Dynamic | Dynamic
# of Deliveries | Single delivery | Single delivery | Frequent smaller deliveries | Frequent small deliveries
Activities | Performed once for the entire project | Repeated until correct | Performed once for a given increment | Repeated until correct
Goal | Manage cost | Correctness of solution | Speed | Customer value via frequent deliveries and feedback
Change | Constrained as much as possible | Incorporated at periodic intervals |  | Incorporated in real-time delivery
Stakeholders | Involved at specific milestones | Are regularly involved |  | Continuously involved
Risks and Costs | Controlled by detailed planning or mostly knowable considerations | Controlled by progressively elaborating the plans with new information |  | Controlled as requirements and constraints emerge

## Slide 8: The Continuum of Project Lifecycles
Degree of Change
Frequency of Delivery
Incremental
Agile
Predictive
Iterative
Low
High
Low
High
Continuum
Source: Project Management Institute, Agile Practice Guide, Project Management Institute Inc., 2017, Page 19.

## Slide 9
Traditional PM Life Cycles
Lecture
03

## Slide 10
Traditional Project Management
Lecture
03
Called Linear, Predictive, or Waterfall and is Logical and intuitive.
Relies on heavy up-front analysis and documentation of the need and problems of the client.
A plan is formed, and a solution is constructed, monitoring is done through comparison to the original plan.

## Slide 11
Traditional Project Management
Lecture
03
Assumes nearly perfect information about the project goal and solution
We have multiple experiences with similar projects before or the project is just a simple well-defined effort.

## Slide 12: Traditional PM has 5 processes groups that interact and overlap
Monitoring and Controlling
Initiating
Planning
Executing
Closing

## Slide 13: Traditional PM addresses 10 areas from initiation to closing
10 Knowledge Areas
Project Integration Management
Project Scope Management
Project Schedule Management
Project Cost Management
Project Quality Management
Project Communication Management
Project Risk Management
Project Resources Management
Project Procurement Management
Project Stakeholder Management

## Slide 14
Traditional Project Management
Characteristics:
Lecture
03
Complete and clearly defined goal, solution, requirements, functions, and features
Few expected scope change requests
Routine and repetitive activities
Use of established templates
Detailed documentation

## Slide 15
Traditional Project Management
Strengths and Weaknesses:
Lecture
03
Strengths | Weaknesses
Easy to understand and manage as stages are clearly defined | Does not accommodate change well
Resource requirements are known from the start | Costs too much
Do not require the most skilled team members | Takes too long before any deliverables are produced
Team members do not have to be co-located | Requires complete and detailed plans
Detailed documentation facilitates transfer of knowledge and handover | Must follow a rigid sequence of processes
Client knows what to expect in terms of scope, cost, and timeframe | Does not focus on client value

## Slide 16
Brings some Agility into Traditional Project Management
Divides the projects into phases (or increments)
Allows for some scope change to happen between phases (or increments)
A need to release deliverables against a more aggressive schedule
Traditional Project Management
(Incremental/Phased) Characteristics:
Lecture
03

## Slide 17
Example:
            A real estate developer may modify design in next phases of its development
            A process re-engineering project may change the priority of remaining processes after each phase
Traditional Project Management
(Incremental/Phased) Characteristics:
Lecture
03

## Slide 18
Traditional Project Management
(Incremental/Phased) Strengths and Weaknesses:
Lecture
03
Strengths | Weaknesses
Produces business value early in the project | The team may not remain intact between increments
Enables better scheduling of scarce resources | Requires hand-off documentation between increments
Accommodates minor scope change requests between increments | Must follow a defined set pf processes
Offers product improvement opportunity | Increments must be defined based on function and feature dependencies rather than business value
More focused on client business value | Takes longer to execute

## Slide 19
Standard Waterfall Model
Rapid Waterfall Model (relies on doing parallel execution)
Staged Waterfall Model (incremental/phased)
Traditional Project Management
Models:
Lecture
03

## Slide 20: Benefits and Drawbacks of Traditional PM
Benefits
Predictability & Control
Suitable for complex projects
Well-defined roles and responsibilities
Extensive documentation
Drawbacks
Less flexible and adaptable
Less Customer Satisfaction
Slower Time to Market
Higher Risk of failing products

## Slide 21: Traditional PM Case Study: Apollo 11 Mission
Challenge:
The Apollo 11 mission was the first mission to land humans on the moon. It was a complex and challenging project with many risks involved. NASA needed to carefully plan and execute the mission in order to ensure its success.

## Slide 22: Traditional PM Case Study: Apollo 11 Mission
Solution:
  NASA used a traditional project management methodology to plan and execute the Apollo 11 mission. This involved developing a detailed project plan, identifying and mitigating risks, and carefully monitoring and controlling the project's progress. NASA also used a l team of specialists from different areas, which helped to ensure that all aspects of the mission were considered and developed in a coordinated manner.
Results:
  The Apollo 11 mission was a success. Neil Armstrong and Buzz Aldrin became the first humans to walk on the moon on July 20, 1969.

## Slide 23
Agile PM Life Cycles
Lecture
03

## Slide 24: Agile Practices and Processes
VISION
PRODUCT BACKLOG
ITERATION/SPRINT BACKLOG
INCREMENT/
RELEASE
PRODUCT
DAILY
MEETING
ITERATION/SPRINT 1-4 WEEKS
ITERATION/
SPRINT
REVIEW
ITERATION/SPRINT PLANNING
x 3-4
Initiation/Planning
Execution
Closing
PRODUCT Roadmap

## Slide 25: All Agile Models are incremental
Agile
Iterative
Adaptive
Designed to be flexible and adaptable to change. Needed for projects where the requirements are complex or uncertain, or where the team needs to be able to respond to feedback from users or stakeholders.
Break down the development process into smaller, manageable chunks called iterations.
At the end of each iteration, the team delivers a working increment of the product. This allows the team to get feedback from users early and often, and to make changes to the plan as needed.

## Slide 26
Complete and clearly defined goals
Solution is known but not in details or minor parts are not defined
Incomplete requirements
Some scope changes are expected
Uses prototypes to discover the complete solution
Agile Project Management (Iterative)
Characteristics:
Lecture
03

## Slide 27
Agile Project Management (Iterative)
Strengths and Weaknesses:
Lecture
03
Strengths | Weaknesses
Based on Just-In-Time Planning | Risks losing team between iterations
Accommodates change very well | Subject to losing priority between iterations
Focused on generating business value | Resource requirements are unclear at project launch
Client previews partial solutions for improvement | Requires a more actively involved client than traditional PM projects
Can process scope changes between iterations | Requires co-located teams
Adaptable to changing business conditions | Implementation of intermediate solutions can be problematic
 | Final solution cannot be defined at project start

## Slide 28
Iterative Structure
Just-In-Time Planning
Critical mission projects
Thrives on change through learning and discovery
Continuously reviewed and adapted to changing conditions
Agile Project Management (Adaptive)
Characteristics:
Lecture
03

## Slide 29
Scrum
Kanban
Feature-Driven Development (FDD)
Extreme Programming (XP)
Crystal
Scaled Agile Framework (SAFe)
Agile Project Management
Models:
Lecture
03

## Slide 30: Benefits and Drawbacks of Agile PM
Benefits
Drawbacks
Flexibility and adaptability
Higher Customer Satisfaction
Faster Time to Market
Lower Risk of failed products
Difficult to manage complex projects
Challenging to keep stakeholders aligned
Requires high-level of team commitment and discipline
Higher risk if team changes

## Slide 31: Agile Case Study: Developing and launching a new music streaming service
Challenge:
Spotify was entering a crowded market with established competitors such as iTunes and Pandora. The company needed to develop and launch its new streaming service quickly and efficiently, while also ensuring that it was high quality and met the needs of its target customers.

## Slide 32: Agile Case Study: Developing and launching a new music streaming service
Solution:
  Spotify used an agile project management methodology to develop and launch its new streaming service. This allowed the company to quickly iterate on its product and get feedback from customers early and often. Spotify also used a cross-functional team approach, which helped to ensure that all aspects of the product were considered and developed in a coordinated manner.
Results:
  Spotify's new music streaming service was launched on time and on budget. The service was well-received by customers and quickly became one of the most popular music streaming services in the world.

## Slide 33
Traditional and Agile PM Life Cycles Similarities and Differences
Lecture
03

## Slide 34: Similarities between Traditional and Agile PM
Both aim to deliver projects on time, on budget, and to scope
Both aim to satisfy the customer
Both require communication and collaboration between team members and stakeholders
Both involve planning, executing, monitoring and controlling
Both use techniques for prioritizing, estimating, and risk management
Both need a PM to lead the projects

## Slide 35: Differences between Traditional and Agile PM (1/2)
Characteristic | Traditional | Agile
Approach | Sequential | Iterative and incremental
Requirements | Gathered and frozen at the beginning of the project | Gathered and refined throughout the project
Planning | Detailed planning done at the beginning of the project | High-level at the beginning of the project, with detailed planning done on a rolling basis
Change management | Changes are difficult and expensive to make once the project plan is set | Changes are welcomed and accommodated throughout the project
Customer involvement | Customer involvement is typically highest at the beginning and end of the project | Close customer involvement throughout the project
Documentation | More emphasis on documentation | Less emphasis on documentation

## Slide 36: Differences between Traditional and Agile PM (2/2)
Characteristic | Traditional | Agile
Team | Specialized and needs to be coordinated | Cross-Functional, Self-Organizing and disciplined
PM | Manager and Leader | Coach, Facilitator, Leader
Customer Relationship | Contractual | Collaborative
End Product | Well known at the beginning | Emerges and known clearly at the end
Focus | Adherence to plan | Delivering customer value
Management | Formal | Casual

## Slide 37: When to use Traditional or Agile PM Life Cycle
Traditional | Agile
Requirements are well-defined and stable | Requirements are complex or uncertain
Projects is complex and require a high degree of predictability | Project needs to be delivered quickly
When regulations or industry standards require specific documentation | When customer feedback is important
When teams (or culture) are not familiar with agile methodologies | Teams are self-organizing and disciplined

## Slide 38
Key Points
Lecture
03
Traditional and Agile PM Life Cycles have many similarities and also differences
Selection of the RIGHT Life Cycle depends on Degree of Change, Frequency of Delivery, and Context of Project
Traditional Life Cycle can be Incremental (ex. Rolling out a system to many branches)
Agile Life Cycles are usually Incremental, Iterative, and Adaptive
Each Life Cycle has its Strengths, weaknesses, benefits and drawbacks

## Slide 39
Preparation for discussion panel:
Question for Discussion:
      Select a project from your organization.
      Identify is it following Traditional or Agile Life Cycle
      List strengths and weaknesses of this life cycle on the project.
For Discussion Panel
Lecture
03

## Slide 40
Before next lecture:
Read the Article:
“Implementing Agile in an Organization: A Six-Step Guide”
For Next Lecture
Lecture
03

## Slide 41
Thank You