## ورقة1
student name |  | Tariq Elqahtani | student Id | 2021206255
Risk Identification |  |  | Risk Analysis data |  | Risk Evaluation | Risk Treatment |  | Project
Risk ID | Category | Description | Impact | Probability | Trigger | Contingency Plan | Risk Owner | Project Name
1 | THREATS | Miscommunication and misunderstanding | high | high | Project delay | Using standard official channels. Holding regular meetings. | Project Manager | مشروع مترو الرياض
2 | THREATS | Fire hazards in working environments. | high | moderate | Project delay, Losing resources | Holding occupational safety awareness sessions. | Contractor Company | مشروع مترو الرياض
3 | OPPORTUNITIES | Improve Riyadh Public Transportation system | high | high | High volume of commuting | Accommodating a larger number of means of transportation. | Ministry of Transportation | مشروع مترو الرياض
4 | OPPORTUNITIES | High boost in economy growth | high | high | Contributing to vision 2030 | Contributing to vision 2030 | Ministry of Economy and Planning | مشروع مترو الرياض
5
6
7
8
من قائمة المشاريع المحددة, عليك تحديد وتحليل عدد 4 مخاطر فقط- منها 2 خطر من نوع تهديد و 2 خطر من نوع فرص

## ورقة2 (hidden)
THREATS | مشروع مترو الرياض | high | high
OPPORTUNITIES | مشروع الهايبر لوب | moderate | moderate
| مشروع مرآة للطاقة الشمسية | low | low